## PMR 1st sem 2020
PROVINCE OF RIZAL PROCUREMENT MONITORING REPORT as of 30 June 2020
Code | Procurement | PMO/ | Is this | Mode of | Actual Procurement Activity | [11 empty] | Source | ABC (Php) |  |  | Contract Cost (Php) |  |  | List of | Date of Receipt of Invitation | [5 empty] | Remarks
(UACS/PAP) | Program/Project | End-User | Early Procurement? | Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | BAC Res Date Recom Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | of Funds | Total | MOOE | CO | Total | MOOE | CO | Invited Observers | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (if applicable) | (Explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES
3000-000-1-2-11-399-006-001 | 1) Improvement/Repainting of Ynares Multi-purpose Covered Court and Stage at Antipolo Nat’l.High School, Brgy. Sta. Cruz, Antipolo City | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 30 C.D. | GF | 1926612.05 |  | 1926612.05 | 1907146.17 |  | 1907146.17 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-005 | 2) Repair/Repainting of Ynares School Bldg. at Pinugay Elem. School, Baras, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 40 | GF | 1469499.07 | 1469499.07 |  | 1454414.41 | 1454414.41 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-024 | 3) Construction of 6x30m Ynares Multi-Purpose Covered Court at San Roque Elem. School, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 64 | GF | 2499800.65 |  | 2499800.65 | 2474536.35 |  | 2474536.35 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000-000-1-1-51-001-003-004 | 4) Construction of Road Leading to Evacuation Center, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 108 | 20%DF | 1337278.24 |  | 1337278.24 | 1323636.11 |  | 1323636.11 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000-000-1-1-51-001-003-006 | 5) Asphalt Overlay of Baras-Pinugay Road, Brgy. San Salvador, Baras, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 116 | GF | 4999107.94 | 4999107.94 |  | 4948896.06 | 4948896.06 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
4000-400-1-1-11-104-003 | 6) Construction of Water System Level II, Brgy. Bangad. Binangonan, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 64 | 20%DF | 3237561.51 |  | 3237561.51 | 3212814.92 |  | 3212814.92 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-030/004 | 7) Imprv./Repair/Repainting of Ynares School Buildings, Covered Pathwalk, Fence at Binangonan & Angono Rizal a) Imprv./Repair of Ynares School Building at Guronasyon Foundation, Inc. National High School, Brgy. Bilibiran, Binangonan, Rizal b) Repair/Repainting of 2-Storey, 6-Rooms Ynares School Building/Covered Pathwalk/CHB Fence (Frontage) at Angono National Highj School, Brgy. Kalayaan, Angono, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 48 | GF | 2643165.8 | 2643165.8 |  | 2616249.78 | 2616249.78 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-600-1-2-11-511-004=008 | 8) Repair/Improvement Ynares Multi-Purpose Covered Court, Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 80 | GF | 1405070.3 | 1405070.3 |  | 1390246.15 | 1390246.15 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-600-1-2-11-511-004-018 | 9) Repainting/Impr. Of Ynares Multi-Purpose Covered Court, Stage, Comfort Room & Const. of Hand Washing Facility, Brgy. Macamot, Binangonan, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 60 | GF | 1657805.35 | 1657805.35 |  | 1642087.16 | 1642087.16 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000-000-1-1-51-001-012-026 | 10) Improvement/Construction of Drainage Canal at A. Mabini St., Brgy. Kaytome, Binangonan, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 64 | GF | 2287005.64 |  | 2287005.64 | 2264704.93 |  | 2264704.93 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000-000-1-1-51-001-012-051 | 11) Improvement/Concreting of Sapang – Malakaban Interconnecting Road, Brgy. Sapang/Malakaban, Binangonan Rizal | PEO |  | Public Bidding | 2020-02-10 | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 90 | 20%DF | 5601251.32 |  | 5601251.32 | 5544567.83 |  | 5544567.83 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000-000-1-1-51-001-012-052 | 12) Concrete Overlay and Improvement of Drainage Canal at St. Dominic Street, Brgy. Janosa, Binangonan, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 76 | 20%DF | 1299008.48 |  | 1299008.48 | 1286083.21 |  | 1286083.21 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-0057 | 13) Construction of 2-Storey, 2-Rooms Ynares School Building at Margarito Duavit Mem. National High School, Brgy. Pila-Pila, Binangonan, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 60 | SEF | 3795254.98 |  | 3795254.98 | 3756149.31 |  | 3756149.31 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-600-1-2-11-511-004-029 | 14) Improvement/Rehabilitation of Wharf, Brgy. Binitangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 90 | GF | 1672868.68 |  | 1672868.68 | 1655403.95 |  | 1655403.95 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-045 | 15) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Karangalan Elem. School, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 64 | GF | 829519.95 |  | 829519.95 | 820939.48 |  | 820939.48 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
6000-000-1-1-51-001-002-043 | 16) Construction of Stone Masonry for Slope Protection (portion) of Creek at Purok 1, Brgy. Bayugo, Jalajala Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 50 | 20%DF | 4363998.8 |  | 4363998.8 | 4322613.33 |  | 4322613.33 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
6000-000-1-1-51-001-002-044 | 17) Construction of Stone Masonry for Slope Protection (portion) of Creek at Purok 5, Brgy. Bayugo, Jalajala Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 60 | 20%DF | 4977619.58 |  | 4977619.58 | 4932470.32 |  | 4932470.32 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-016-033 | 18) Construction of Ynares Stage at Punta Elem. School, Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 107 | GF | 999988 |  | 999988 | 989890.9 |  | 989890.9 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-016-039 | 19) Repair/Repainting of School Building at Pagkalinawan Elem. School, Brgy. Pagkalinawan, Jalajala, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 137 | GF | 2811975.08 | 2811975.08 |  | 2781164.07 | 2781164.07 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000=000-1-1-51-001-002-053 | 20) Improvement/Concreting of N. Venadas Street, Sitio Labac, Brgy. San Guilermo, Morong, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 71 | GF | 1519139.41 |  | 1519139.41 | 1504038.75 |  | 1504038.75 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-051 | 21) Construction of 2-Storey, 2-Room Ynares School Building at Tomas Claudio Mem. Elem. School, Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 128 | GF | 3901808.1 |  | 3901808.1 | 3862552.38 |  | 3862552.38 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000-000-1-2-11-399-006-045 | 22) Construction of Stone Masonry for Slope Protection (portion) of Pililla River, Sitio Libid, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding | 2020-02-10 | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 80 | 20%DF | 7496658.44 |  | 7496658.44 | 7423926.38 |  | 7423926.38 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000-000-1-2-11-399-006-046 | 23) Construction of Stone Masonry For Slope Protection (portion) of Matagbak Creek, Sitio Matagbak, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2020-02-10 | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 54 | 20%DF | 5498422.45 |  | 5498422.45 | 5445838.4 |  | 5445838.4 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-600-1-2-11-511-004-037 | 24) Const. of 15x18m Ynares Multi-Purpose Covered Court (Rafter Type) at East Bellevue Residences Phase 1, Brgy. San Isidro, Rodrigues, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 60 | GF | 2647644.76 |  | 2647644.76 | 2623525.27 |  | 2623525.27 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-600-1-2-11-511-004-038 | 25) Construction of 15x24m Ynares Multi-Purpose Covered Court (Rafter Type) at East Bellevue Residences Phase 1, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 90 | GF | 3311347 |  | 3311347 | 3277457.12 |  | 3277457.12 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-600-1-2-11-511-004-014 | 26) Construction of Ynares Stage, Improvement of Ynares Multi-Purpose Covered Court at Eastwood Residence Phase 7-7A, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 60 | 20%DF | 1279303.29 |  | 1279303.29 | 1267779.44 |  | 1267779.44 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-600-1-2-11-511-004-031 | 27) Construction/Provision of Wash facilities (Water, Sanitation & Hygiene) at Eastwood Residence Blk.90 Lot 22 Phase 3, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 128 | GF | 819489.68 |  | 819489.68 | 810741.6 |  | 810741.6 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-022 | 28) Construction of 2-Storey, 4-Rooms at Marciana Catolos Mem. Elem. School, Brgy. Kay Buto, Tanay, Rizal | PEO |  | Public Bidding | 2020-02-10 | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 42 | GF | 7797504.19 |  | 7797504.19 | 7746730.7 |  | 7746730.7 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-019 | 29) Repair/Improvement of School Building, Fence & Const. of Gate at Daraetan National High School, Brgy. Daraetan, Tanay, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 60 | GF | 1528270.04 | 1528270.04 |  | 1511060.8 | 1511060.8 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3999-600-1-2-11-511-004-030 | 30) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) & Improvement of Ynares Multi-Purpose Covered Court at Brgy. Cuyambay & Brgy. Sampaloc, Tanay,Rizal a) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Sitio Jamboree, Brgy. Cuyambay b) Improvement of Yanres Multi-Purpose Covered Court at Sampaloc Elem. School, Brgy. Sampaloc | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 100 | GF | 1189486.82 |  | 1189486.82 | 1177086.64 |  | 1177086.64 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
86803465.6
Total Contract Price of Procurement Activities Conducted | [17 empty] | 85974751.92
Total Savings (Total Alloted Budget - Total Contract Price) | [17 empty] | 828713.68
8000-000-1-1-51-001-023/002 | 1) Overlaying of Roads at Angono & Cardona, Riza a) Asphalt Overlaying of E. Dela Paz St., Brgy. San Pedro, Angono b) Asphalt Overlaying of Ampucao Road (portion), Brgy. Iglesia, Cardona | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 70 | PDRRMF | 2533096.87 | 2533096.87 |  | 2507449.79 | 2507449.79 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-600-1-2-11-511-004-002/009 | 2) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court/Stage/ Multi-Purpose Buildings & Movable Bleachers at Angono & Binangonan, Rizal a) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court/Stage 2-Storey Multi-Purpose Building & Movable Bleachers at Bloomingdale Homes Subd. Brgy San Pedro Angono b) Improvement/Repair of Ynares Multi-Purpose Building (Brgy.Hall), Brgy. Tagpos, Binangonan | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 150 | GF | 1911009.65 | 1911009.65 |  | 1892339.97 | 1892339.97 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-600.1-2-11-511-004-007 | 3) Improvement/Repair of Ynares Multi-Purpose Covered Court, Brgy. Tabon,Binangonan Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 68 | GF | 1401717.25 |  | 1401717.25 | 1386740.96 |  | 1386740.96 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-600-1-2-11-511-004-019 | 4) Repair/Improvement of Stage & Construction of School Signage at Brgy. Janosa, Binangonan, Rizal a) Repair/Improvement of Stage at Brgy. Janosa b) Construction of School Signage at Janosa Elementary School, Brgy. Janosa | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 96 | GF | 810888.33 | 810888.33 |  | 801733.19 | 801733.19 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-599-006-031 | 5) Improvement/Repair of Ynares Multi-Purpose Covered Court, at Mahabang Parang Nattional High School, San Juan Heights, Brgy Mahabang Parang, Binangonan , Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 108 | GF | 669564.23 |  | 669564.23 | 662854.77 |  | 662854.77 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-043 | 6) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Lunsad Elem. School, Brgy. Lunsad, Binangonan, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 90 | GF | 853558.18 |  | 853558.18 | 844955.39 |  | 844955.39 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-047 | 7) Costruction of 2-Storeys, 6 rooms Ynares School Building at Ithan Elem. School Brgy.Ithan, Binangonan, Rizal | PEO |  | Public Bidding | 2020-06-02 | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 220 | SEF | 9994514.37 |  | 9994514.37 | 9894424.93 |  | 9894424.93 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-044 | 8) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Libid Elem. School, Brgy, Libid, Binangonan, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 80 | SEF | 1099427.01 |  | 1099427.01 | 1088015.01 |  | 1088015.01 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-048 | 9) Costruction of 2-Storeys, 6 rooms Ynares School Building at Kalinawan Elem. School Brgy.Kalinawan, Binangonan,Rizal | PEO |  | Public Bidding | 2020-06-02 | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 60 | SEF | 11045036.77 |  | 11045036.77 | 10934038.83 |  | 10934038.83 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-002 | 10) Concreting of Road at Saint Pancratius Street, Park Place Village, Brgy San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 60 | GF | 2479886.06 |  | 2479886.06 | 2454910.72 |  | 2454910.72 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-027 | 11) Asphalt overlaying/ Concrete Reblocking (portion) of A. Mabini St., Brgy. Sto. Nino, Cainta, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 60 | GF | 2089555.42 | 2089555.42 |  | 2068521.21 | 2068521.21 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-028 | 12) Asphalt overlaying of C. Cruz St., BrgySto. Nino, Cainta, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 52 | GF | 1298002.33 | 1298002.33 |  | 1284399.03 | 1284399.03 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-028 | 13) Repair/Repainting of Ynares School Buildings& Improvement of YnaresMulti-Purpose Covered Court at Evangelista Elem. School, Brgy. Evangelista Baras, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 70 | GF | 2149924.18 | 2149924.18 |  | 2128353.22 | 2128353.22 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-600-1-2-11-511-994-005 | 14) Repair of Roofing / Ceiling of Brgy.Hall Main and Repair of Flooring of Ynares Multi-Purpose Covered Court at Sitio Cinco, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 70 | GF | 795911.67 | 795911.67 |  | 787670.23 | 787670.23 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-511-001-002-004 | 15) Construction of Drainage Canal at I.D Julian Street, Brgy. Iglesia, Cardona, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 68 | GF | 898261.6 |  | 898261.6 | 889716.55 |  | 889716.55 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-600-1-2-11-511-004-010 | 16) Repair/Improvement of Ynares Multi-Purpose Building& Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Balibago & Brgy. Looc, Cardona, Rizal a) Repair/Improvement of 2-StoreyYnares Multi-Purpose Building Brgy. Balibago b) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court atTadlak Elementary School, Brgy. Looc | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 60 | GF | 627317.58 | 627317.58 |  | 620328.12 | 620328.12 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-055 | 17) Construction of 2-Storeys, 4-rooms, Ynares School Building at Mariano C. San Juan Elem. School Brgy. San Roque, Cardona,Rizal | PEO |  | Public Bidding | 2020-06-02 | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 70 | SEF | 7436499.19 |  | 7436499.19 | 7381382.22 | 7381382.22 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-030 | 18) Asphalt overlaying/ Concrete Reblocking (portion) of Segundo Pillas St., Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 100 | GF | 2294941.09 | 2294941.09 |  | 2271203.4 | 2271203.4 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-049 | 19) Improvement /Rehabiltation of E. Pillas Street (portion) Brgy Punta Jalajala, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 60 | GF | 1099746.64 |  | 1099746.64 | 1087203.4 |  | 1087203.4 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-010 | 20) Rehabiltation of Feeder Road at Sitio Calasio, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 92 | 20%DF | 2494259.17 |  | 2494259.17 | 2468198.94 |  | 2468198.94 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-003-010 | 21) Concreting (portion) of Rambo Feeder Road atBrgy. Halayhayin, Pililla, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 68 | 20%DF | 8475449.27 |  | 8475449.27 | 8391145.82 |  | 8391145.82 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-039 | 22) Asphalt overlaying and Concrete Reblocking (portion) of A. Luna St., Brgy. Quisa,Pililla Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 60 | GF | 2453181.97 | 2453181.97 |  | 2428187.04 | 2428187.04 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-040 | 23) Asphalt overlaying of San Antonio Road Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 40 | GF | 3583900.85 | 3583900.85 |  | 3536855.76 | 3536855.76 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-300-1-2-11-511-004-027 | 24) Repair/Repainting 2-Units 1-Storey Multi-Purpose Building (Health Center/ Day Care Center), Brgy. Imatong, Pililla, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 90 | GF | 1043241.57 | 1043241.57 |  | 1032531.46 | 1032531.46 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-017 | 25) Improvement of School Fence/Construction of School Arc & Repair of Gate & Artesian Well at Brgy. Bagumbayan & Brgy. Hulo, Pililla, Rizal a) Improvement of School Fence at Matagbak Elem. School. BrgyBagumbayan b) Construction of School Arc & Repair of Gate & Artesian Well at Hulo Elem. School. Brgy. Hulo | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 72 | GF | 729129.55 |  | 729129.55 | 721355.1 |  | 721355.1 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-300-1-2-11-51-006-032 | 26) Construction /Provision of Wash facilities (Water, Sanitation & Hygiene) at Eastwood Residences. Brgy. San Isidro, Rodriguez, Rizal a) Construction /Provision of Wash facilities (Water, Sanitation & Hygiene) at Eastwood Residences Phase 7-7A, Brgy. San Isidro b) Construction /Provision of Wash facilities (Water, Sanitation & Hygiene) at Eastwood Residences Phase 4, Brgy San Isidro | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 70 | GF | 1679214.25 |  | 1679214.25 | 1665055.72 |  | 1665055.72 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-300-1-2-11-511-004-036 | 27) Construction of Ynares Stage & Improvement of Ynares Multi-Purpose Covered Court at SouthVille 8C Phase 1K, Kasiglahan Village, Brgy. San. Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 136 | GF | 1799827.23 |  | 1799827.23 | 1783129.58 |  | 1783129.58 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-052 | 28) Construction of 2-Storey, 8-Rooms Ynares School Building at Patiis Elem. School, Brgy. Malanday, San Mateo, Rizal | PEO |  | Public Bidding | 2020-06-02 | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 80 | SEF | 11708530.37 |  | 11708530.37 | 11617648.72 |  | 11617648.72 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-059 | 29) Construction of 4-Storey, 8-Rooms Ynares School Building at Wawa Elem. School, Brgy. Wawa, Tanay, Rizal | PEO |  | Public Bidding | 2020-06-02 | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 50 | SEF | 17997702.28 |  | 17997702.28 | 17910009.76 |  | 17910009.76 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-046 | 30) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Bagumbayan Elem. School, Brgy. Bagumbayan, Teresa, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 76 | GF | 849471.16 |  | 849471.16 | 840450.23 |  | 840450.23 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-023 | 31) Asphalt Overlaying of L. Cerreno St., Macamot, Binangonan, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 60 | TF | 4499987.49 | 4499987.49 |  | 4455296.22 | 4455296.22 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-300-1-2-511-004-025 | 1) Repair/Improvement of Ynares Multi-Purpose Covered Court & Repair of Comfort Room at Brgy. San Jose, Brgy. Dalig, & Brgy. Mayamot, Antipolo City a). Repair/Improvement of Ynares Multi-Purpose Covered Court at Sitio Hinapao, Brgy. San Jose b) Improvement of Ynares Multi-Purpose Covered Court at Sitio Kamatisan, Brgy. Dalig c) Repair of 2-Seater Comfort Room at Ynares Multi-Purpose Covered Court , Town & Country Executive Village, Brgy. Mayamot | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 100 | GF | 798,836.65 | 798,836.65 |  | 790990.35 | 790990.35 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-040 | 2) Improvement (Provision of Tiles) of School Buildings at San Vicente Elem. School, Brgy. San Vicente, Angono, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 82 | SEF | 563000.1 |  | 563000.1 | 557812.84 |  | 557812.84 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-300-1-2-511-004-024 | 3) Repainting/Improvement of Ynares Multi-Purpose Covered Court & Construction of Comfort Room at Rainbow Village I, Brgy. Kalayaan, Angono, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 134 | 20%DF | 1349140.11 | 1349140.11 |  | 1336342.64 | 1336342.64 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-001-002-056 | 4) Improvement/Construction of Stone Masonry for Slope Protection and Concreting of Creek bed, Brgy. Malakaban, Binangonan, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 80 | 20%DF | 3111979 | 3111979 |  | 3080962.17 | 3080962.17 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-2-11-399-006 | 5) Improvement of School Building, Concreting of Ground & Construction of Gate at Darangan Elem. School, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 140 | SEF | 774019.6 |  | 774019.6 | 766070.48 |  | 766070.48 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-300-1-2-11-511-004-006 | 6) Improvement/Repair of Ynares Multi-Purpose Covered Court, Brgy. Pilapila, Binangonan, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 80 | GF | 1475316.45 |  | 1475316.45 | 1460416.45 |  | 1460416.45 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-2-11-399-006=041 | 7) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Casimiro A. Ynares, Sr. Elem. School, Brgy. Mambog, Binangonan, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 60 | GF | 999613.24 |  | 999613.24 | 988556.64 |  | 988556.64 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-2-11-399-006-042 | 8) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Bangad Elem. School, Brgy. Bangad, Binangonan, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 60 | GF | 973773.75 |  | 973773.75 | 963809.26 |  | 963809.26 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-2-211-399-006-058 | 9) Construction of 2-Storey, 10-Rooms, Ynares School Building at Don Jose Ynares, Sr. Mem. School, Brgy. San Carlos, Binangonan, Rizal | PEO |  | Public Bidding | 2020-06-08 | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 60 | SEF | 17099800.67 |  | 17099800.67 | 17011690.29 |  | 17011690.29 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-001-002-003 | 10) Improvement/Concreting of Burbank Street (Area 10 &11) at Brookside Hills Subd.,Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 76 | 20%DF | 4498938.88 |  | 4498938.88 | 4453857.07 |  | 4453857.07 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-2-11-399-006-049 | 11) Construction of 4-Storey, 8-Rooms, Ynares School Building at Rosario Elem. School, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding | 2020-06-08 | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 76 | SEF | 17915053.01 |  | 17915053.01 | 17814208.57 |  | 17814208.57 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-300-1-2-11-511-004-004 | 12) Replacement of CHB Wall & Steel Matting Fence at Rotary Day Care Center, Southville 9 Phase I, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 70 | GF | 749901.36 | 749901.36 |  | 742324.71 | 742324.71 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-300-1-2-11-511-004-028 | 13) Construction of Perimeter Fence of Rural Health Unit at Southville 9 Phase 2, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 100 | GF | 1494341.4 |  | 1494341.4 | 1479243.72 |  | 1479243.72 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-2-11-399-006-050 | 14) Construction of 2-Storey, 8-Rooms, Ynares School Building at Looc Elem. School, Brgy. Looc, Cardona, Rizal | PEO |  | Public Bidding | 2020-06-08 | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 90 | SEF | 11799906.51 |  | 11799906.51 | 11719503.61 |  | 11719503.61 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-002-006 | 15) Rehabilitation/Improvement of Road at Sitio Pinagkitran, Brgy. Boor, Cardona, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 100 | GF | 1997935.84 |  | 1997935.84 | 1977575.89 |  | 1977575.89 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-002-007 | 16) Rehabilitation/Concreting of Bayanihan Street, Brgy. 3rd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 60 | GF | 1605821.75 |  | 1605821.75 | 1589303.18 |  | 1589303.18 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-002-034 | 17) Asphalt Overlaying of A. Kalaw Street, Sitio Sambungan, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 70 | GF | 1888518.34 | 1888518.34 |  | 1869366.44 | 1869366.44 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-002-029 | 18) Asphalt Overlaying/Concrete Reblocking (portion) of Serafin Reyes Street, Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 70 | GF | 1349834.11 | 1349834.11 |  | 1335683.31 | 1335683.31 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-1-11-104-005 | 19) Construction of 2-Units Artesian Well, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 162 | 20%DF | 519636.54 |  | 519636.54 | 514479.12 |  | 514479.12 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-003-009 | 20) Concreting (portion) of Road at Pililla GK Village, Pililla, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 70 | 20%DF | 1711067.4 |  | 1711067.4 | 1604140.49 |  | 1604140.49 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-003-009 | 21) Construction of Ynares Stage at Phase 2 Eastwood Greenview Subd., Brgy. San Isidro, Rodriguez, Rizal, | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 100 | 20%DF | 999951.42 |  | 999951.42 | 990783.04 |  | 990783.04 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-001-002-011 | 22) Concreting/Construction of Drainage Canal of Road at DaangTubo East, Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 72 | 20%DF | 979204.85 |  | 979204.85 | 968783.6 |  | 968783.6 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-300-1-2-11-399-006-019 | 23) Repair of Various Ynares School Building at Tanay National High School, Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 60 | SEF | 4531339.74 |  | 4531339.74 | 4484852.04 |  | 4484852.04 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-2-11-399-006-056 | 24) Construction of 2-Storey, 6-Rooms, Ynares School Building at Abuyod Elem. School, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding | 2020-06-08 | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 80 | SEF | 9999649.57 |  | 9999649.57 | 9939303.32 |  | 9939303.32 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-300-1-2-11-511-004-022 | 25) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Dalig, Teresa, Rizal a) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Sitio Abuyod, Brgy. Dalig b) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Carissa Homes East II, Brgy. Dalig c) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Pantay National High School, Brgy. Dalig d) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Abuyod Elem. School, Brgy. Dalig | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 80 | GF | 1179678.71 |  | 1179678.71 | 1168963.89 |  | 1168963.89 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
4000-400-1-1-11-104-004 4000-400-1-1-11-104-002 | 1) Construction of Elevated Water Tank; Installation of Water Distribution Lines, & Construction of Artesian Well at Brgy. Bombong & Brgy. Rayap, Binangonan, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 100 | 20%DP | 1758102.71 |  | 1758102.71 | 1741025.84 |  | 1741025.84 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
4000-400-1-1-11-104-001 | 2) Construction of Water System Level III & Upgrading of Electrical Service Entrance at Sapang Elem. School, Brgy. Sapang, Binangonan, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 100 | 20%DP | 1999904.07 |  | 1999904.07 | 1980769.46 |  | 1980769.46 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-003-022 | 3) Upgrading of Maria Clara St., (B. Pag-Asa – Rizal Avenue), Brgy. Sta. Ana & Brgy. San Isidro, Taytay, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 189 | 20%DP | 7999202.6 |  | 7999202.6 | 7913758.96 |  | 7913769.96 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
3000-000-1-2-11-399-006-036 | 4) Construction of 15x30 m Ynares Multi-Purpose Covered Court at Taytay Senior High School, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 130 |  | 3949193.66 |  | 3949193.66 | 3908774.59 |  | 3908774.59 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
3000-000-1-2-11-399-006-026 | 5 Construction of Fence, Riprap & Concreting of School Ground at Taytay Senior High School, Brgu. Dolores, Taytay, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 110 |  | 2802678.95 |  | 2802678.45 | 2772417.24 |  | 2772417.24 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
3000-000-1-2-11-511-004-017 | 6) Construction of 2-Storey Tnares Multi-Purpose Building at Palmera I, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 136 | 20%DP | 3499748.62 |  | 3499748.62 | 3466211.26 |  | 3466211.26 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-002-033 | 7) Asphalt Overlaying/Concrete Reblocking (portion) of J.P. Burgos St., Sitio Sambungan, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 80 | GF | 5392786.74 |  | 5392886.74 | 5332278.55 |  |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-004 | 8) Construction/extension of Jalajala Municipal Building, Brgy. First District, Jalajala, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 120 | GF | 8254477.79 |  | 8254477.69 | 8.276,075.33 |  | 8176075.33 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-002-009 | 9) Improvement/Concreting (portion) of Road at Sitio Yapak, Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 72 | 20%DP | 2488574.95 |  | 2488574.95 | 3463628.46 |  | 2,463,,628.46 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-002-047 | 10) Construction of Stone Masonry Headwall (portion) of Wawa Boulevard, Brgy. Wawa, Pililla, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 60 | 20%DP | 1461827.85 |  | 1461827.85 | 1445720.73 |  | 1445710.72 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-002-035 | 11) Asphalt Overlaying and Concrete Reblocking (portion) of Sitio Bulacan I Road, Brgy. Bagumbayan, Pililla, | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 84 | GF | 4199474.71 |  | 4199474.71 | 4144565.49 |  |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-002-056 | 12) Asphalt Overlaying and Concrete Reblocking (portion) of Sitio Ligua Road, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 80 | GF | 4671419.43 |  | 4671419.43 | 4615131.64 | 4615131.64 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-004-002-037 | 13) Asphalt Overlaying and Concrete Reblocking (portion) of Sitio Lipat Lipat Road, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 84 | GF | 6175634.09 |  | 6175634.09 | 6101172.51 | 4615131.64 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-002-038 | 14) Asphalt Overlaying and Concrete Reblocking (portion) of P. Oleta St., Brgy. Wawa, Pililla, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 76 | GF | 4166641.1 |  | 4166641.1 | 4112258.22 | 4112258.22 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
3000-000-1-2-11-399-006-014 | 15) Repair/Repainting of Ynares School Bldg. at Virgilio B. Melendres Elem. School, Brgy. Takungan, Pililla, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 72 | SEF | 1865092.45 |  | 2865092.45 | 1846175.36 | 1846175.36 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-013 | 16) Asphalt Overlaying of Various Roads at Bancom Life Homes, Brgy. Gulod Malaya, San Mateo, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 100 | GF | 14317638.31 |  | 14317638.31 | 14317638.31 |  |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-039 | 17) Construction of Ynares Multi-Purpose Covered Court (Rafter Type) at Carissa Homes East-1, Brgy. Bagumbayan, Teresa, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 128 | 20%DP | 4188259.54 |  |  | 4146269.15 |  | 4146269.15 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-600-1-2-11-511-004-041 | 1) Construction of 2-Storey, Ynares Multi-Purpose Building (Senior Citizens’ Building) at Brgy. Poblacion Ibaba, Angono, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-025 | 2) As[halt Overlaying/Concrete Reblocking (portion) of F. Cequeña St., Brgy. Macamot, Binangonan, Rizal | PEO |  | Public Bidding | 2020-07-07 | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-010 | 3) Construction of 2-Storey, Multi-Purpose Building at Mahabang Parang Elem. School, Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-600-1-2-11-511-004-047 | 4) Construction of 2-Stprey Ynares Multi-Purpose Building (Senior Citizens’ Office) at Apple Village I, Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-004-019 | 5) Upgrading of B. Pag-Asa St. (Rizal Ave.-Isagani St.) Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-003-021 | 6) Improvement/Concreting of Road at Block 12, Sitio Tapayan, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-050 | 7) Improvement/Rehabilitation of Tenement Road, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-002 | 8) Construction of Ynares Stage at Taytay Senior High School, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-042 | 9) Construction of Stone Masonry for Slope Protection (portion) of Turnina River Ext., Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000=800-1-1-57-001-002-031 | 10) Asphalt Overlaying/Concrete Reblocking (portion) of Villanueva St., Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-032 | 11) Asphalt Overlaying/Concrete Reblocking (portion) of Emeterio Pillas St., Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-400-1-2-21-005-008-006 | 12) Repair of Ynares Municipal Hospital, Brgy. 1st District, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-013 | 13) Construction of Covered Pathwalk at Talaga Elem. School, Sitio Talaga, Brgy. Maybancal, Morong, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-600-1-2-11-511-004-013 | 14) Repair/Repainting of 2-Units, 2-Storey Ynares Multi-Purpose Building (Brgy. Hall.Day Care/Health Center) Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-041 | 15) Repair/Rehabilitation of Stone Masonry for Slope Protection of Pililla River (near M.L. Quezon St.), Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-600-1-2-511-004-021 | 16) Construction of 2-Storey, Ynares Multi-Purpose Building (Senior Citizen’s Hall) at Sitio Libid, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-034 | 17) Repair/Repainting of 3-Units, 2-Storey, 6-Rooms Ynares School Building at Quisao Elem. School, Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-003-012 | 18) Asphalt Overlaying/Concrete Reblocking (portion) of Col. S. Cruz St., Brgy. Balite and San Rafael, Rodriguez, Rizal | PEO |  | Public Bidding | 2020-07-07 | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-003-015 | 19) Asphalt Overlaying/Concrete Reblocking (portion) of Daang Bakal St., Rodriduez, Rizal | PEO |  | Public Bidding | 2020-07-07 | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-400-1-1-11-104-007 | 20) Construction of 2,000 Gallons Elevated Steel Water Tank at Balagbag Elem. School, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-022 | 21) Rehabilitation of Drainage Canal at GSIS Road (Daang Bakal) Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding | 2020-07-07 | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-003-015 | 22) Asphalt Overlaying/Concrete Reblocking (portion) of Mayor Jose F. Diaz Ave., Brgy. Gulod Malaya, San Mateo, Rizal | PEO |  | Public Bidding | 2020-07-07 | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-003-016 | 23) Rehabilitation/Improvement of Drainage Canal at Kambal Road, Brgy. Guitnang Bayan I and Guitnang Bayan II, San Mateo, Rizal | PEO |  | Public Bidding | 2020-07-07 | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-023 | 24) Construction of 17x30 Ynares Multi-Purpose Covered Court at Sampaloc National High School, Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-400-1-1-11-104-008 | 25) Construction of Water System Level II at Teresa District Jail, Sitio Buhangin, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-000-1-1-51-001-004-002 | 1) Rehabilitation of Floodway East embankment Road, Cainta-Taytay, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-0424 | 1a) Improvement/Repair of Ynares Multi-Purpose Covered Court & Improvement of Perimeter Fence at Bry. Sta. Cruz & Brgy. Dela Paz, Antipolo City a) Improvement of Ynares Multi-Purpose Covered Court & Improvement of Perimeter Fence at Brgy. Sta. Cruz & Brgy. Dela Paz, Antipolo City b) Repair of Ynares Multi-Purpose Covered Court at Banjers Village Phase 3, Brgy. Sta. Cruz c) Improvement of Perimeter Fence at Sitio Kabute, Brgy. Dela Paz | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-060 | 2) Construction of Ynares Stage at Dr. Vivencio Villamayor Integrated School, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-61 | 3) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Binangonan Central Elem. School, Brgy. Layunan, Binangonan, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-044 | 4) Improvement of Ynares Multi-Purpose Covered Court & Stage at Montevilla Subdivision, Brgy. Bilibiran, Binangonan, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-045 | 5) Construction of 2-Storey Ynares Multi-Purpose Building at Oliveros Compound, Kalawaan, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-046 | 6) Construction of 2-Storey Ynares Multi-Purpose Building at Jannsen Ville Subd., Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-400-1-1-11-104-010 | 7) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) Brgy. Tuna, Cardona, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-050 | 8) Repair of Ynares Multi-Purpose Covered Court, Brgy. Looc, Cardona, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-066 | 9) Repair/Repainting of Various Ynares School Building at Dalig Elem. School, Brgy. Dalig, Cardona, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-066 | 10) Concreting of creek bed at Purok I and Purok 2, Brgy. Balibago, Cardona, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-067 | 11) Improvement/Construction of Stone Masonry for Slope Protection of creek (portion), Brgy. Nagsulo, Cardona, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-011 | 12) Extension of Existing 2-Storey Ynares Multi-PurposecBuilding, Brgy. 3rd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-600-1-2-11-399-006-064 | 13) Construction of Covered Pathwalk at Punta Elem. School, Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 14) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Bagumbong Elem. School, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 15) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Sipsipin Elem. School, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-063 | 16) Concreting of School Ground & Construction of Artesian Well at Brgy. 2nd District& Brgy. Pagkalinawan, Jalajala, Rizal a) Concreting of School Ground (portion) at Jalajala National High School, Brgy. 2nd District b) Construction of 1-Unit Artesian Well, Brgy. Pagkalinawan | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-067 | 17) Repair/Repainting/Improvement of Ynares School Buildings, Ynares Stage and Ynares Multi-Purpose Covered Court at Hulo National High School, Brgy. Hulo, Pililla, Rizal a) Repair/Repainting of Ynares Schoo; Buildings, Ynares Stage and Ynares Multi-Purpose Covered Court at Hulo National High School, Brgy. Hulo b) Improvement of Ynares School Buildings, Ynares Stage and Ynares Multi-Purpose Covered Court at Hulo National High School, Brgy. Hulo | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 18) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Pililla Elem. School (Central), Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 19) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at URS Pililla, Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 20) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Hulo National High School, Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-400-940-001-003-001 | 21) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Hulo Elem. School, Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-400-40-001-003-001 | 22) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Malaya Elem. School, Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-000-1-1-51 | 23) Improvement/Construction of Drainage Canal at Block 3 Street and Block 17 Street, St. Peterville Subd., Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-040 | 24) Construction of Ynares Multi-Purpose Building & Construction of Drainage Canal at Rodriguez & Baras, Rizal a) Construction of 2-Storey Ynares Multi-Purpose Building at Eastwood Residences Phase 2, Brgy. San Isidro, Rodriguez b) Construction of Drainage Canal Cover at Trabajo Street, Brgy. San Jose, Baras | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-069 | 25) Improvement of Various School Buildings at Tagumpay National High School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-39-006-071 | 26) Construction of Perimeter Fence at Talaga Elem. School, Sitio Talaga, Brgy. Maybancal, Morong, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-070 | 27) Rehabilitation/Concreting of Zinia Street and Cardinal Ext. Street, Modesta Village, Sto. Niño, San Mateo, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-071 | 28) Concrete Reblocking of Cattleya Street, Modesta Village, Sto. Niño, San Mateo, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-900-900-1-2-40-940-011-003-001 | 29) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Sitio Aguho, Tanay, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-055 | 30) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Sitio Abuyod, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-000-1-1-51-001-004-002 | 1) Rehabilitation of Floodway East embankment Road, Cainta-Taytay, Rizal | PEO |  | Public Bidding | 2020-08-17 | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-0424 | 1a) Improvement/Repair of Ynares Multi-Purpose Covered Court & Improvement of Perimeter Fence at Bry. Sta. Cruz & Brgy. Dela Paz, Antipolo City a) Improvement of Ynares Multi-Purpose Covered Court at Bankers Village Phase 3, Brgy. Sta. Cruz b) Repair of Ynares Multi-Purpose Covered Court at Bankers Village Phase 3, Brgy. Sta. Cruz c) Improvement of Perimeter Fence at Sitio Kabute, Brgy. Dela Paz | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-060 | 2) Construction of Ynares Stage at Dr. Vivencio Villamayor Integrated School, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-61 | 3) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Binangonan Central Elem. School, Brgy. Layunan, Binangonan, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-044 | 4) Improvement of Ynares Multi-Purpose Covered Court & Stage at Montevilla Subdivision, Brgy. Bilibiran, Binangonan, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-045 | 5) Construction of 2-Storey Ynares Multi-Purpose Building at Oliveros Compound, Kalawaan, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-046 | 6) Construction of 2-Storey Ynares Multi-Purpose Building at Jannsen Ville Subd., Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-400-1-1-11-104-010 | 7) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) Brgy. Tuna, Cardona, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-050 | 8) Repair of Ynares Multi-Purpose Covered Court, Brgy. Looc, Cardona, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-066 | 9) Repair/Repainting of Various Ynares School Building at Dalig Elem. School, Brgy. Dalig, Cardona, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-066 | 10) Concreting of creek bed at Purok I and Purok 2, Brgy. Balibago, Cardona, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-067 | 11) Improvement/Construction of Stone Masonry for Slope Protection of creek (portion), Brgy. Nagsulo, Cardona, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-011 | 12) Extension of Existing 2-Storey Ynares Multi-PurposecBuilding, Brgy. 3rd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-600-1-2-11-399-006-064 | 13) Construction of Covered Pathwalk at Punta Elem. School, Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 14) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Bagumbong Elem. School, Jalajala, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 15) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Sipsipin Elem. School, Jalajala, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-063 | 16) Concreting of School Ground & Construction of Artesian Well at Brgy. 2nd District& Brgy. Pagkalinawan, Jalajala, Rizal a) Concreting of School Ground (portion) at Jalajala National High School, Brgy. 2nd District b) Construction of 1-Unit Artesian Well, Brgy. Pagkalinawan | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-067 | 17) Repair/Repainting/Improvement of Ynares School Buildings, Ynares Stage and Ynares Multi-Purpose Covered Court at Hulo National High School, Brgy. Hulo, Pililla, Rizal a) Repair/Repainting of Ynares Schoo; Buildings, Ynares Stage and Ynares Multi-Purpose Covered Court at Hulo National High School, Brgy. Hulo b) Improvement of Ynares School Buildings, Ynares Stage and Ynares Multi-Purpose Covered Court at Hulo National High School, Brgy. Hulo | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 18) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Pililla Elem. School (Central), Pililla, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 19) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at URS Pililla, Pililla, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 20) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Hulo National High School, Pililla, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-400-940-001-003-001 | 21) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Hulo Elem. School, Pililla, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-400-40-001-003-001 | 22) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Malaya Elem. School, Pililla, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-000-1-1-51 | 23) Improvement/Construction of Drainage Canal at Block 3 Street and Block 17 Street, St. Peterville Subd., Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-040 | 24) Construction of Ynares Multi-Purpose Building & Construction of Drainage Canal at Rodriguez & Baras, Rizal a) Construction of 2-Storey Ynares Multi-Purpose Building at Eastwood Residences Phase 2, Brgy. San Isidro, Rodriguez b) Construction of Drainage Canal Cover at Trabajo Street, Brgy. San Jose, Baras | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-069 | 25) Improvement of Various School Buildings at Tagumpay National High School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-39-006-071 | 26) Construction of Perimeter Fence at Talaga Elem. School, Sitio Talaga, Brgy. Maybancal, Morong, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-070 | 27) Rehabilitation/Concreting of Zinia Street and Cardinal Ext. Street, Modesta Village, Sto. Niño, San Mateo, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-071 | 28) Concrete Reblocking of Cattleya Street, Modesta Village, Sto. Niño, San Mateo, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-900-900-1-2-40-940-011-003-001 | 29) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Sitio Aguho, Tanay, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-055 | 30) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Sitio Abuyod, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-001 | 1) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Victoriaville Homes, Sitio Upper Lucban, Antipolo City | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-056 | 2) Construction of 2-Storey Multi-Purpose Building at Vermont Royale Executive Village, Brgy. Mayamot, Antipolo City | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-006 | 3) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Meralco 4th Home Village, Binangonan, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-057 | 4) Construction of Daycare Center & Health Center, Brgy. Macamot, Binangonan, Rizal | PEO |  | Public Bidding | 2020-08-24 | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-012-060 | 5) Improvement/Construction of Double Box Culvert along Oja Road and Construction of Stone Masonry for Slope Protection (portion) of Creek, Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-391-006-062 | 6) Construction of School Fence with Gate at Arinda Elem. School, Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-114 | 7) Repair/Repainting of 1-Storey, 5-Rooms, Ynares School Bldg., Construction of Riprap & Canal of Ynares Multi-Purpose Covered Court at Tuna Balibago National High School (Lambac Annex), Brgy. Lambac, Cardona, Rizal a) Repair/Repainting of 1-Storey, 5-Rooms Ynares School Building at Tuna Balibago National High School (Lambac Annex), Brgy. Lambac b) Construction of Riprap & Canal of Ynares Multi-Purpose Covered Court at Tuna Balibago National High School (Lambac Annex), Brgy. Lambac | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-003 | 8) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Looc Elem. School, Cardona, Rizal | PEO |  | Public Bidding | 24 Aug 20- | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-065 | 9) Improvement & Repainting of Ynares Multi-Purpose Covered Court at Brgy. Lambac, Cardona, Rizal a) Improvement of Ynares Multi-Purpose Covered Court at Brgy. Lambac b) Repainting of Ynares Multi-Purpose Covered Court at Brgy. Lambac | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-009-002 | 10) Construction of Multi-Purpose Provincial DRRM Center at Brgy. San Roqye, Cardona, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004 | 11) Repair of Ynares Multi-Purpose Covered Court, Brgy. Pagkalinawan, Jalajala, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-064 | 12) Construction of Stone Masonry for Slope Protection (portion) of Creek at Purok 5 (Ilog Mingming), Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding | 24 Aug 20- | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-065 | 13) Construction of Stone Masonry for Slope Protection (portion) of Creek at Purok 6, Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-069 | 14) Construction of Perimeter Fence of Barangay Hall Compound at Sitio Tabing Ilog, Brgy. San Guillermo, Morong, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-004-001 | 15) Construction of Multi-Purpose Provincial DRRM Center at Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding | 24 Aug 20- | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-006 | 16) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Bugarin Elem. School, Pililla, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-052A | 17) Repair/Repainting/Improvement of Ynares Multi-Purpose Building & School Mini Playground at Brgy. Niogan & Brgy. Quisao, Pililla, Rizal a) Repair/Repainting of Ynares Multi-Purpose Building at Brgy. Niogan b) Improvement of Ynares Multi-Purpose Building at Brgy. Niogan c) Repair/Repainting of School Mini Playground at Quisao Elem. School, Brgy. Quisao | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-012 | 18) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Geronimo Elem. School, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-013 | 19) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Southville 8B National High School, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-014 | 20) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Eastwood Greenview Phase 3B, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-070 | 21) Construction of 15x30m Ynares Multi-Purpose Covered Court (Rafter Type) at Villa Ana Maria Subd., Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-071 | 22) Construction of 2-Storey Ynares Multi-Purpose Bldg. at Kasiglahan Village (Phase IA), Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-136 | 23) Improvement of Ynares Multi-Purpose Covered Court at Manggahan Elem. School, Brgy. Manggahan, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-073 | 24) Construction of Ynares Stage at Congressville Subd., Brgy. Manggahan, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-600-1-2-11-511-004-053 | 25) Improvement/Rehabilitation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Macabud & Brgy. Mascap, Rodriguez, Rizal a) Improvement of Ynares Multi-Purpose Covered Court, Brgy. Macabud b) Rehabilitation of Electrical Lighting System of Ynares Multi-Purpose Covered Court, Brgy. Mascap | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-076 | 26) Improvement of Ynares Multi-Purpose Covered Court & Construction of Fence at Eastwood Residences, Phase 8/8A, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-399-006-137 | 27) Improvement of Ynares Multi-Purpose Covered Court & Construction of Welcome Arc at Brgy. San Jose & Brgy. San Isidro, Rodriguez, Rizal a) Improvement of Ynares Multi-Purpose Covered Court at Kasiglahan Village National High School, Brgy. San Jose b) Construction of 2-Units Welcome Arc at Southville 8C Elem. School, Brgy. San Isidro | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-078 | 28) Improvement of Ynares Multi-Purpose Covered Court & Construction of Comfort Room at Brgy. Sto. Niño & Brgy. Malanday, San Mateo, Rizal a) Improvement of Ynares Multi-Purpose Covered Court (Tennis Court) at Modesta Village, Brgy. Sto. Niño b) Construction of Comfort Room at Brgy. Malanday | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-080 | 29) Construction of 10x18m Ynares Multi-Purpose Covered Court (Badminton Court) at La Mar Village, Brgy. Guitnang Bayan II, San Mateo, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-076 | 1) Repair & Renovation of School canteen & H.E. Room at Janosa Elem. School, Brgy. Janosa, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King
3000-000-1-2-11-399-006-088 | 2) Construction of 2-Storey, 4-Rooms Ynares School Building at Pinagdilawan Elem. School, Brgy. Pinagdilawan, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-077 | 3) Construction of Feeding Center & Improvement of Ynares Stage at Janosa Elem. School, Brgy. Janosa, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-078 | 4) Repair/Repainting of 1-Storey, 2-Rooms BOD Building at Kinagatan Elem. School, Brgy. Kinagatan, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-082 | 5) Repair/Repainting of Ynares School Buildings at Binangonan Elem. School, Brgy. Batingan, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-511-004-058 | 6) Construction of 2-Storey Ynares Multi-Purpose Bldg. at Area 8 Greenwoods Executive Village, Brgy. San Andres, Cainta, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-090 | 7) Construction of 3-Storey Multi-Purpose Building at Arinda Rlem. School, Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-511-004-059 | 8) Construction/Improvement of Ynares Multi-Purpose Covered & Ynares Multi-Purpose Bldg. Cainta & Taytay, Rizal a) Construction of 17x30 m Ynares Volleyball/Badminton Court at Area 8, Greenwoods Executive Village, Brgy. San Andres, Cainta b) Improvement of Ynares Multi-Purpose Covered Court at Area 8, Greenwoods Executive Village, Brgy./ San Juan, Cainta, Rizal c) Improvement of 2-Storey, Ynares Multi-Purpose Bldg. at Bagong Pag=Asa Elem. School, Brgy. San Juan, Taytay | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-399-006-100 | 9) Construction of Ynares Stage at Baras-Pinugay Elem. School (Annex), Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-399-006-101 | 10) Improvement of Ynares Multi-Purpose Covered Court at Baras-Pinugay National High School, Phase II, Southville 9, Ynares Village, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-511-004-061 | 11) Rehabilitation of Electrical Lighting System of Baras Gymnasium, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-399-006-102 | 12) Repair/Repainting of Ynares School Buildings at Santiago Elem. School, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-125 | 13) Construction of 2-Storey, 6-Rooms Ynares School Building at Tadlak Elem. School, Brgy. Looc, Cardona, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-511-004-063 | 14) Improvement of Ynares Multi-Purpose Covered Court at Brgy. Sampad, Cardona, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-122 | 15) Repair/Repainting of 1-Storey, 3-Rooms Ynares School Building at Bernardo F. San Juan National High School, Brgy. San Roque, Cardona, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-143 | 16) Construction of Side Protection & Improvement of Ynares Multi-Purpose Covered Court & Stage at Brgy. Calahan, Brgy. Boor & Brgy. Subay, Cardona, Rizal a) Construction of Side Protection of 2-Storey, 4-Rooms Ynares School Bldg. at Patunhay Calahan Elem. School, Brgy. Calahan b) Improvement of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Boor c) Improvement of Ynares Multi-Purpose Covered Court and Stage, Brgy. Subay | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-119 | 17) Improvement of Ynares Stage & Ground of Schools at Cardona & Morong, Rizal a) Improvement of Ynares Stage at Bernardo F. San Juan National High School, Brgy. San Roque, Cardona b) Improvement of Ground at Timoteo A. Reyes, Sr. Mem. Elem. School, Brgy. San Pedro, Morong | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
8000-800-1-1-51-001-002-063 | 18) Construction of Stone Masonry Wall of Creek (Along JICA Road), Brgy. Lubo, Jalajala, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-130 | 19) Construction of 4-Storey, 8-Rooms Ynares School Building at Timoteo A. Reyes, Sr. Mem. Elem. School, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-134 | 20) Construction of 2-Storey, 6-Rooms Ynares School Building at Virgilio Melendres Elem. School, Brgy. Takungan, Pililla, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
8000-800-1-1-51-001-003-012 | 21) Rehabilitation/Improvement of Various Streets at Amityville Subd., Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-600-1-2-11-511-004-016 | 22) Construction of 2-Storey Ynares Multi-Purpose Bldg. (Day Care Center) at Southville 8A Block 28, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
8000-800-1-1-51-001-003-012 | 23) Construction of Covered Pathwalk & Fence at Amityville Elem. School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-511-004-077 | 24) Repair/Repainting of Ynares Multi-Purpose Covered Court & Fence at N.T.A. Village, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
8000-000-1-1-51-001-002-012 | 25) Improvement/Concreting of Various Roads at Divine Mercy Village, Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
9000-900-1-2-40-940-001-001-001 | 26) Construction of Stone Masonry for Slope Protection of Ampid River, Brgy. Ampid I and Brgy. Ampid II, San Mateo, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-148 | 27) Construction of 2-Storey, 6-Rooms Ynares Ynares School Building at Silangan Elem. School (Buntong Palay Annex), Brgy. Silangan, san Mateo, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
8000-000-1-1-51-001-002-074 | 28) Rehabilitation/Asphalt Patching of Parking Area at Ynares Sports Arena (YSA), Pasig City | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
1000-000-1-1-11-003-005 | 29) Construction of Justice Building at Government Center, Sitio Cabading, Brgy. Inarawan, Antipolo City | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-400-1-2-21-005-008-003 | Construction of Rizal Provincial Hospital System (RPHS) Taytay Annex | PEO |  | Public Bidding |  | 30 Sep-6 Oct 20 | 2020-10-07 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-075 | 1a) Construction of 2-Storey, 4-Rooms Ynares School Building at San Vicente Elem. School, Brgy. San Vicente, Angono, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-079 | 2) Repair/Repainting of 1-Storey, 3-Rooms BOD Building at Kinagatan Elem. School, Brgy. Kinagatan, Binangonan, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-085 | 3) Construction of Ynares Stage at Sitio Mata Elem. School, Brgy. Palangoy, Binangonan, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-087 | 4) Repair/Repainting of 2-Storey, 6-Rooms Ynares School Bldg. at Macamot Elem. School, Brgy. Macamot, Binangonan, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-089 | 5) Repair/Repainting of Ynares School Building & Construction of Covered Pathwalk/Replacement of Gate at Cainta & Taytay, Rizal a) Repair.Repainting of 2-Storey, 6-Rooms Ynares School Building at Kabisig Elem. School, Brgy. San Andres, Cainta b) Construction of Covered Pathwalk/Replacement of Gate at Benjamin B. Esguerra Mem. National High School, Brgy. Sta. Ana, Taytay | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-093 | 6) Repair/Repainting of Ynares School Buildings at Muzon Elem. School, Brgy. Muzon, Taytay, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-095 | 7) Repair/Repainting of Ynares School Buildings at Casimiro A. Ynares Sr. Mem. Nat’l High School, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-096 | 8) Repair/Repainting of Ynares Multi-Purpose Covered Court, Concrete Bleacher & Stage at Brgy. Dolores & Brgy. San Juan, Taytay, Rizal a) Repair/Repainting of Ynares Multi-Purpose Covered Court, Concrete Bleacher & Stage at Casimiro A. Ynares Sr. Mem. Nat’l High School, Brgy. Dolores b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Kapalaran Elem. School, Brgy. San Juan | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
1000-000-1-1-11-003-006 | 9) Repair/Repainting of the Provincial Prosecutor’s Office, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
9000-900-1-2-40-940-001-002-009-003 | 10) Construction of Multi-Purpose Provincial DRRM Center at Motorpool Compound, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
8000-800-1-1-51-001-006 | 11) Construction of Building for Philippine National Police, Bureau of Jail Management & Penology and Bureau of Fire Protection at Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-104 | 12) Repair/Repainting of Ynares School Building at Baras National High School, Brgy. San Juan, Baras, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-106 | 13) Concreting of School Ground at Santiago Elem. School, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-107 | 14) Construction of Covered Pathwalk at Baras-Pinugay National High School (Phase 2), Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-110 | 15) Repair/Repainting of Ynares Multi-Purpose Covered Court at Baras-Pinugay National High School, Sitio Habitat, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-109 | 16) Installation of Steel Grills for School Building & Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. San Juan, Baras, Rizal a) Installation of Steel Grills for 4-Storey, 20-Rooms DepEd Building at Baras Senior High School, Brgy. San Juan b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Baras National High School, Brgy. San Juan | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-111 | 17) Improvement of Ynares Multi-Purpose Covered Court & Ynares Stage at Santiago Elem. School, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-105 | 18) Construction of Covered Pathwalk at Santiago Elem. School, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-114 | 19) Repair/Repainting of 2-Storey, 6-Rooms Ynares School Building at Bernardo F. San Juan National High School, Brgy. San Roque, Cardona, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-121 | 20) Repair/Repainting of 2-Storey, 4-Rooms Ynares School Building at Bernardo F. San Juan National High School, Brgy. San Roque, Cardona, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-300-1-1-11-104-011 | 21) Rehabilitation of Water System, Brgy. Pagkalinawan, Jalajala, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-129 | 22) Repair/Repainting of Ynares School Buildings at Brgy. San Pedro & Brgy. San Juan, Morong, Rizal a) Repair/Repainting of 2-Storey, 4-Rooms Ynares School Building at Timoteo A. Reyes Sr. Mem. Elem. School, Brgy. San Pedro b) Repair/Repainting of 2-Storey, 4-Rooms Ynares School Building at Roman Tantiongco Mem. Elem. School, Brgy. San Juan | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-132 | 23) Construction of Ynares Stage & Flagpole at Lagundi Elem. School, Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-135 | 24) Construction of Covered Pathwalk at Roman Tantiongco Mem. Elem. School, Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-138 | 25) Repair/Repainting of Ynares School Buildings at Montalban Heights National High School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-33000-000-1-2- | 26) Improvement/Repair/Repainting of Ynares School Building at Colegio de Montalban, Brgy. Sam Jose, Rodriguez, Rizal a) Improvement of 2-Storey, 10-Rooms Ynares School Building at Colegio de Montalban, Brgy. San Jose b) Repair/Repainting of 2-Storey, 10-Rooms Ynares School Building at Colegio de Montalban, Brgy. San Jose | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-142 | 27) Construction of 2-Storey, 6-Rooms Ynares School Building at Manggahan National High School, Brgy. Manggahan, Rodriguez, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
8000-000-1-1-51-001-002-048 | 28) Rehabilitation/Improvement of Drainage System of Various Streets, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-143 | 29) Repair/Repainting of School Buildings at Guitnang Bayan Elem. School, Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-145 | 30) Repair/Repainting of Ynares School Buildings & Construction of Comfort Room at Brgy. Gulod Malaya & Brgy. Ampid II, San Mateo, Rizal a) Repair/Repainting of Ynares School Buildings at Gulod Malaya Elem. School, Brgy. Gulod Malaya b) Construction of 2-Seater Comfort Room at Ampid National High School, Brgy. Ampid II | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
ON-GOING PROCUREMENT ACTIVITIES
8000-800-1-1-51-001-002-075 | 1) Construction of Flood Interceptor at Gate 1 and Sitio Kasoy entrance (along Sumulong Highway) of Kingsville Subd., Brgy. Mambugan, Antipolo City | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-400-1-1-51-001-003-001 | 2) Improvement of Roads at Southville 9, Brgy. San Jose, Antipolo City | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-400-1-1-51-001-002-014 | 3) Improvement of Roads at Brgy. Kaytome, Binangonan, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-400-1-1-51-001-002-015 | 4) Improvement of Upper Kasinay Road to Mabuhay Homes 2000, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-800-1-1-51-001-002-058 | 5) Improvement of Road at Mabuhay Homes 2000, Brgy. Pantok, Binangonan, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-000-1-2-11-399-006-078 | 6) Improvement of School Buildings & Repair/Repainting of Ynares Stage at Brgy. Kinagatan & Brgy. Bangad, Binangonan, Rizal a) Improvement of 1-Storey, 2-Rooms BOD Building at Kinagatan Elem. School, Brgy. Kinagatan b) Improvement of 1-Storey, 3-Rooms BOD Building at Kinagatan Elem. School, Brgy. Kinagatan c) Repair/Repainting of Ynares Stage at Bangad Elem. School, Brgy. Bangad | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-000-1-2-11-399-006--83 | 7) Improvement/Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Banagd & Brgy. Mambog, Binangonan, Rizal a) Improvement of Ynares Multi-Purpose Covered Court at Bangad Elem. School, Brgy. Bangad b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Casimiro A. Ynares, Sr. Elem. School, Brgy. Mambog, Binangonan, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-000-1-2-11-399-006-149 | 8) Construction of 4-Storey, 12-Rooms Ynares School Building at Darangan Elem. School, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-800-1-1-51-001-002-061 | 9) Improvement of London Street, Cypress Village, Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-800-1-1-51-001-002-076 | 10) Asphalt Overlaying of Taytay-Angono Coastal Road, Taytay, Angono, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-000-1-2-11-399-006-112 | 11) Construction of Fence & Installation of Steel Grills of Ynares School Building at Baras-Pinugay National High School, Sitio Habitat, Brgy. Pinugay, Baras, Rizal a) Construction of Fence at Baras-Pinugay National High School, Sitio Habitat, Brgy. Pinugay, Baras, Rizal b) Installation of Steel Grills for 4-Storey, 8-Rooms Ynares School Building at Baras-Pinugay National High School. Sitio Habitat, Brgy. Pinugay | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-300-1-2-11-511-004-082 | 12) Improvement/Repair/Repainting of Ynares Multi-Purpose Buildings at Jalajala & Cardona, Rizal a) Improvement of Ynares Multi-Purpose Building, Brgy. Bagumbong, Jalajala b) Repair/Repainting of Ynares Multi-Purpose Building, Brgy. Bagumbong, Jalajala c) Repair of 2-Storey Ynares Multi-Purpose Bldg. (Health & Day Care Center) Brgy. Looc, Cardona | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-000-1-1-51-001-001-007 | 13) Construction of Municipality Jail at Philippine National Police Compound, Brgy. 3rd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-300-1-2-11-511-004-084 | 14) Improvement/Repair/Repainting of Ynares Multi-Purpose Covered Court at Sitio Caingin, Brgy.San Juan. Morong, Rizal a) Improvement of Ynares Multi=Purpose Covered Court at Sitio Caingin, Brgy. San Juan b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Sitio Caingin, Brgy. San Juan | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-400-1-1-51-001-002-021 | 15) Improvement of Roads at Brgy. San Juan, Morong, RIzal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-000-1-2-11-399-006-127 | 16) Repair/Repainting of 1-Storey, 3-Rooms Ynares School Buildings at Timoteo A. Reyes Sr. Mem. Elem. School, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-400-1-1-51-001-002-017 | 17) Improvement of Roads at Avila Compound, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-400-1-1-51-001-002-018 | 18) Improvement of Circumferential Road, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-400-1-1-51-001-002-019 | 19) Improvement of Roads at Brgy. Takungan, Pililla, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-000-1-1-51-001-001-006 | 20) Construction of Jail Building for Bureau of Jail Management & Penology and National Bureau of Investigation at Pililla Municipal Compound, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-000-1-1-51-001-002-069 | 21) Construction of Box Culvert at Natividad Street, Looban, Brgy. Maly, San Mateo, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-000-1-2-11-399-006-144 | 22) Repair/Repainting of Multi-Purpose Covered Court & Stage, Ynares School Building at Brgy. Guitnang Bayan I & Brgy. Ampid, San Mateo, Rizal a) Repair/Repainting of Multi-Purpose Covered Court & Stage at Guitnang Bayan I Elem. Scool, Brgy. Guitnang Bayan I, San Mateo, Rizal b) Repair/Repainting of 2-Storey, 6-Rooms Ynares School Bldg. at Ampid National High School, Brgy. Ampid, San Mateo, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-800-1-1-51-001-004-007 | 1) Improvement of Nazarene Road, Antipolo City | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-009 | 2) Rehabilitation/Improvement of Marigman St., Antipolo City | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-001 | 3) Rehabilitation/Improvement of Roman Roxas Road, Antipolo-Teresa-Baras, Rizal | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-003 | 4I mprovement of LLDA Road, Cardona, Rizal | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-002 | 5) Rehabilitation/Improvement of Morong-Bombongan Road, Morong, Rizal | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-005 | 6) Improvement of Morong-Lagundi Road, Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-008 | 7) Rehabilitation/Improvement of Velasquez St., Taytay, Rizal | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-006 | 8) Rehabilitation/Improvement of L. Wood St., Taytay, Rizal | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-004 | 9) Improvement/Rehabilitation of Cabrera Road (Burol Road), Taytay, Rizal | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
3000-000-1-2-11-399-006-098 | 1) Construction of 2-Storey, 8-Rooms Ynares School Building at Tapayan Elem. School, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 7 Dec-13 Dec 20 | 2020-12-14 |  | 2020-12-28 | 2020-12-18 | 2020-12-28 |  | 2021-01-15 | 2021-01-25
3000-000-1-2-11-399-006-099 | 2) Construction of 4-Storey, 12-Rooms Ynares School Building at Dolores Elem. School, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 7 Dec-13 Dec 20 | 2020-12-14 |  | 2020-12-28 | 2020-12-18 | 2020-12-28 |  | 2021-01-15 | 2021-01-25
3000-000-1-2-11-399-006-123 | 3) Construction of 2-Storey, 10-Rooms Ynares School Building at Cardona Senior High School, Brgy. San Roque, Cardona, Rizal | PEO |  | Public Bidding |  | 7 Dec-13 Dec 20 | 2020-12-14 |  | 2020-12-28 | 2020-12-18 | 2020-12-28 |  | 2021-01-15 | 2021-01-25
3000-000-1-2-11-399-006-124 | 4) Construction of 2-Stoery, 4-Rooms Ynares School Building at Dalig Elem. School, Brgy. Dalig, Cardona, Rizal | PEO |  | Public Bidding |  | 7 Dec-13 Dec 20 | 2020-12-14 |  | 2020-12-28 | 2020-12-18 | 2020-12-28 |  | 2021-01-15 | 2021-01-25
3000-000-1-2-11-399-006-150 | 5) Construction of 4-Storey, 12-Rooms Ynares School Building at Antonio C. Esguerra Memorial National High School, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 7 Dec-13 Dec 20 | 2020-12-14 |  | 2020-12-28 | 2020-12-18 | 2020-12-28 |  | 2021-01-15 | 2021-01-25
3000-000-1-2-11-399-006-151 | 6) Relocation of Ynares Multi-Purpose Covered Court at Antonio C. Esguerra Memorial National High School, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 7 Dec-13 Dec 20 | 2020-12-14 |  | 2020-12-28 | 2020-12-18 | 2020-12-28 |  | 2021-01-15 | 2021-01-25
Total Alloted Budget of On-going Procurement Activities | [17 empty] | 277560833.5 | 34540331.92 | 239832341.44 | 248442841.36 | 55694441.98 | 190644231.48
| Prepared by: | [8 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
|  | MA. TERESA E. LASQUETY | [12 empty] | Engr. LUISITO G. MUNSOD | [8 empty] | HON. REBECCA A. YNARES
|  | Head - BAC Secretariat | [12 empty] | BAC Chairperson | [8 empty] | Governor

## PMR 2nd sem 2020
PROVINCE OF RIZAL PROCUREMENT MONITORING REPORT as of 30 June 2020
Code | Procurement | PMO/ | Is this | Mode of | Actual Procurement Activity | [11 empty] | Source | ABC (Php) |  |  | Contract Cost (Php) |  |  | List of | Date of Receipt of Invitation | [5 empty] | Remarks
(UACS/PAP) | Program/Project | End-User | Early Procurement? | Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | BAC Res Date Recom Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | of Funds | Total | MOOE | CO | Total | MOOE | CO | Invited Observers | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (if applicable) | (Explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES
3000-000-1-2-11-399-006-001 | 1) Improvement/Repainting of Ynares Multi-purpose Covered Court and Stage at Antipolo Nat’l.High School, Brgy. Sta. Cruz, Antipolo City | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 30 C.D. | GF | 1926612.05 |  | 1926612.05 | 1907146.17 |  | 1907146.17 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-005 | 2) Repair/Repainting of Ynares School Bldg. at Pinugay Elem. School, Baras, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 40 | GF | 1469499.07 | 1469499.07 |  | 1454414.41 | 1454414.41 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-024 | 3) Construction of 6x30m Ynares Multi-Purpose Covered Court at San Roque Elem. School, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 64 | GF | 2499800.65 |  | 2499800.65 | 2474536.35 |  | 2474536.35 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000-000-1-1-51-001-003-004 | 4) Construction of Road Leading to Evacuation Center, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 108 | 20%DF | 1337278.24 |  | 1337278.24 | 1323636.11 |  | 1323636.11 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000-000-1-1-51-001-003-006 | 5) Asphalt Overlay of Baras-Pinugay Road, Brgy. San Salvador, Baras, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 116 | GF | 4999107.94 | 4999107.94 |  | 4948896.06 | 4948896.06 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
4000-400-1-1-11-104-003 | 6) Construction of Water System Level II, Brgy. Bangad. Binangonan, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 64 | 20%DF | 3237561.51 |  | 3237561.51 | 3212814.92 |  | 3212814.92 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-030/004 | 7) Imprv./Repair/Repainting of Ynares School Buildings, Covered Pathwalk, Fence at Binangonan & Angono Rizal a) Imprv./Repair of Ynares School Building at Guronasyon Foundation, Inc. National High School, Brgy. Bilibiran, Binangonan, Rizal b) Repair/Repainting of 2-Storey, 6-Rooms Ynares School Building/Covered Pathwalk/CHB Fence (Frontage) at Angono National Highj School, Brgy. Kalayaan, Angono, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 48 | GF | 2643165.8 | 2643165.8 |  | 2616249.78 | 2616249.78 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-600-1-2-11-511-004=008 | 8) Repair/Improvement Ynares Multi-Purpose Covered Court, Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 80 | GF | 1405070.3 | 1405070.3 |  | 1390246.15 | 1390246.15 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-600-1-2-11-511-004-018 | 9) Repainting/Impr. Of Ynares Multi-Purpose Covered Court, Stage, Comfort Room & Const. of Hand Washing Facility, Brgy. Macamot, Binangonan, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 60 | GF | 1657805.35 | 1657805.35 |  | 1642087.16 | 1642087.16 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000-000-1-1-51-001-012-026 | 10) Improvement/Construction of Drainage Canal at A. Mabini St., Brgy. Kaytome, Binangonan, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 64 | GF | 2287005.64 |  | 2287005.64 | 2264704.93 |  | 2264704.93 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000-000-1-1-51-001-012-051 | 11) Improvement/Concreting of Sapang – Malakaban Interconnecting Road, Brgy. Sapang/Malakaban, Binangonan Rizal | PEO |  | Public Bidding | 2020-02-10 | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 90 | 20%DF | 5601251.32 |  | 5601251.32 | 5544567.83 |  | 5544567.83 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000-000-1-1-51-001-012-052 | 12) Concrete Overlay and Improvement of Drainage Canal at St. Dominic Street, Brgy. Janosa, Binangonan, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 76 | 20%DF | 1299008.48 |  | 1299008.48 | 1286083.21 |  | 1286083.21 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-0057 | 13) Construction of 2-Storey, 2-Rooms Ynares School Building at Margarito Duavit Mem. National High School, Brgy. Pila-Pila, Binangonan, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 60 | SEF | 3795254.98 |  | 3795254.98 | 3756149.31 |  | 3756149.31 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-600-1-2-11-511-004-029 | 14) Improvement/Rehabilitation of Wharf, Brgy. Binitangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 90 | GF | 1672868.68 |  | 1672868.68 | 1655403.95 |  | 1655403.95 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-045 | 15) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Karangalan Elem. School, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 64 | GF | 829519.95 |  | 829519.95 | 820939.48 |  | 820939.48 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
6000-000-1-1-51-001-002-043 | 16) Construction of Stone Masonry for Slope Protection (portion) of Creek at Purok 1, Brgy. Bayugo, Jalajala Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 50 | 20%DF | 4363998.8 |  | 4363998.8 | 4322613.33 |  | 4322613.33 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
6000-000-1-1-51-001-002-044 | 17) Construction of Stone Masonry for Slope Protection (portion) of Creek at Purok 5, Brgy. Bayugo, Jalajala Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 60 | 20%DF | 4977619.58 |  | 4977619.58 | 4932470.32 |  | 4932470.32 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-016-033 | 18) Construction of Ynares Stage at Punta Elem. School, Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 107 | GF | 999988 |  | 999988 | 989890.9 |  | 989890.9 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-016-039 | 19) Repair/Repainting of School Building at Pagkalinawan Elem. School, Brgy. Pagkalinawan, Jalajala, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 137 | GF | 2811975.08 | 2811975.08 |  | 2781164.07 | 2781164.07 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000=000-1-1-51-001-002-053 | 20) Improvement/Concreting of N. Venadas Street, Sitio Labac, Brgy. San Guilermo, Morong, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 71 | GF | 1519139.41 |  | 1519139.41 | 1504038.75 |  | 1504038.75 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-051 | 21) Construction of 2-Storey, 2-Room Ynares School Building at Tomas Claudio Mem. Elem. School, Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 128 | GF | 3901808.1 |  | 3901808.1 | 3862552.38 |  | 3862552.38 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000-000-1-2-11-399-006-045 | 22) Construction of Stone Masonry for Slope Protection (portion) of Pililla River, Sitio Libid, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding | 2020-02-10 | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 80 | 20%DF | 7496658.44 |  | 7496658.44 | 7423926.38 |  | 7423926.38 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
8000-000-1-2-11-399-006-046 | 23) Construction of Stone Masonry For Slope Protection (portion) of Matagbak Creek, Sitio Matagbak, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2020-02-10 | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 54 | 20%DF | 5498422.45 |  | 5498422.45 | 5445838.4 |  | 5445838.4 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-600-1-2-11-511-004-037 | 24) Const. of 15x18m Ynares Multi-Purpose Covered Court (Rafter Type) at East Bellevue Residences Phase 1, Brgy. San Isidro, Rodrigues, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 60 | GF | 2647644.76 |  | 2647644.76 | 2623525.27 |  | 2623525.27 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-600-1-2-11-511-004-038 | 25) Construction of 15x24m Ynares Multi-Purpose Covered Court (Rafter Type) at East Bellevue Residences Phase 1, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 90 | GF | 3311347 |  | 3311347 | 3277457.12 |  | 3277457.12 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-600-1-2-11-511-004-014 | 26) Construction of Ynares Stage, Improvement of Ynares Multi-Purpose Covered Court at Eastwood Residence Phase 7-7A, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 60 | 20%DF | 1279303.29 |  | 1279303.29 | 1267779.44 |  | 1267779.44 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-600-1-2-11-511-004-031 | 27) Construction/Provision of Wash facilities (Water, Sanitation & Hygiene) at Eastwood Residence Blk.90 Lot 22 Phase 3, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 128 | GF | 819489.68 |  | 819489.68 | 810741.6 |  | 810741.6 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-022 | 28) Construction of 2-Storey, 4-Rooms at Marciana Catolos Mem. Elem. School, Brgy. Kay Buto, Tanay, Rizal | PEO |  | Public Bidding | 2020-02-10 | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 42 | GF | 7797504.19 |  | 7797504.19 | 7746730.7 |  | 7746730.7 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3000-000-1-2-11-399-006-019 | 29) Repair/Improvement of School Building, Fence & Const. of Gate at Daraetan National High School, Brgy. Daraetan, Tanay, Rizal | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 60 | GF | 1528270.04 | 1528270.04 |  | 1511060.8 | 1511060.8 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
3999-600-1-2-11-511-004-030 | 30) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) & Improvement of Ynares Multi-Purpose Covered Court at Brgy. Cuyambay & Brgy. Sampaloc, Tanay,Rizal a) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Sitio Jamboree, Brgy. Cuyambay b) Improvement of Yanres Multi-Purpose Covered Court at Sampaloc Elem. School, Brgy. Sampaloc | PEO |  | Public Bidding |  | 11-17 Feb 20 | 2020-02-17 |  | 2020-02-28 | 2020-03-03 | 2020-03-09 |  | 2020-03-12 | 2020-03-20 | 2020-03-26 | 100 | GF | 1189486.82 |  | 1189486.82 | 1177086.64 |  | 1177086.64 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2020-02-11 |  | 2020-02-11
86803465.6
Total Contract Price of Procurement Activities Conducted | [17 empty] | 85974751.92
Total Savings (Total Alloted Budget - Total Contract Price) | [17 empty] | 828713.68
8000-000-1-1-51-001-023/002 | 1) Overlaying of Roads at Angono & Cardona, Riza a) Asphalt Overlaying of E. Dela Paz St., Brgy. San Pedro, Angono b) Asphalt Overlaying of Ampucao Road (portion), Brgy. Iglesia, Cardona | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 70 | PDRRMF | 2533096.87 | 2533096.87 |  | 2507449.79 | 2507449.79 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-600-1-2-11-511-004-002/009 | 2) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court/Stage/ Multi-Purpose Buildings & Movable Bleachers at Angono & Binangonan, Rizal a) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court/Stage 2-Storey Multi-Purpose Building & Movable Bleachers at Bloomingdale Homes Subd. Brgy San Pedro Angono b) Improvement/Repair of Ynares Multi-Purpose Building (Brgy.Hall), Brgy. Tagpos, Binangonan | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 150 | GF | 1911009.65 | 1911009.65 |  | 1892339.97 | 1892339.97 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-600.1-2-11-511-004-007 | 3) Improvement/Repair of Ynares Multi-Purpose Covered Court, Brgy. Tabon,Binangonan Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 68 | GF | 1401717.25 |  | 1401717.25 | 1386740.96 |  | 1386740.96 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-600-1-2-11-511-004-019 | 4) Repair/Improvement of Stage & Construction of School Signage at Brgy. Janosa, Binangonan, Rizal a) Repair/Improvement of Stage at Brgy. Janosa b) Construction of School Signage at Janosa Elementary School, Brgy. Janosa | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 96 | GF | 810888.33 | 810888.33 |  | 801733.19 | 801733.19 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-599-006-031 | 5) Improvement/Repair of Ynares Multi-Purpose Covered Court, at Mahabang Parang Nattional High School, San Juan Heights, Brgy Mahabang Parang, Binangonan , Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 108 | GF | 669564.23 |  | 669564.23 | 662854.77 |  | 662854.77 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-043 | 6) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Lunsad Elem. School, Brgy. Lunsad, Binangonan, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 90 | GF | 853558.18 |  | 853558.18 | 844955.39 |  | 844955.39 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-047 | 7) Costruction of 2-Storeys, 6 rooms Ynares School Building at Ithan Elem. School Brgy.Ithan, Binangonan, Rizal | PEO |  | Public Bidding | 2020-06-02 | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 220 | SEF | 9994514.37 |  | 9994514.37 | 9894424.93 |  | 9894424.93 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-044 | 8) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Libid Elem. School, Brgy, Libid, Binangonan, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 80 | SEF | 1099427.01 |  | 1099427.01 | 1088015.01 |  | 1088015.01 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-048 | 9) Costruction of 2-Storeys, 6 rooms Ynares School Building at Kalinawan Elem. School Brgy.Kalinawan, Binangonan,Rizal | PEO |  | Public Bidding | 2020-06-02 | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 60 | SEF | 11045036.77 |  | 11045036.77 | 10934038.83 |  | 10934038.83 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-002 | 10) Concreting of Road at Saint Pancratius Street, Park Place Village, Brgy San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 60 | GF | 2479886.06 |  | 2479886.06 | 2454910.72 |  | 2454910.72 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-027 | 11) Asphalt overlaying/ Concrete Reblocking (portion) of A. Mabini St., Brgy. Sto. Nino, Cainta, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 60 | GF | 2089555.42 | 2089555.42 |  | 2068521.21 | 2068521.21 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-028 | 12) Asphalt overlaying of C. Cruz St., BrgySto. Nino, Cainta, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 52 | GF | 1298002.33 | 1298002.33 |  | 1284399.03 | 1284399.03 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-028 | 13) Repair/Repainting of Ynares School Buildings& Improvement of YnaresMulti-Purpose Covered Court at Evangelista Elem. School, Brgy. Evangelista Baras, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 70 | GF | 2149924.18 | 2149924.18 |  | 2128353.22 | 2128353.22 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-600-1-2-11-511-994-005 | 14) Repair of Roofing / Ceiling of Brgy.Hall Main and Repair of Flooring of Ynares Multi-Purpose Covered Court at Sitio Cinco, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 70 | GF | 795911.67 | 795911.67 |  | 787670.23 | 787670.23 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-511-001-002-004 | 15) Construction of Drainage Canal at I.D Julian Street, Brgy. Iglesia, Cardona, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 68 | GF | 898261.6 |  | 898261.6 | 889716.55 |  | 889716.55 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-600-1-2-11-511-004-010 | 16) Repair/Improvement of Ynares Multi-Purpose Building& Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Balibago & Brgy. Looc, Cardona, Rizal a) Repair/Improvement of 2-StoreyYnares Multi-Purpose Building Brgy. Balibago b) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court atTadlak Elementary School, Brgy. Looc | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 60 | GF | 627317.58 | 627317.58 |  | 620328.12 | 620328.12 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-055 | 17) Construction of 2-Storeys, 4-rooms, Ynares School Building at Mariano C. San Juan Elem. School Brgy. San Roque, Cardona,Rizal | PEO |  | Public Bidding | 2020-06-02 | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 70 | SEF | 7436499.19 |  | 7436499.19 | 7381382.22 | 7381382.22 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-030 | 18) Asphalt overlaying/ Concrete Reblocking (portion) of Segundo Pillas St., Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 100 | GF | 2294941.09 | 2294941.09 |  | 2271203.4 | 2271203.4 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-049 | 19) Improvement /Rehabiltation of E. Pillas Street (portion) Brgy Punta Jalajala, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 60 | GF | 1099746.64 |  | 1099746.64 | 1087203.4 |  | 1087203.4 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-010 | 20) Rehabiltation of Feeder Road at Sitio Calasio, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 92 | 20%DF | 2494259.17 |  | 2494259.17 | 2468198.94 |  | 2468198.94 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-003-010 | 21) Concreting (portion) of Rambo Feeder Road atBrgy. Halayhayin, Pililla, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 68 | 20%DF | 8475449.27 |  | 8475449.27 | 8391145.82 |  | 8391145.82 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-039 | 22) Asphalt overlaying and Concrete Reblocking (portion) of A. Luna St., Brgy. Quisa,Pililla Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 60 | GF | 2453181.97 | 2453181.97 |  | 2428187.04 | 2428187.04 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-040 | 23) Asphalt overlaying of San Antonio Road Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 40 | GF | 3583900.85 | 3583900.85 |  | 3536855.76 | 3536855.76 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-300-1-2-11-511-004-027 | 24) Repair/Repainting 2-Units 1-Storey Multi-Purpose Building (Health Center/ Day Care Center), Brgy. Imatong, Pililla, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 90 | GF | 1043241.57 | 1043241.57 |  | 1032531.46 | 1032531.46 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-017 | 25) Improvement of School Fence/Construction of School Arc & Repair of Gate & Artesian Well at Brgy. Bagumbayan & Brgy. Hulo, Pililla, Rizal a) Improvement of School Fence at Matagbak Elem. School. BrgyBagumbayan b) Construction of School Arc & Repair of Gate & Artesian Well at Hulo Elem. School. Brgy. Hulo | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 72 | GF | 729129.55 |  | 729129.55 | 721355.1 |  | 721355.1 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-300-1-2-11-51-006-032 | 26) Construction /Provision of Wash facilities (Water, Sanitation & Hygiene) at Eastwood Residences. Brgy. San Isidro, Rodriguez, Rizal a) Construction /Provision of Wash facilities (Water, Sanitation & Hygiene) at Eastwood Residences Phase 7-7A, Brgy. San Isidro b) Construction /Provision of Wash facilities (Water, Sanitation & Hygiene) at Eastwood Residences Phase 4, Brgy San Isidro | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 70 | GF | 1679214.25 |  | 1679214.25 | 1665055.72 |  | 1665055.72 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-300-1-2-11-511-004-036 | 27) Construction of Ynares Stage & Improvement of Ynares Multi-Purpose Covered Court at SouthVille 8C Phase 1K, Kasiglahan Village, Brgy. San. Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 136 | GF | 1799827.23 |  | 1799827.23 | 1783129.58 |  | 1783129.58 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-052 | 28) Construction of 2-Storey, 8-Rooms Ynares School Building at Patiis Elem. School, Brgy. Malanday, San Mateo, Rizal | PEO |  | Public Bidding | 2020-06-02 | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 80 | SEF | 11708530.37 |  | 11708530.37 | 11617648.72 |  | 11617648.72 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-059 | 29) Construction of 4-Storey, 8-Rooms Ynares School Building at Wawa Elem. School, Brgy. Wawa, Tanay, Rizal | PEO |  | Public Bidding | 2020-06-02 | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 50 | SEF | 17997702.28 |  | 17997702.28 | 17910009.76 |  | 17910009.76 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-046 | 30) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Bagumbayan Elem. School, Brgy. Bagumbayan, Teresa, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 76 | GF | 849471.16 |  | 849471.16 | 840450.23 |  | 840450.23 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
8000-000-1-1-51-001-002-023 | 31) Asphalt Overlaying of L. Cerreno St., Macamot, Binangonan, Rizal | PEO |  | Public Bidding |  | 4-10 Jun 20 | 2020-06-10 |  | 2020-06-23 | 2020-06-26 | 2020-07-02 | 2020-07-08 | 2020-07-15 | 23-Jult-20 |  | 60 | TF | 4499987.49 | 4499987.49 |  | 4455296.22 | 4455296.22 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-300-1-2-511-004-025 | 1) Repair/Improvement of Ynares Multi-Purpose Covered Court & Repair of Comfort Room at Brgy. San Jose, Brgy. Dalig, & Brgy. Mayamot, Antipolo City a). Repair/Improvement of Ynares Multi-Purpose Covered Court at Sitio Hinapao, Brgy. San Jose b) Improvement of Ynares Multi-Purpose Covered Court at Sitio Kamatisan, Brgy. Dalig c) Repair of 2-Seater Comfort Room at Ynares Multi-Purpose Covered Court , Town & Country Executive Village, Brgy. Mayamot | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 100 | GF | 798,836.65 | 798,836.65 |  | 790990.35 | 790990.35 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-04 |  | 2020-06-04
3000-000-1-2-11-399-006-040 | 2) Improvement (Provision of Tiles) of School Buildings at San Vicente Elem. School, Brgy. San Vicente, Angono, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 82 | SEF | 563000.1 |  | 563000.1 | 557812.84 |  | 557812.84 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-300-1-2-511-004-024 | 3) Repainting/Improvement of Ynares Multi-Purpose Covered Court & Construction of Comfort Room at Rainbow Village I, Brgy. Kalayaan, Angono, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 134 | 20%DF | 1349140.11 | 1349140.11 |  | 1336342.64 | 1336342.64 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-001-002-056 | 4) Improvement/Construction of Stone Masonry for Slope Protection and Concreting of Creek bed, Brgy. Malakaban, Binangonan, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 80 | 20%DF | 3111979 | 3111979 |  | 3080962.17 | 3080962.17 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-2-11-399-006 | 5) Improvement of School Building, Concreting of Ground & Construction of Gate at Darangan Elem. School, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 140 | SEF | 774019.6 |  | 774019.6 | 766070.48 |  | 766070.48 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-300-1-2-11-511-004-006 | 6) Improvement/Repair of Ynares Multi-Purpose Covered Court, Brgy. Pilapila, Binangonan, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 80 | GF | 1475316.45 |  | 1475316.45 | 1460416.45 |  | 1460416.45 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-2-11-399-006=041 | 7) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Casimiro A. Ynares, Sr. Elem. School, Brgy. Mambog, Binangonan, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 60 | GF | 999613.24 |  | 999613.24 | 988556.64 |  | 988556.64 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-2-11-399-006-042 | 8) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Bangad Elem. School, Brgy. Bangad, Binangonan, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 60 | GF | 973773.75 |  | 973773.75 | 963809.26 |  | 963809.26 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-2-211-399-006-058 | 9) Construction of 2-Storey, 10-Rooms, Ynares School Building at Don Jose Ynares, Sr. Mem. School, Brgy. San Carlos, Binangonan, Rizal | PEO |  | Public Bidding | 2020-06-08 | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 60 | SEF | 17099800.67 |  | 17099800.67 | 17011690.29 |  | 17011690.29 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-001-002-003 | 10) Improvement/Concreting of Burbank Street (Area 10 &11) at Brookside Hills Subd.,Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 76 | 20%DF | 4498938.88 |  | 4498938.88 | 4453857.07 |  | 4453857.07 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-2-11-399-006-049 | 11) Construction of 4-Storey, 8-Rooms, Ynares School Building at Rosario Elem. School, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding | 2020-06-08 | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 76 | SEF | 17915053.01 |  | 17915053.01 | 17814208.57 |  | 17814208.57 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-300-1-2-11-511-004-004 | 12) Replacement of CHB Wall & Steel Matting Fence at Rotary Day Care Center, Southville 9 Phase I, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 70 | GF | 749901.36 | 749901.36 |  | 742324.71 | 742324.71 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-300-1-2-11-511-004-028 | 13) Construction of Perimeter Fence of Rural Health Unit at Southville 9 Phase 2, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 100 | GF | 1494341.4 |  | 1494341.4 | 1479243.72 |  | 1479243.72 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-2-11-399-006-050 | 14) Construction of 2-Storey, 8-Rooms, Ynares School Building at Looc Elem. School, Brgy. Looc, Cardona, Rizal | PEO |  | Public Bidding | 2020-06-08 | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 90 | SEF | 11799906.51 |  | 11799906.51 | 11719503.61 |  | 11719503.61 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-002-006 | 15) Rehabilitation/Improvement of Road at Sitio Pinagkitran, Brgy. Boor, Cardona, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 100 | GF | 1997935.84 |  | 1997935.84 | 1977575.89 |  | 1977575.89 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-002-007 | 16) Rehabilitation/Concreting of Bayanihan Street, Brgy. 3rd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 60 | GF | 1605821.75 |  | 1605821.75 | 1589303.18 |  | 1589303.18 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-002-034 | 17) Asphalt Overlaying of A. Kalaw Street, Sitio Sambungan, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 70 | GF | 1888518.34 | 1888518.34 |  | 1869366.44 | 1869366.44 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-002-029 | 18) Asphalt Overlaying/Concrete Reblocking (portion) of Serafin Reyes Street, Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 70 | GF | 1349834.11 | 1349834.11 |  | 1335683.31 | 1335683.31 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-1-11-104-005 | 19) Construction of 2-Units Artesian Well, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 162 | 20%DF | 519636.54 |  | 519636.54 | 514479.12 |  | 514479.12 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-003-009 | 20) Concreting (portion) of Road at Pililla GK Village, Pililla, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 70 | 20%DF | 1711067.4 |  | 1711067.4 | 1604140.49 |  | 1604140.49 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-003-009 | 21) Construction of Ynares Stage at Phase 2 Eastwood Greenview Subd., Brgy. San Isidro, Rodriguez, Rizal, | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 100 | 20%DF | 999951.42 |  | 999951.42 | 990783.04 |  | 990783.04 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
8000-800-1-1-51-001-002-011 | 22) Concreting/Construction of Drainage Canal of Road at DaangTubo East, Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 72 | 20%DF | 979204.85 |  | 979204.85 | 968783.6 |  | 968783.6 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-300-1-2-11-399-006-019 | 23) Repair of Various Ynares School Building at Tanay National High School, Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 60 | SEF | 4531339.74 |  | 4531339.74 | 4484852.04 |  | 4484852.04 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-000-1-2-11-399-006-056 | 24) Construction of 2-Storey, 6-Rooms, Ynares School Building at Abuyod Elem. School, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding | 2020-06-08 | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 80 | SEF | 9999649.57 |  | 9999649.57 | 9939303.32 |  | 9939303.32 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
3000-300-1-2-11-511-004-022 | 25) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Dalig, Teresa, Rizal a) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Sitio Abuyod, Brgy. Dalig b) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Carissa Homes East II, Brgy. Dalig c) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Pantay National High School, Brgy. Dalig d) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Abuyod Elem. School, Brgy. Dalig | PEO |  | Public Bidding |  | 10-16 Jun 20 | 2020-06-17 |  | 2020-06-30 | 2020-07-06 | 2020-07-13 | 2020-07-17 | 2020-07-22 | 2020-07-30 |  | 80 | GF | 1179678.71 |  | 1179678.71 | 1168963.89 |  | 1168963.89 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-10 |  | 2020-06-10
4000-400-1-1-11-104-004 4000-400-1-1-11-104-002 | 1) Construction of Elevated Water Tank; Installation of Water Distribution Lines, & Construction of Artesian Well at Brgy. Bombong & Brgy. Rayap, Binangonan, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 100 | 20%DP | 1758102.71 |  | 1758102.71 | 1741025.84 |  | 1741025.84 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
4000-400-1-1-11-104-001 | 2) Construction of Water System Level III & Upgrading of Electrical Service Entrance at Sapang Elem. School, Brgy. Sapang, Binangonan, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 100 | 20%DP | 1999904.07 |  | 1999904.07 | 1980769.46 |  | 1980769.46 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-003-022 | 3) Upgrading of Maria Clara St., (B. Pag-Asa – Rizal Avenue), Brgy. Sta. Ana & Brgy. San Isidro, Taytay, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 189 | 20%DP | 7999202.6 |  | 7999202.6 | 7913758.96 |  | 7913769.96 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
3000-000-1-2-11-399-006-036 | 4) Construction of 15x30 m Ynares Multi-Purpose Covered Court at Taytay Senior High School, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 130 |  | 3949193.66 |  | 3949193.66 | 3908774.59 |  | 3908774.59 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
3000-000-1-2-11-399-006-026 | 5 Construction of Fence, Riprap & Concreting of School Ground at Taytay Senior High School, Brgu. Dolores, Taytay, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 110 |  | 2802678.95 |  | 2802678.45 | 2772417.24 |  | 2772417.24 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
3000-000-1-2-11-511-004-017 | 6) Construction of 2-Storey Tnares Multi-Purpose Building at Palmera I, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 136 | 20%DP | 3499748.62 |  | 3499748.62 | 3466211.26 |  | 3466211.26 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-002-033 | 7) Asphalt Overlaying/Concrete Reblocking (portion) of J.P. Burgos St., Sitio Sambungan, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 80 | GF | 5392786.74 |  | 5392886.74 | 5332278.55 |  |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-004 | 8) Construction/extension of Jalajala Municipal Building, Brgy. First District, Jalajala, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 120 | GF | 8254477.79 |  | 8254477.69 | 8.276,075.33 |  | 8176075.33 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-002-009 | 9) Improvement/Concreting (portion) of Road at Sitio Yapak, Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 72 | 20%DP | 2488574.95 |  | 2488574.95 | 3463628.46 |  | 2,463,,628.46 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-002-047 | 10) Construction of Stone Masonry Headwall (portion) of Wawa Boulevard, Brgy. Wawa, Pililla, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 60 | 20%DP | 1461827.85 |  | 1461827.85 | 1445720.73 |  | 1445710.72 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-002-035 | 11) Asphalt Overlaying and Concrete Reblocking (portion) of Sitio Bulacan I Road, Brgy. Bagumbayan, Pililla, | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 84 | GF | 4199474.71 |  | 4199474.71 | 4144565.49 |  |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-002-056 | 12) Asphalt Overlaying and Concrete Reblocking (portion) of Sitio Ligua Road, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 80 | GF | 4671419.43 |  | 4671419.43 | 4615131.64 | 4615131.64 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-004-002-037 | 13) Asphalt Overlaying and Concrete Reblocking (portion) of Sitio Lipat Lipat Road, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 84 | GF | 6175634.09 |  | 6175634.09 | 6101172.51 | 4615131.64 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
8000-800-1-1-51-001-002-038 | 14) Asphalt Overlaying and Concrete Reblocking (portion) of P. Oleta St., Brgy. Wawa, Pililla, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 76 | GF | 4166641.1 |  | 4166641.1 | 4112258.22 | 4112258.22 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-06-29 |  | 2020-06-29
3000-000-1-2-11-399-006-014 | 15) Repair/Repainting of Ynares School Bldg. at Virgilio B. Melendres Elem. School, Brgy. Takungan, Pililla, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 72 | SEF | 1865092.45 |  | 2865092.45 | 1846175.36 | 1846175.36 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-013 | 16) Asphalt Overlaying of Various Roads at Bancom Life Homes, Brgy. Gulod Malaya, San Mateo, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 100 | GF | 14317638.31 |  | 14317638.31 | 14317638.31 |  |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-039 | 17) Construction of Ynares Multi-Purpose Covered Court (Rafter Type) at Carissa Homes East-1, Brgy. Bagumbayan, Teresa, Rizal | PEO |  | Public Bidding | 2020-06-26 | 29 Jun-5 July 20 | 2020-07-06 |  | 2020-07-17 | 2020-07-21 | 2020-07-27 | 2020-07-31 | 2020-08-08 | 2020-08-14 | 2020-07-29 | 128 | 20%DP | 4188259.54 |  |  | 4146269.15 |  | 4146269.15 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-600-1-2-11-511-004-041 | 1) Construction of 2-Storey, Ynares Multi-Purpose Building (Senior Citizens’ Building) at Brgy. Poblacion Ibaba, Angono, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-025 | 2) As[halt Overlaying/Concrete Reblocking (portion) of F. Cequeña St., Brgy. Macamot, Binangonan, Rizal | PEO |  | Public Bidding | 2020-07-07 | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-010 | 3) Construction of 2-Storey, Multi-Purpose Building at Mahabang Parang Elem. School, Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-600-1-2-11-511-004-047 | 4) Construction of 2-Stprey Ynares Multi-Purpose Building (Senior Citizens’ Office) at Apple Village I, Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-004-019 | 5) Upgrading of B. Pag-Asa St. (Rizal Ave.-Isagani St.) Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-003-021 | 6) Improvement/Concreting of Road at Block 12, Sitio Tapayan, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-050 | 7) Improvement/Rehabilitation of Tenement Road, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-002 | 8) Construction of Ynares Stage at Taytay Senior High School, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-042 | 9) Construction of Stone Masonry for Slope Protection (portion) of Turnina River Ext., Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000=800-1-1-57-001-002-031 | 10) Asphalt Overlaying/Concrete Reblocking (portion) of Villanueva St., Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-032 | 11) Asphalt Overlaying/Concrete Reblocking (portion) of Emeterio Pillas St., Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-400-1-2-21-005-008-006 | 12) Repair of Ynares Municipal Hospital, Brgy. 1st District, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-013 | 13) Construction of Covered Pathwalk at Talaga Elem. School, Sitio Talaga, Brgy. Maybancal, Morong, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-600-1-2-11-511-004-013 | 14) Repair/Repainting of 2-Units, 2-Storey Ynares Multi-Purpose Building (Brgy. Hall.Day Care/Health Center) Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-041 | 15) Repair/Rehabilitation of Stone Masonry for Slope Protection of Pililla River (near M.L. Quezon St.), Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-600-1-2-511-004-021 | 16) Construction of 2-Storey, Ynares Multi-Purpose Building (Senior Citizen’s Hall) at Sitio Libid, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-034 | 17) Repair/Repainting of 3-Units, 2-Storey, 6-Rooms Ynares School Building at Quisao Elem. School, Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-003-012 | 18) Asphalt Overlaying/Concrete Reblocking (portion) of Col. S. Cruz St., Brgy. Balite and San Rafael, Rodriguez, Rizal | PEO |  | Public Bidding | 2020-07-07 | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-003-015 | 19) Asphalt Overlaying/Concrete Reblocking (portion) of Daang Bakal St., Rodriduez, Rizal | PEO |  | Public Bidding | 2020-07-07 | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-400-1-1-11-104-007 | 20) Construction of 2,000 Gallons Elevated Steel Water Tank at Balagbag Elem. School, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-022 | 21) Rehabilitation of Drainage Canal at GSIS Road (Daang Bakal) Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding | 2020-07-07 | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-003-015 | 22) Asphalt Overlaying/Concrete Reblocking (portion) of Mayor Jose F. Diaz Ave., Brgy. Gulod Malaya, San Mateo, Rizal | PEO |  | Public Bidding | 2020-07-07 | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-003-016 | 23) Rehabilitation/Improvement of Drainage Canal at Kambal Road, Brgy. Guitnang Bayan I and Guitnang Bayan II, San Mateo, Rizal | PEO |  | Public Bidding | 2020-07-07 | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-023 | 24) Construction of 17x30 Ynares Multi-Purpose Covered Court at Sampaloc National High School, Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-400-1-1-11-104-008 | 25) Construction of Water System Level II at Teresa District Jail, Sitio Buhangin, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-000-1-1-51-001-004-002 | 1) Rehabilitation of Floodway East embankment Road, Cainta-Taytay, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-0424 | 1a) Improvement/Repair of Ynares Multi-Purpose Covered Court & Improvement of Perimeter Fence at Bry. Sta. Cruz & Brgy. Dela Paz, Antipolo City a) Improvement of Ynares Multi-Purpose Covered Court & Improvement of Perimeter Fence at Brgy. Sta. Cruz & Brgy. Dela Paz, Antipolo City b) Repair of Ynares Multi-Purpose Covered Court at Banjers Village Phase 3, Brgy. Sta. Cruz c) Improvement of Perimeter Fence at Sitio Kabute, Brgy. Dela Paz | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-060 | 2) Construction of Ynares Stage at Dr. Vivencio Villamayor Integrated School, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-61 | 3) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Binangonan Central Elem. School, Brgy. Layunan, Binangonan, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-044 | 4) Improvement of Ynares Multi-Purpose Covered Court & Stage at Montevilla Subdivision, Brgy. Bilibiran, Binangonan, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-045 | 5) Construction of 2-Storey Ynares Multi-Purpose Building at Oliveros Compound, Kalawaan, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-046 | 6) Construction of 2-Storey Ynares Multi-Purpose Building at Jannsen Ville Subd., Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-400-1-1-11-104-010 | 7) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) Brgy. Tuna, Cardona, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-050 | 8) Repair of Ynares Multi-Purpose Covered Court, Brgy. Looc, Cardona, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-066 | 9) Repair/Repainting of Various Ynares School Building at Dalig Elem. School, Brgy. Dalig, Cardona, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-066 | 10) Concreting of creek bed at Purok I and Purok 2, Brgy. Balibago, Cardona, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-067 | 11) Improvement/Construction of Stone Masonry for Slope Protection of creek (portion), Brgy. Nagsulo, Cardona, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-011 | 12) Extension of Existing 2-Storey Ynares Multi-PurposecBuilding, Brgy. 3rd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-600-1-2-11-399-006-064 | 13) Construction of Covered Pathwalk at Punta Elem. School, Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 14) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Bagumbong Elem. School, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 15) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Sipsipin Elem. School, Jalajala, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-063 | 16) Concreting of School Ground & Construction of Artesian Well at Brgy. 2nd District& Brgy. Pagkalinawan, Jalajala, Rizal a) Concreting of School Ground (portion) at Jalajala National High School, Brgy. 2nd District b) Construction of 1-Unit Artesian Well, Brgy. Pagkalinawan | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-067 | 17) Repair/Repainting/Improvement of Ynares School Buildings, Ynares Stage and Ynares Multi-Purpose Covered Court at Hulo National High School, Brgy. Hulo, Pililla, Rizal a) Repair/Repainting of Ynares Schoo; Buildings, Ynares Stage and Ynares Multi-Purpose Covered Court at Hulo National High School, Brgy. Hulo b) Improvement of Ynares School Buildings, Ynares Stage and Ynares Multi-Purpose Covered Court at Hulo National High School, Brgy. Hulo | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 18) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Pililla Elem. School (Central), Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 19) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at URS Pililla, Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 20) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Hulo National High School, Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-400-940-001-003-001 | 21) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Hulo Elem. School, Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-400-40-001-003-001 | 22) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Malaya Elem. School, Pililla, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-000-1-1-51 | 23) Improvement/Construction of Drainage Canal at Block 3 Street and Block 17 Street, St. Peterville Subd., Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-040 | 24) Construction of Ynares Multi-Purpose Building & Construction of Drainage Canal at Rodriguez & Baras, Rizal a) Construction of 2-Storey Ynares Multi-Purpose Building at Eastwood Residences Phase 2, Brgy. San Isidro, Rodriguez b) Construction of Drainage Canal Cover at Trabajo Street, Brgy. San Jose, Baras | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-069 | 25) Improvement of Various School Buildings at Tagumpay National High School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-39-006-071 | 26) Construction of Perimeter Fence at Talaga Elem. School, Sitio Talaga, Brgy. Maybancal, Morong, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-070 | 27) Rehabilitation/Concreting of Zinia Street and Cardinal Ext. Street, Modesta Village, Sto. Niño, San Mateo, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-071 | 28) Concrete Reblocking of Cattleya Street, Modesta Village, Sto. Niño, San Mateo, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-900-900-1-2-40-940-011-003-001 | 29) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Sitio Aguho, Tanay, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-055 | 30) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Sitio Abuyod, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 8 Jul-14 Jul 20 | 2020-07-15 |  | 2020-07-28 | 2020-08-03 | 2020-08-10 |  | 2020-08-14 | 2020-08-21 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-000-1-1-51-001-004-002 | 1) Rehabilitation of Floodway East embankment Road, Cainta-Taytay, Rizal | PEO |  | Public Bidding | 2020-08-17 | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-0424 | 1a) Improvement/Repair of Ynares Multi-Purpose Covered Court & Improvement of Perimeter Fence at Bry. Sta. Cruz & Brgy. Dela Paz, Antipolo City a) Improvement of Ynares Multi-Purpose Covered Court at Bankers Village Phase 3, Brgy. Sta. Cruz b) Repair of Ynares Multi-Purpose Covered Court at Bankers Village Phase 3, Brgy. Sta. Cruz c) Improvement of Perimeter Fence at Sitio Kabute, Brgy. Dela Paz | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-060 | 2) Construction of Ynares Stage at Dr. Vivencio Villamayor Integrated School, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-61 | 3) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Binangonan Central Elem. School, Brgy. Layunan, Binangonan, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-044 | 4) Improvement of Ynares Multi-Purpose Covered Court & Stage at Montevilla Subdivision, Brgy. Bilibiran, Binangonan, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-045 | 5) Construction of 2-Storey Ynares Multi-Purpose Building at Oliveros Compound, Kalawaan, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-046 | 6) Construction of 2-Storey Ynares Multi-Purpose Building at Jannsen Ville Subd., Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-400-1-1-11-104-010 | 7) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) Brgy. Tuna, Cardona, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-050 | 8) Repair of Ynares Multi-Purpose Covered Court, Brgy. Looc, Cardona, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-066 | 9) Repair/Repainting of Various Ynares School Building at Dalig Elem. School, Brgy. Dalig, Cardona, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-066 | 10) Concreting of creek bed at Purok I and Purok 2, Brgy. Balibago, Cardona, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-067 | 11) Improvement/Construction of Stone Masonry for Slope Protection of creek (portion), Brgy. Nagsulo, Cardona, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-011 | 12) Extension of Existing 2-Storey Ynares Multi-PurposecBuilding, Brgy. 3rd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-600-1-2-11-399-006-064 | 13) Construction of Covered Pathwalk at Punta Elem. School, Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 14) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Bagumbong Elem. School, Jalajala, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 15) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Sipsipin Elem. School, Jalajala, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-063 | 16) Concreting of School Ground & Construction of Artesian Well at Brgy. 2nd District& Brgy. Pagkalinawan, Jalajala, Rizal a) Concreting of School Ground (portion) at Jalajala National High School, Brgy. 2nd District b) Construction of 1-Unit Artesian Well, Brgy. Pagkalinawan | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-067 | 17) Repair/Repainting/Improvement of Ynares School Buildings, Ynares Stage and Ynares Multi-Purpose Covered Court at Hulo National High School, Brgy. Hulo, Pililla, Rizal a) Repair/Repainting of Ynares Schoo; Buildings, Ynares Stage and Ynares Multi-Purpose Covered Court at Hulo National High School, Brgy. Hulo b) Improvement of Ynares School Buildings, Ynares Stage and Ynares Multi-Purpose Covered Court at Hulo National High School, Brgy. Hulo | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 18) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Pililla Elem. School (Central), Pililla, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 19) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at URS Pililla, Pililla, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-003-001 | 20) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Hulo National High School, Pililla, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-400-940-001-003-001 | 21) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Hulo Elem. School, Pililla, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-400-40-001-003-001 | 22) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Malaya Elem. School, Pililla, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-000-1-1-51 | 23) Improvement/Construction of Drainage Canal at Block 3 Street and Block 17 Street, St. Peterville Subd., Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-040 | 24) Construction of Ynares Multi-Purpose Building & Construction of Drainage Canal at Rodriguez & Baras, Rizal a) Construction of 2-Storey Ynares Multi-Purpose Building at Eastwood Residences Phase 2, Brgy. San Isidro, Rodriguez b) Construction of Drainage Canal Cover at Trabajo Street, Brgy. San Jose, Baras | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-069 | 25) Improvement of Various School Buildings at Tagumpay National High School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-39-006-071 | 26) Construction of Perimeter Fence at Talaga Elem. School, Sitio Talaga, Brgy. Maybancal, Morong, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-070 | 27) Rehabilitation/Concreting of Zinia Street and Cardinal Ext. Street, Modesta Village, Sto. Niño, San Mateo, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-071 | 28) Concrete Reblocking of Cattleya Street, Modesta Village, Sto. Niño, San Mateo, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-900-900-1-2-40-940-011-003-001 | 29) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Sitio Aguho, Tanay, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-055 | 30) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Sitio Abuyod, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 17 Aug-23 Aug 20 | 2020-08-24 |  | 2020-09-04 | 2020-09-07 | 2020-09-11 |  | 2020-09-15 | 2020-09-18 | 2020-09-25 | [8 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-001 | 1) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Victoriaville Homes, Sitio Upper Lucban, Antipolo City | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-056 | 2) Construction of 2-Storey Multi-Purpose Building at Vermont Royale Executive Village, Brgy. Mayamot, Antipolo City | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-006 | 3) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Meralco 4th Home Village, Binangonan, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-057 | 4) Construction of Daycare Center & Health Center, Brgy. Macamot, Binangonan, Rizal | PEO |  | Public Bidding | 2020-08-24 | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-012-060 | 5) Improvement/Construction of Double Box Culvert along Oja Road and Construction of Stone Masonry for Slope Protection (portion) of Creek, Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-391-006-062 | 6) Construction of School Fence with Gate at Arinda Elem. School, Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-114 | 7) Repair/Repainting of 1-Storey, 5-Rooms, Ynares School Bldg., Construction of Riprap & Canal of Ynares Multi-Purpose Covered Court at Tuna Balibago National High School (Lambac Annex), Brgy. Lambac, Cardona, Rizal a) Repair/Repainting of 1-Storey, 5-Rooms Ynares School Building at Tuna Balibago National High School (Lambac Annex), Brgy. Lambac b) Construction of Riprap & Canal of Ynares Multi-Purpose Covered Court at Tuna Balibago National High School (Lambac Annex), Brgy. Lambac | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-003 | 8) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Looc Elem. School, Cardona, Rizal | PEO |  | Public Bidding | 24 Aug 20- | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-065 | 9) Improvement & Repainting of Ynares Multi-Purpose Covered Court at Brgy. Lambac, Cardona, Rizal a) Improvement of Ynares Multi-Purpose Covered Court at Brgy. Lambac b) Repainting of Ynares Multi-Purpose Covered Court at Brgy. Lambac | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-009-002 | 10) Construction of Multi-Purpose Provincial DRRM Center at Brgy. San Roqye, Cardona, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004 | 11) Repair of Ynares Multi-Purpose Covered Court, Brgy. Pagkalinawan, Jalajala, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-064 | 12) Construction of Stone Masonry for Slope Protection (portion) of Creek at Purok 5 (Ilog Mingming), Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding | 24 Aug 20- | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
8000-800-1-1-51-001-002-065 | 13) Construction of Stone Masonry for Slope Protection (portion) of Creek at Purok 6, Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-069 | 14) Construction of Perimeter Fence of Barangay Hall Compound at Sitio Tabing Ilog, Brgy. San Guillermo, Morong, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-004-001 | 15) Construction of Multi-Purpose Provincial DRRM Center at Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding | 24 Aug 20- | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-006 | 16) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Bugarin Elem. School, Pililla, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-052A | 17) Repair/Repainting/Improvement of Ynares Multi-Purpose Building & School Mini Playground at Brgy. Niogan & Brgy. Quisao, Pililla, Rizal a) Repair/Repainting of Ynares Multi-Purpose Building at Brgy. Niogan b) Improvement of Ynares Multi-Purpose Building at Brgy. Niogan c) Repair/Repainting of School Mini Playground at Quisao Elem. School, Brgy. Quisao | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-012 | 18) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Geronimo Elem. School, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-013 | 19) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Southville 8B National High School, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
9000-900-1-2-40-940-001-002-014 | 20) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Eastwood Greenview Phase 3B, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-070 | 21) Construction of 15x30m Ynares Multi-Purpose Covered Court (Rafter Type) at Villa Ana Maria Subd., Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-071 | 22) Construction of 2-Storey Ynares Multi-Purpose Bldg. at Kasiglahan Village (Phase IA), Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-136 | 23) Improvement of Ynares Multi-Purpose Covered Court at Manggahan Elem. School, Brgy. Manggahan, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-073 | 24) Construction of Ynares Stage at Congressville Subd., Brgy. Manggahan, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-600-1-2-11-511-004-053 | 25) Improvement/Rehabilitation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Macabud & Brgy. Mascap, Rodriguez, Rizal a) Improvement of Ynares Multi-Purpose Covered Court, Brgy. Macabud b) Rehabilitation of Electrical Lighting System of Ynares Multi-Purpose Covered Court, Brgy. Mascap | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-076 | 26) Improvement of Ynares Multi-Purpose Covered Court & Construction of Fence at Eastwood Residences, Phase 8/8A, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-399-006-137 | 27) Improvement of Ynares Multi-Purpose Covered Court & Construction of Welcome Arc at Brgy. San Jose & Brgy. San Isidro, Rodriguez, Rizal a) Improvement of Ynares Multi-Purpose Covered Court at Kasiglahan Village National High School, Brgy. San Jose b) Construction of 2-Units Welcome Arc at Southville 8C Elem. School, Brgy. San Isidro | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-078 | 28) Improvement of Ynares Multi-Purpose Covered Court & Construction of Comfort Room at Brgy. Sto. Niño & Brgy. Malanday, San Mateo, Rizal a) Improvement of Ynares Multi-Purpose Covered Court (Tennis Court) at Modesta Village, Brgy. Sto. Niño b) Construction of Comfort Room at Brgy. Malanday | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-300-1-2-11-511-004-080 | 29) Construction of 10x18m Ynares Multi-Purpose Covered Court (Badminton Court) at La Mar Village, Brgy. Guitnang Bayan II, San Mateo, Rizal | PEO |  | Public Bidding |  | 24 Aug-30 Aug 20 | 2020-09-02 |  | 2020-09-15 | 2020-09-18 | 2020-09-24 |  | 2020-09-30 | 2020-10-07 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2020-09-02 |  | 2020-09-15
3000-000-1-2-11-399-006-076 | 1) Repair & Renovation of School canteen & H.E. Room at Janosa Elem. School, Brgy. Janosa, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30 | [9 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King
3000-000-1-2-11-399-006-088 | 2) Construction of 2-Storey, 4-Rooms Ynares School Building at Pinagdilawan Elem. School, Brgy. Pinagdilawan, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-077 | 3) Construction of Feeding Center & Improvement of Ynares Stage at Janosa Elem. School, Brgy. Janosa, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-078 | 4) Repair/Repainting of 1-Storey, 2-Rooms BOD Building at Kinagatan Elem. School, Brgy. Kinagatan, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-082 | 5) Repair/Repainting of Ynares School Buildings at Binangonan Elem. School, Brgy. Batingan, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-511-004-058 | 6) Construction of 2-Storey Ynares Multi-Purpose Bldg. at Area 8 Greenwoods Executive Village, Brgy. San Andres, Cainta, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-090 | 7) Construction of 3-Storey Multi-Purpose Building at Arinda Rlem. School, Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-511-004-059 | 8) Construction/Improvement of Ynares Multi-Purpose Covered & Ynares Multi-Purpose Bldg. Cainta & Taytay, Rizal a) Construction of 17x30 m Ynares Volleyball/Badminton Court at Area 8, Greenwoods Executive Village, Brgy. San Andres, Cainta b) Improvement of Ynares Multi-Purpose Covered Court at Area 8, Greenwoods Executive Village, Brgy./ San Juan, Cainta, Rizal c) Improvement of 2-Storey, Ynares Multi-Purpose Bldg. at Bagong Pag=Asa Elem. School, Brgy. San Juan, Taytay | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-399-006-100 | 9) Construction of Ynares Stage at Baras-Pinugay Elem. School (Annex), Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-399-006-101 | 10) Improvement of Ynares Multi-Purpose Covered Court at Baras-Pinugay National High School, Phase II, Southville 9, Ynares Village, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-511-004-061 | 11) Rehabilitation of Electrical Lighting System of Baras Gymnasium, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-399-006-102 | 12) Repair/Repainting of Ynares School Buildings at Santiago Elem. School, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-125 | 13) Construction of 2-Storey, 6-Rooms Ynares School Building at Tadlak Elem. School, Brgy. Looc, Cardona, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-511-004-063 | 14) Improvement of Ynares Multi-Purpose Covered Court at Brgy. Sampad, Cardona, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-122 | 15) Repair/Repainting of 1-Storey, 3-Rooms Ynares School Building at Bernardo F. San Juan National High School, Brgy. San Roque, Cardona, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-143 | 16) Construction of Side Protection & Improvement of Ynares Multi-Purpose Covered Court & Stage at Brgy. Calahan, Brgy. Boor & Brgy. Subay, Cardona, Rizal a) Construction of Side Protection of 2-Storey, 4-Rooms Ynares School Bldg. at Patunhay Calahan Elem. School, Brgy. Calahan b) Improvement of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Boor c) Improvement of Ynares Multi-Purpose Covered Court and Stage, Brgy. Subay | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-119 | 17) Improvement of Ynares Stage & Ground of Schools at Cardona & Morong, Rizal a) Improvement of Ynares Stage at Bernardo F. San Juan National High School, Brgy. San Roque, Cardona b) Improvement of Ground at Timoteo A. Reyes, Sr. Mem. Elem. School, Brgy. San Pedro, Morong | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
8000-800-1-1-51-001-002-063 | 18) Construction of Stone Masonry Wall of Creek (Along JICA Road), Brgy. Lubo, Jalajala, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-130 | 19) Construction of 4-Storey, 8-Rooms Ynares School Building at Timoteo A. Reyes, Sr. Mem. Elem. School, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-134 | 20) Construction of 2-Storey, 6-Rooms Ynares School Building at Virgilio Melendres Elem. School, Brgy. Takungan, Pililla, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
8000-800-1-1-51-001-003-012 | 21) Rehabilitation/Improvement of Various Streets at Amityville Subd., Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-600-1-2-11-511-004-016 | 22) Construction of 2-Storey Ynares Multi-Purpose Bldg. (Day Care Center) at Southville 8A Block 28, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
8000-800-1-1-51-001-003-012 | 23) Construction of Covered Pathwalk & Fence at Amityville Elem. School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-511-004-077 | 24) Repair/Repainting of Ynares Multi-Purpose Covered Court & Fence at N.T.A. Village, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
8000-000-1-1-51-001-002-012 | 25) Improvement/Concreting of Various Roads at Divine Mercy Village, Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
9000-900-1-2-40-940-001-001-001 | 26) Construction of Stone Masonry for Slope Protection of Ampid River, Brgy. Ampid I and Brgy. Ampid II, San Mateo, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-000-1-2-11-399-006-148 | 27) Construction of 2-Storey, 6-Rooms Ynares Ynares School Building at Silangan Elem. School (Buntong Palay Annex), Brgy. Silangan, san Mateo, Rizal | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
8000-000-1-1-51-001-002-074 | 28) Rehabilitation/Asphalt Patching of Parking Area at Ynares Sports Arena (YSA), Pasig City | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
1000-000-1-1-11-003-005 | 29) Construction of Justice Building at Government Center, Sitio Cabading, Brgy. Inarawan, Antipolo City | PEO |  | Public Bidding |  | 18 Sep-24 Sep 20 | 2020-09-24 |  | 2020-10-06 | 2020-10-12 | 2020-10-19 |  | 2020-10-23 | 2020-10-30
3000-400-1-2-21-005-008-003 | Construction of Rizal Provincial Hospital System (RPHS) Taytay Annex | PEO |  | Public Bidding |  | 30 Sep-6 Oct 20 | 2020-10-07 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-075 | 1a) Construction of 2-Storey, 4-Rooms Ynares School Building at San Vicente Elem. School, Brgy. San Vicente, Angono, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-079 | 2) Repair/Repainting of 1-Storey, 3-Rooms BOD Building at Kinagatan Elem. School, Brgy. Kinagatan, Binangonan, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-085 | 3) Construction of Ynares Stage at Sitio Mata Elem. School, Brgy. Palangoy, Binangonan, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-087 | 4) Repair/Repainting of 2-Storey, 6-Rooms Ynares School Bldg. at Macamot Elem. School, Brgy. Macamot, Binangonan, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-089 | 5) Repair/Repainting of Ynares School Building & Construction of Covered Pathwalk/Replacement of Gate at Cainta & Taytay, Rizal a) Repair.Repainting of 2-Storey, 6-Rooms Ynares School Building at Kabisig Elem. School, Brgy. San Andres, Cainta b) Construction of Covered Pathwalk/Replacement of Gate at Benjamin B. Esguerra Mem. National High School, Brgy. Sta. Ana, Taytay | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-093 | 6) Repair/Repainting of Ynares School Buildings at Muzon Elem. School, Brgy. Muzon, Taytay, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-095 | 7) Repair/Repainting of Ynares School Buildings at Casimiro A. Ynares Sr. Mem. Nat’l High School, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-096 | 8) Repair/Repainting of Ynares Multi-Purpose Covered Court, Concrete Bleacher & Stage at Brgy. Dolores & Brgy. San Juan, Taytay, Rizal a) Repair/Repainting of Ynares Multi-Purpose Covered Court, Concrete Bleacher & Stage at Casimiro A. Ynares Sr. Mem. Nat’l High School, Brgy. Dolores b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Kapalaran Elem. School, Brgy. San Juan | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
1000-000-1-1-11-003-006 | 9) Repair/Repainting of the Provincial Prosecutor’s Office, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
9000-900-1-2-40-940-001-002-009-003 | 10) Construction of Multi-Purpose Provincial DRRM Center at Motorpool Compound, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
8000-800-1-1-51-001-006 | 11) Construction of Building for Philippine National Police, Bureau of Jail Management & Penology and Bureau of Fire Protection at Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-104 | 12) Repair/Repainting of Ynares School Building at Baras National High School, Brgy. San Juan, Baras, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-106 | 13) Concreting of School Ground at Santiago Elem. School, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-107 | 14) Construction of Covered Pathwalk at Baras-Pinugay National High School (Phase 2), Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-110 | 15) Repair/Repainting of Ynares Multi-Purpose Covered Court at Baras-Pinugay National High School, Sitio Habitat, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-109 | 16) Installation of Steel Grills for School Building & Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. San Juan, Baras, Rizal a) Installation of Steel Grills for 4-Storey, 20-Rooms DepEd Building at Baras Senior High School, Brgy. San Juan b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Baras National High School, Brgy. San Juan | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-111 | 17) Improvement of Ynares Multi-Purpose Covered Court & Ynares Stage at Santiago Elem. School, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-105 | 18) Construction of Covered Pathwalk at Santiago Elem. School, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-114 | 19) Repair/Repainting of 2-Storey, 6-Rooms Ynares School Building at Bernardo F. San Juan National High School, Brgy. San Roque, Cardona, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-121 | 20) Repair/Repainting of 2-Storey, 4-Rooms Ynares School Building at Bernardo F. San Juan National High School, Brgy. San Roque, Cardona, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-300-1-1-11-104-011 | 21) Rehabilitation of Water System, Brgy. Pagkalinawan, Jalajala, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-129 | 22) Repair/Repainting of Ynares School Buildings at Brgy. San Pedro & Brgy. San Juan, Morong, Rizal a) Repair/Repainting of 2-Storey, 4-Rooms Ynares School Building at Timoteo A. Reyes Sr. Mem. Elem. School, Brgy. San Pedro b) Repair/Repainting of 2-Storey, 4-Rooms Ynares School Building at Roman Tantiongco Mem. Elem. School, Brgy. San Juan | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-132 | 23) Construction of Ynares Stage & Flagpole at Lagundi Elem. School, Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-135 | 24) Construction of Covered Pathwalk at Roman Tantiongco Mem. Elem. School, Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-138 | 25) Repair/Repainting of Ynares School Buildings at Montalban Heights National High School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-33000-000-1-2- | 26) Improvement/Repair/Repainting of Ynares School Building at Colegio de Montalban, Brgy. Sam Jose, Rodriguez, Rizal a) Improvement of 2-Storey, 10-Rooms Ynares School Building at Colegio de Montalban, Brgy. San Jose b) Repair/Repainting of 2-Storey, 10-Rooms Ynares School Building at Colegio de Montalban, Brgy. San Jose | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-142 | 27) Construction of 2-Storey, 6-Rooms Ynares School Building at Manggahan National High School, Brgy. Manggahan, Rodriguez, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
8000-000-1-1-51-001-002-048 | 28) Rehabilitation/Improvement of Drainage System of Various Streets, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-143 | 29) Repair/Repainting of School Buildings at Guitnang Bayan Elem. School, Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
3000-000-1-2-11-399-006-145 | 30) Repair/Repainting of Ynares School Buildings & Construction of Comfort Room at Brgy. Gulod Malaya & Brgy. Ampid II, San Mateo, Rizal a) Repair/Repainting of Ynares School Buildings at Gulod Malaya Elem. School, Brgy. Gulod Malaya b) Construction of 2-Seater Comfort Room at Ampid National High School, Brgy. Ampid II | PEO |  | Public Bidding |  | 2 Oct-8 Oct 20 | 2020-10-08 |  | 2020-10-20 | 2020-10-26 | 2020-12-03 |  | 2020-12-09 | 2020-12-14
ON-GOING PROCUREMENT ACTIVITIES
8000-800-1-1-51-001-002-075 | 1) Construction of Flood Interceptor at Gate 1 and Sitio Kasoy entrance (along Sumulong Highway) of Kingsville Subd., Brgy. Mambugan, Antipolo City | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-400-1-1-51-001-003-001 | 2) Improvement of Roads at Southville 9, Brgy. San Jose, Antipolo City | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-400-1-1-51-001-002-014 | 3) Improvement of Roads at Brgy. Kaytome, Binangonan, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-400-1-1-51-001-002-015 | 4) Improvement of Upper Kasinay Road to Mabuhay Homes 2000, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-800-1-1-51-001-002-058 | 5) Improvement of Road at Mabuhay Homes 2000, Brgy. Pantok, Binangonan, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-000-1-2-11-399-006-078 | 6) Improvement of School Buildings & Repair/Repainting of Ynares Stage at Brgy. Kinagatan & Brgy. Bangad, Binangonan, Rizal a) Improvement of 1-Storey, 2-Rooms BOD Building at Kinagatan Elem. School, Brgy. Kinagatan b) Improvement of 1-Storey, 3-Rooms BOD Building at Kinagatan Elem. School, Brgy. Kinagatan c) Repair/Repainting of Ynares Stage at Bangad Elem. School, Brgy. Bangad | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-000-1-2-11-399-006--83 | 7) Improvement/Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Banagd & Brgy. Mambog, Binangonan, Rizal a) Improvement of Ynares Multi-Purpose Covered Court at Bangad Elem. School, Brgy. Bangad b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Casimiro A. Ynares, Sr. Elem. School, Brgy. Mambog, Binangonan, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-000-1-2-11-399-006-149 | 8) Construction of 4-Storey, 12-Rooms Ynares School Building at Darangan Elem. School, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-800-1-1-51-001-002-061 | 9) Improvement of London Street, Cypress Village, Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-800-1-1-51-001-002-076 | 10) Asphalt Overlaying of Taytay-Angono Coastal Road, Taytay, Angono, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-000-1-2-11-399-006-112 | 11) Construction of Fence & Installation of Steel Grills of Ynares School Building at Baras-Pinugay National High School, Sitio Habitat, Brgy. Pinugay, Baras, Rizal a) Construction of Fence at Baras-Pinugay National High School, Sitio Habitat, Brgy. Pinugay, Baras, Rizal b) Installation of Steel Grills for 4-Storey, 8-Rooms Ynares School Building at Baras-Pinugay National High School. Sitio Habitat, Brgy. Pinugay | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-300-1-2-11-511-004-082 | 12) Improvement/Repair/Repainting of Ynares Multi-Purpose Buildings at Jalajala & Cardona, Rizal a) Improvement of Ynares Multi-Purpose Building, Brgy. Bagumbong, Jalajala b) Repair/Repainting of Ynares Multi-Purpose Building, Brgy. Bagumbong, Jalajala c) Repair of 2-Storey Ynares Multi-Purpose Bldg. (Health & Day Care Center) Brgy. Looc, Cardona | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-000-1-1-51-001-001-007 | 13) Construction of Municipality Jail at Philippine National Police Compound, Brgy. 3rd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-300-1-2-11-511-004-084 | 14) Improvement/Repair/Repainting of Ynares Multi-Purpose Covered Court at Sitio Caingin, Brgy.San Juan. Morong, Rizal a) Improvement of Ynares Multi=Purpose Covered Court at Sitio Caingin, Brgy. San Juan b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Sitio Caingin, Brgy. San Juan | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-400-1-1-51-001-002-021 | 15) Improvement of Roads at Brgy. San Juan, Morong, RIzal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-000-1-2-11-399-006-127 | 16) Repair/Repainting of 1-Storey, 3-Rooms Ynares School Buildings at Timoteo A. Reyes Sr. Mem. Elem. School, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-400-1-1-51-001-002-017 | 17) Improvement of Roads at Avila Compound, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-400-1-1-51-001-002-018 | 18) Improvement of Circumferential Road, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-400-1-1-51-001-002-019 | 19) Improvement of Roads at Brgy. Takungan, Pililla, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-000-1-1-51-001-001-006 | 20) Construction of Jail Building for Bureau of Jail Management & Penology and National Bureau of Investigation at Pililla Municipal Compound, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-000-1-1-51-001-002-069 | 21) Construction of Box Culvert at Natividad Street, Looban, Brgy. Maly, San Mateo, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
3000-000-1-2-11-399-006-144 | 22) Repair/Repainting of Multi-Purpose Covered Court & Stage, Ynares School Building at Brgy. Guitnang Bayan I & Brgy. Ampid, San Mateo, Rizal a) Repair/Repainting of Multi-Purpose Covered Court & Stage at Guitnang Bayan I Elem. Scool, Brgy. Guitnang Bayan I, San Mateo, Rizal b) Repair/Repainting of 2-Storey, 6-Rooms Ynares School Bldg. at Ampid National High School, Brgy. Ampid, San Mateo, Rizal | PEO |  | Public Bidding |  | 11 Nov-17 Nov 20 | 2020-11-17 |  | 2020-12-03 | 2020-12-07 | 2020-12-14 |  | 2020-12-18 | 2020-12-28
8000-800-1-1-51-001-004-007 | 1) Improvement of Nazarene Road, Antipolo City | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-009 | 2) Rehabilitation/Improvement of Marigman St., Antipolo City | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-001 | 3) Rehabilitation/Improvement of Roman Roxas Road, Antipolo-Teresa-Baras, Rizal | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-003 | 4I mprovement of LLDA Road, Cardona, Rizal | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-002 | 5) Rehabilitation/Improvement of Morong-Bombongan Road, Morong, Rizal | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-005 | 6) Improvement of Morong-Lagundi Road, Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-008 | 7) Rehabilitation/Improvement of Velasquez St., Taytay, Rizal | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-006 | 8) Rehabilitation/Improvement of L. Wood St., Taytay, Rizal | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
8000-800-1-1-51-001-004-004 | 9) Improvement/Rehabilitation of Cabrera Road (Burol Road), Taytay, Rizal | PEO |  | Public Bidding |  | 23 Nov-29 Nov 20 | 2020-12-01 |  | 2020-12-15 | 2020-12-18 | 2020-12-28 |  | 2021-01-07 | 2021-01-07
3000-000-1-2-11-399-006-098 | 1) Construction of 2-Storey, 8-Rooms Ynares School Building at Tapayan Elem. School, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 7 Dec-13 Dec 20 | 2020-12-14 |  | 2020-12-28 | 2020-12-18 | 2020-12-28 |  | 2021-01-15 | 2021-01-25
3000-000-1-2-11-399-006-099 | 2) Construction of 4-Storey, 12-Rooms Ynares School Building at Dolores Elem. School, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 7 Dec-13 Dec 20 | 2020-12-14 |  | 2020-12-28 | 2020-12-18 | 2020-12-28 |  | 2021-01-15 | 2021-01-25
3000-000-1-2-11-399-006-123 | 3) Construction of 2-Storey, 10-Rooms Ynares School Building at Cardona Senior High School, Brgy. San Roque, Cardona, Rizal | PEO |  | Public Bidding |  | 7 Dec-13 Dec 20 | 2020-12-14 |  | 2020-12-28 | 2020-12-18 | 2020-12-28 |  | 2021-01-15 | 2021-01-25
3000-000-1-2-11-399-006-124 | 4) Construction of 2-Stoery, 4-Rooms Ynares School Building at Dalig Elem. School, Brgy. Dalig, Cardona, Rizal | PEO |  | Public Bidding |  | 7 Dec-13 Dec 20 | 2020-12-14 |  | 2020-12-28 | 2020-12-18 | 2020-12-28 |  | 2021-01-15 | 2021-01-25
3000-000-1-2-11-399-006-150 | 5) Construction of 4-Storey, 12-Rooms Ynares School Building at Antonio C. Esguerra Memorial National High School, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 7 Dec-13 Dec 20 | 2020-12-14 |  | 2020-12-28 | 2020-12-18 | 2020-12-28 |  | 2021-01-15 | 2021-01-25
3000-000-1-2-11-399-006-151 | 6) Relocation of Ynares Multi-Purpose Covered Court at Antonio C. Esguerra Memorial National High School, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 7 Dec-13 Dec 20 | 2020-12-14 |  | 2020-12-28 | 2020-12-18 | 2020-12-28 |  | 2021-01-15 | 2021-01-25
Total Alloted Budget of On-going Procurement Activities | [17 empty] | 277560833.5 | 34540331.92 | 239832341.44 | 248442841.36 | 55694441.98 | 190644231.48
| Prepared by: | [8 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
|  | (Sgd) MA. TERESA E. LASQUETY | [12 empty] | (Sgd) Engr. LUISITO G. MUNSOD | [8 empty] | (Sgd) HON. REBECCA A. YNARES
|  | Head - BAC Secretariat | [12 empty] | BAC Chairperson | [8 empty] | Governor