## PMR 2022- AS OF JUNE 2022
PROVINCE OF RIZAL PROCUREMENT MONITORING REPORT as of JUNE 2022
Code | Procurement | PMO/ | Is this | Mode of | Actual Procurement Activity | [11 empty] | Source | ABC (Php) |  |  | Contract Cost (Php) |  |  | List of | Date of Receipt of Invitation | [5 empty] | Remarks
(UACS/PAP) | Program/Project | End-User | Early Procurement? | Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | BAC Res Date Recom Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | of Funds | Total | MOOE | CO | Total | MOOE | CO | Invited Observers | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (if applicable) | (Explaining changes from the APP)
| 1) Asphalt Overlaying/Concrete Reblocking (portion) of Road with Drainage Canal at Chief Medina St., Brgy. San Isidro, Angono, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 140 | GF | 5899012.61 | 5899013.61 |  | 5857723.24 | 5857724.24 |  | Engr. Nelson Pajarillo King Simon
8000-000-1-1-51-001-002-001
3000-000-1-1-31-392-004-002 | 2) Repair/Repainting of Ynares Multi-Purpose Covered Court at Phase IV-B, Brgy. Dela Paz, Antipolo City | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 80 | GF | 1293079.23 | 1293079.23 |  | 1262380.49 | 1262380.49 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-003 3000-300-1-2-11-511-005-042 | 3) Repair/Repainting of Ynares Multi-Purpose Covered Court and CVHA Office at Brgy. Mambugan and Brgy. Bagong Nayon, Antipolo City a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Francisville Subd., Brgy. Mambugan b) Repair/Repainting of CVHA Office at Cogeo Village, Brgy. Bagong Nayon | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 100 | GF | 523,776.37 378,727.56 902,503.93 | 523,776.37 378,727.56 902,503.94 |  | 511,696.78 370,235.53 881,932.31 | 511,696.78 370,235.53 881,932.32 |  | Engr. Nelson Pajarillo Simon King
3000-400-1-1-11-006-001 | 4) Installation of Water Distribution Lines, Brgy. Bangad, Binangonan, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 68 | GF | 2200180.66 | 2200180.66 |  | 2170326.53 | 2170326.53 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-088 | 5) Improvement/Concreting of C. Bolado Ave., Brgy. Tatala, Binangonan, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 140 | GF | 6674281.55 |  | 6674281.55 | 6626263.2 |  | 6626263.2 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-037 | 6) Asphalt Overlaying of Various Roads at Brgy. Libid, Binangonan, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 80 | GF | 3405774.85 | 3405774.85 |  | 3379653.76 | 3379653.76 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-014 | 7) Construction of Water System Level II at Painaan Elem. School-Heroes Ville Annex, Brgy. Pinugay, Baras, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 140 | GF | 3370772.35 |  | 3370772.35 | 3348570.83 |  | 3348570.83 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-049 | 8) Asphalt Overlaying/Concrete Reblocking (portion) of Bayani Ferrera Road (Formerly Alejo St.) Brgy. Rizal, Baras, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 120 | GF | 7475034.89 | 7475034.89 |  | 7422276.6 | 7422276.6 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-008 | 9) Asphalt Overlay of PPC to Rumagit Road, Brgy. Concepcion, Baras, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 100 | GF | 4995776.23 | 4995776.23 |  | 14910644.52 | 14910644.52 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-009 | 10) Asphalt Overlay of Haya St., Brgy. San Juan, Baras, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 60 | GF | 3013268.32 | 3013268.32 |  | 2985951.24 | 2985951.24 |  | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-014 | 11) Construction of 2-Storey Ynares Multi-Purpose Bldg. at Greenpark Village Phase 8A Zone 4 Brgy. San Isidro, Cainta, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 156 | GF | 3952255.92 |  | 3952255.92 | 3920107.5 |  | 3920107.5 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-030 | 12) Construction of Ynares Stage with Side Protection, Brgy. Boor, Cardona, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 80 | GF | 1695543.67 |  | 1695543.67 | 1668629.47 |  | 1668629.47 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-084 | 13) Asphalt Overlaying/Concrete Reblocking at Sangalang St., Brgy. Pagkalinawan, Jalajala, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 100 | GF | 9590290.89 | 9590290.89 |  | 9527305.22 | 9527305.22 |  | Engr. Nelson Pajarillo Simon King
1000-000-1-1-11-007-002 | 14) Construction of Storage Room at Morong Fire Central Station, Brgy. San Juan, Morong, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 88 | GF | 1233021.17 |  | 1233021.17 | 1213206.14 |  | 1213206.14 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-032 | 15) Improvement of Ynares Multi-Purpose Bldg. (Brgy. Hall), Brgy. San Juan, Morong, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 56 | GF | 651976.81 |  | 651976.81 | 634816.76 |  | 634816.76 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-027 | 16) Concreting (portion) of Masantol Feeder Road, Brgy. Quisao, Pililla, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 100 | GF | 1975556.73 |  | 1975556.73 | 1942884.38 |  | 1942884.38 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-028 | 17) Concreting of Maputing Paa Feeder Road, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 100 | GF | 1999271.68 |  | 1999271.68 | 1969117.1 |  | 1969117.1 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-058 | 18) Asphalt Overlaying/Concrete Reblocking (portion) of Road with Drainage Canal at Rizal St., Brgy. Malaya, Pililla, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 180 | GF | 9061675 | 9061675 |  | 9001256.65 | 9001256.65 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-016 | 19) Construction of 15 x 30m Ynares Multi-Purpose Covered Court (Rafter Type) at Eastwood Residences (Phase 9), Brgy. San Isidro, Rodriguez, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 120 | GF | 4780140.51 |  | 4780140.51 | 4739100.74 |  | 4739100.74 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-073 8000-000-1-1-51-001-002-074 8000-000-1-1-51-001-002-072 | 20) Construction of Roadway Lightings at Brgy. Burgos, Rodriguez, Rizal a) Construction of Roadway Lightings at Metro Montaña Village Phase I, Brgy. Burgos b) Construction of Roadway Lightings at Metro Montaña Village Phase II, Brgy. Burgos c) Construction of Roadway Lightings at Gold River Subd.,Brgy. Burgos | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 120 | GF | 6,032,534.29 3,679,534.66 1,462,601.52 11,174,670.47 |  | 6,032,534.29 3,679,534.66 1,462,601.52 11,174,670.47 | 5,978,610.07 3,664,949.77 1,462,568.69 4,106,128.53 |  | 5,978,610.07 3,664,949.77 1,462,568.69 4,106,128.53 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-075 | 21) Construction of Roadway Lightings at Millex Rd., Brgy. Manggahan, Rodriguez, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 60 | GF | 2349546.32 |  | 2349546.32 | 2317488.14 |  | 2317488.14 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-076 | 22) Construction of Roadway Lightings at E. Manuel St. & A. Bonifacio St., Brgy. San Jose and Brgy. Rosario, Rodriguez, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 80 | GF | 4566938.83 |  | 4566938.83 | 4527157.38 |  | 4527157.38 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-077 8000-000-1-1-51-001-002-078 8000-000-1-1-51-001-002-079 8000-000-1-1-51-001-002-080 | 23) Construction of Roadway Lightings at Brgy. San Jose, Rodriguez, Rizal a) Construction of Roadway Lightings at Bautista St., Guevarra St., F. San Juan St., & Col. S. Cruz St., Brgy. San Jose b) Construction of Roadway Lightings at Dao St., Molave St., & Yakal St., Brgy. San Jose c) Construction of Roadway Lightings at R. Reyes St., & Liamson St., Brgy. San Jose d) Construction of Roadway Lightings at Bagong Buhay, Phase I L2, Sub Urban Village, Brgy. San Jose | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 120 | GF | 4,786,966.66 4,229,891.79 3,343,916.90 2,685,065.52 15,045,840.87 |  | 4,786,966.66 4,229,891.79 3,343,916.90 2,685,065.52 15,045,840.87 | 4,759,782.38 4.205,862.59 3,321,723.89 2,667,399.14 14,954,768.00 |  | 4,759,782.38 4.205,862.59 3,321,723.89 2,667,399.14 14,954,768.00 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-013 3000-000-1-1-31-392-004-014 | 24) Imrpovement of Ynares Multi-Purpose Covered Court at Brgy. San Jose, Rodriguez, Rizal a) Imrpovement of Ynares Multi-Purpose Covered Court at Southville 8C Phase 1 K2, Brgy. San Jose b) Imrpovement of Ynares Multi-Purpose Covered Court at North Triangle Alliance (NTA) Village, Brgy. San Jose | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 100 | GF | 1,616,971.89 1,066,938.84 2,683,910.73 |  | 1,616,971.89 1,066,938.84 2,683,910.73 | 1,592,712.66 1,057,134.11 2,654,031.36 |  | 1,592,712.66 1,057,134.11 2,654,031.36 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-015 3000-300-1-2-11-511-005-027 | 25) Imrpovement of Ynares Multi-Purpose Covered Court/Ynares Multi-Purpose Building at Brgy. San Isidro, Rodriguez, Rizal a) Imrpovement of Ynares Multi-Purpose Covered Court at East Meridian Phase 1a (Bianca), Brgy. San Isidro b) Improvement of 2-Storey Ynares Multi-Purpose Bldg. (HOA Office) at Eastwood Residences Phase 6, Brgy. San Isidro | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 120 | GF | 1,521,637.11 314,212.21 1,835,840.32 |  | 1,521,637.11 314,212.21 1,835,840.32 | 1,506,891.49 303,740.27 1,810,631.76 |  | 1,506,891.49 303,740.27 1,810,631.76 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-006 | 26) Construction of Perimeter Fence at Tierra Verde Phase 3 Eastwood Residences, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 108 | GF | 2005019.01 |  | 2005019.01 | 1973193.85 |  | 1973193.85 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-034 | 27) Construction of Ynares Stage at Eastwood Residences Phase 6, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 100 | GF | 1105460.9 |  | 1105460.9 | 1075005.18 |  | 1075005.18 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-064 | 28) Improvement/Construction of Drainage Canal at Chico St., Brgy. Sto. Niño, San Mateo, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 160 | GF | 7280019.31 |  | 7280019.31 | 7229011.84 |  | 7229011.84 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-022 | 29) Construction of Slope Protection/Retaining Wall along Taytay River, Taytay, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 80 | GF | 3430971.95 |  | 3430971.95 | 3396650.63 |  | 3396650.63 | Engr. Nelson Pajarillo Simon King
9000-900-1-0-40-002-005-014 | 30) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Sto. Niño Integrated School, Sto. Niño, Tanay, Rizal | PEO |  | PUBLIC BIDDING | 2021-12-13 | 17-23-Dec-21 | 2021-12-24 |  | 2022-01-05 | 2022-01-11 | 2022-01-21 |  | 2022-01-28 | 2022-02-04 | 2022-01-28 | 64 | GF | 1158692.35 |  | 1158692.35 | 1129796.74 |  | 1129796.74 | Engr. Nelson Pajarillo Simon King
| 1) Construction of New Binangonan Municipal Building, Binangonan, Rizal | PEO |  | Public Bidding | 2021-11-19 | 19-23 Dec-21 | 2021-12-24 |  | 2022-01-07 | 2022-01-13 | 2022-01-21 |  | 2022-02-11 | 2022-02-23 | 2022-03-23 | 696 | GF | 410419542.34 |  | 410419542.34 | 409916689.75 |  | 409916689.75 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-008 | 1) Repair/Repainting of Ynares Multi-Purpose Covered Court and Ynares Stage at San Vicente Elem. School, Brgy. San Vicente, Angono, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 70 | GF | 1740592.76 | 1740592.76 |  | 1712418.62 | 1712418.62 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-010 | 2) Construction of 2-Storey Ynares Multi-Purpose Building at Sitio Silangan, Brgy. Dela Paz, Antipolo City | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 156 | GF | 3161170.48 |  | 3161170.48 | 3137096.11 |  | 3137096.11 | Engr. Nelson Pajarillo Simon King
3000-400-1-1-11-006-002 | 3) Construction of 4,000 Gallons Elevated Steel Water Tank and Installation of Additional Pipe Lines at Brgy. Kaytome, Binangonan, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 90 | GF | 2001017.21 |  | 2001017.21 | 1974108.56 |  | 1974108.56 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-011 | 4) Construction of 2-Storey Ynares Multi-Purpose Building at Brgy. Pipindan, Binangonan, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 172 | GF | 5050721.97 |  | 5050721.97 | 5006517.75 |  | 5006517.75 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-004 | 5) Concreting of Cequeña St., Brgy. Tatala, Binangonan, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 100 | GF | 1764396.59 |  | 1764396.59 | 1733306.12 |  | 1733306.12 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-006 | 6) Improvement/Concreting of of Katwiran Street with Drainage Canal, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 60 | GF | 1443191.68 |  | 1443191.68 | 1418098.92 |  | 1418098.92 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-003 | 7) Concreting of Road at Kasarinlan Baras Eco Park, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 200 | GF | 15499511.54 |  | 15499511.54 | 15405333.08 |  | 15405333.08 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-082 | 8) Improvement/Concreting of Bluefield St., at Brookside Hills Subd., Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 140 | GF | 5824291.69 |  | 5824291.69 | 5783111.97 |  | 5783111.97 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-082 | 9) Asphalt Overlaying/Concrete Reblocking (portion) of Pauna St., Brgy. Del Remedio, Cardona, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 80 | GF | 1688544.28 | 1688544.28 |  | 1664343.61 | 1664343.61 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-083 | 10) Asphalt Overlaying of Rosario St., Brgy. Del Remedio, Cardona, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 60 | GF | 1170167.98 | 1170167.98 |  | 1143097.31 | 1143097.31 |  | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-015 | 11) Improvement/Extension of 2-Storey Ynares Multi-Purpose Bldg. at Brgy. 2nd District, Jalajala, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 104 | GF | 3742211.65 |  | 3742211.65 | 3705183.82 |  | 3705183.82 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-019 | 12) Construction of Drainage Canal at Timoteo A. Reyes Mem. Elem. School, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 60 | GF | 1134383.68 |  | 1134383.68 | 1106185.46 |  | 1106185.46 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-091 | 13) Improvement/Construction of Drainage Canal at Mabini St., Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 120 | GF | 2798478.45 |  | 2798478.45 | 2767503.08 |  | 2767503.08 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-052 | 14) Asphalt Overlaying/Concrete Reblocking (portion) of Garrovillas St., Brgy. San Jose, Morong, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 80 | GF | 3115180.54 | 3115180.54 |  | 3801094.66 | 3801094.66 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-059 | 15) Asphalt Overlaying/Concrete Reblocking (portion) of Road with Drainage Canal at Andallo St., Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 120 | GF | 4763735.74 | 4763735.74 |  | 4723505.75 | 4723505.75 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-085 | 16) Asphalt Overlaying of G. Talavera St., Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 60 | GF | 1454258.41 | 1454258.41 |  | 1429857.81 | 1429857.81 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-086 | 17) Asphalt Overlaying/Concrete Reblocking (portion) of Sitio Lamuan Feeder Road, Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 100 | GF | 3418976.78 | 3418976.78 |  | 3385094.49 | 3385094.49 |  | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-038 3000-300-1-2-11-511-005-037 | 18) Repair/Improvement of Ynares Multi-Purpose Covered Court at Brgy. Manggahan, Rodriguez, Rizal a) Repair of Ynares Multi-Purpose Covered Court at Congresville Subd., Brgy. Manggahan b) Improvement of Ynares Multi-Purpose Covered Court at Congresville Subd., Brgy. Manggahan | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 100 | GF | 689,458.76 2,697,554.72 3,387,013.48 |  | 689,458.76 2,697,554.72 3,387,013.48 | 685,540.14 2,665,681.60 3,351,221.74 |  | 685,540.14 2,665,681.60 3,351,221.74 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-039 | 19) Repair/Repainting of Ynares Multi-Purpose Covered Court at Sitio Kayrupa, Brgy. Manggahan, Rodriguez, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 60 | GF | 1080087.54 | 1080087.54 |  | 1056082.22 | 1056082.22 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-012 | 20) Repair/Repainting of Ynares Multi-Purpose Covered Court at Southville 8C Phase I K2, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 45 | GF | 1063931.01 | 1063931.01 |  | 1042622.88 | 1042622.88 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-060 | 21) Improvement/Concreting of Kalantas St., Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 80 | GF | 1553482.48 |  | 1553482.48 | 1524360.33 |  | 1524360.33 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-062 | 22) Concreting of Road with Drainage Canal at P. Guevarra St., Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 60 | GF | 834274.32 |  | 834274.32 | 815060.63 |  | 815060.63 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-061 | 23) Application of Pavement Markings along Mayon Avenue at Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 60 | GF | 295333.13 | 295333.13 |  | 284313.03 | 284313.03 |  | Engr. Nelson Pajarillo Simon King
9000-900-1-0-40-002-005-011 | 24) Construction/Provision of Wash Facilities (Water, Sanitation, & Hygiene) at Christine Ville Subd., Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 64 | GF | 947277.9 |  | 947277.9 | 928111.71 |  | 928111.71 | Engr. Nelson Pajarillo Simon King
9000-900-1-0-40-002-005-012 | 25) Construction/Provision of Wash Facilities (Water, Sanitation, & Hygiene) at Eastwood Residence Phase I-IA, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 64 | GF | 947278.94 |  | 947278.94 | 930478.88 |  | 930478.88 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-016 | 26) Improvement/Construction of Steel Grating Canal Cover of Roads at Southville 8 Phase I, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 60 | GF | 342281.72 |  | 342281.72 | 328213.34 |  | 328213.34 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-028 | 27) Construction of 2-Storey Ynares Multi-Purpose Building at La Mar Village, Brgy. Guitnang Bayan II, San Mateo, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 156 | GF | 4129969.24 |  | 4129969.24 | 4090811.61 |  | 4090811.61 | Engr. Nelson Pajarillo Simon King
9000-900-1-0-40-002-005-015 | 28) Construction/Provision of Wash Facilities (Water, Sanitation, & Hygiene), Brgy. Cayabu, Tanay, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 64 | GF | 1285864.26 |  | 1285864.26 | 1260733.9 |  | 1260733.9 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-087 | 29) Asphalt Overlaying/Concrete Reblocking (portion) of Various Roads, Brgy. Poblacion, Teresa, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 100 | GF | 5973846.68 | 5973846.68 |  | 5930865.9 | 5930865.9 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-023 | 30) Construction of Stone Masonry for Slope Protection (portion) of Greenview isle Creek, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding | 2021-12-20 | 21-27 Dec-21 | 2021-12-28 |  | 2022-01-10 | 2022-01-17 | 2022-01-25 |  | 2022-01-31 | 2022-02-09 | 2022-02-16 | 180 | GF | 7553021.52 |  | 7553021.52 | 7469426.04 |  | 7469426.04 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-043 | 1) Construction of 2-Storey Ynares Multi-Purpose Bldg. at Baytown Homes Subd., Brgy. Kalayaan, Angono, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 156 | GF | 4180999.31 |  | 4180999.31 | 4142872.24 |  | 4142872.24 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-029 | 2) Construction of 2-Storey Ynares multi-Purpose Bldg. (Senior Citizens Office) at Samsonville, Brgy. Mayamot, Antipolo City | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 156 | GF | 4179485.14 |  | 4179485.14 | 4136310.51 |  | 4136310.51 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-002 | 3) Improvement/Concreting (portion) of Road at Sitio San Ysiro, Brgy. San Jose, Antipolo City | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 220 | GF | 39347072.27 |  | 39347072.27 | 39206326.14 |  | 39206326.14 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-089 | 4) Concreting (portion) of Road at Malinis St., Brgy. Lunsad, Binangonan, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 100 | GF | 3884312.01 |  | 3884312.01 | 3845366.88 |  | 3845366.88 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-093 | 5) Construction of Drainage Canal at M. Oja Road, Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 100 | GF | 2920051.99 |  | 2920051.99 | 2888010.25 |  | 2888010.25 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-090 | 6) Construction of Drainage Canal (portion) at Mesa St., Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 80 | GF | 2218061.9 |  | 2218061.9 | 2190949.58 |  | 2190949.58 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-027 8000-000-1-1-51-001-002-028 8000-000-1-1-51-001-002-029 8000-000-1-1-51-001-002-030 8000-000-1-1-51-001-002-031 | 7) Construction of Roadway Lightings at Brgy. Pag-Asa, Binangonan, Rizal a) Construction of Roadway Lightings at Antazo Compound, Brgy. Pag-Asa b) Construction of Roadway Lightings at Liwanag Compound, Brgy. Pag-Asa c) Construction of Roadway Lightings at Diaz I Compound, Brgy. Pag-Asa d) Construction of Roadway Lightings at San Clemente Subdivision,Brgy. Pag-Asa e) Construction of Roadway Lightings at Sitio Hangganan, Brgy. Pag-Asa | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 80 | GF | 475,615.12 701,769.01 701,769.01 1,360,357.23 1,800,512.26 5,040,022.63 |  | 475,615.12 701,769.01 701,769.01 1,360,357.23 1,800,512.26 5,040,022.63 | 471,814.63 694,338.25 694,338.25 1,347,422.67 1,786,453.07 4,994,366.87 |  | 471,814.63 694,338.25 694,338.25 1,347,422.67 1,786,453.07 4,994,366.87 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-035 | 8) Construction of Roadway Lightings at Brgy. Habagatan,Binangonan, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 90 | GF | 6243144.45 |  | 6243144.45 | 6192051.88 |  | 6192051.88 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-007 | 9) Asphalt Overlaying/Concrete Reblocking (portion) of Maharlika Road, Brgy. San Salvador and Brgy. Rizal, Baras, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 80 | GF | 3217226.63 | 3217226.63 |  | 3184292.32 |  | 3184292.32 | Engr. Nelson Pajarillo Simon King
9000-900-1-0-40-002-005-002 | 10) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Baras-Pinugay National High School, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 64 | GF | 993522.46 |  | 993522.46 | 973491.86 |  | 973491.86 | Engr. Nelson Pajarillo Simon King
9000-900-1-0-40-002-005-004 | 11) Construction/Provision of Wash Facilities(Water, Sanitation & Hygiene) at Greenwoods Executive Village Area 8, Brgy. San Andres, Cainta, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 70 | GF | 1069808.78 |  | 1069808.78 | 1045709.71 |  | 1045709.71 | Engr. Nelson Pajarillo Simon King
9000-900-1-0-40-002-005-005 | 12) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Brgy. Boor, Cardona, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 72 | GF | 1180005.45 |  | 1180005.45 | 1151102.26 |  | 1151102.26 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-010 8000-000-1-1-51-001-002-011 | 13) Construction of Roadway Lightings at Brgy. Lambac and Brgy. Sampad, Cardona, Rizal a) Construction of Roadway Lightings, Brgy. Lambac b) Construction of Roadway Lightings, Brgy. Sampad | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 90 | GF | 2,509,604.20 3,252,838.84 5,762,443.04 |  | 2,509,604.20 3,252,838.84 5,762,443.04 | 2,489,300.96 3,223,982.83 5,713,283.79 |  | 2,489,300.96 3,223,982.83 5,713,283.79 | Engr. Nelson Pajarillo Simon King
9000-900-1-0-40-002-005-007 | 14) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Sitio Pulong Ligaya, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 64 | GF | 1076121.64 |  | 1076121.64 | 1048069.53 |  | 1048069.53 | Engr. Nelson Pajarillo Simon King
9000-900-1-0-40-002-005-008 | 15) Construction/Provision of Wash Facilities Water, Sanitation & Hygiene) at Bayugo National High School, Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 64 | GF | 1061438 |  | 1061438 | 1031435.84 |  | 1031435.84 | Engr. Nelson Pajarillo Simon King
1000-000-1-1-11-007-001 | 16) Improvement of Morong Fire Station at Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 70 | GF | 1561297.11 |  | 1561297.11 | 1533140.73 |  | 1533140.73 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-015 | 17) Asphalt Overlaying/Concrete Reblocking (portion) of Road with Drainage Canal at Estrella St., Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 80 | GF | 1799231.9 | 1799231.9 |  | 1759584.1 | 1759584.1 |  | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-007 | 18) Improvement of Ynares Multi-Purpose Building, Brgy. Guitnang Bayan II, San Mateo, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 90 | GF | 1412433.87 |  | 1412433.87 | 1371376.97 |  | 1371376.97 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-017 | 19) Construction of 2-Storey Ynares Multi-Purpose Building (Day Care Center) at Divine Mercy Subd., Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 156 | GF | 3934132.92 |  | 3934132.92 | 3901033 |  | 3901033 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-017 | 20) Improvement of Ynares Multi-Purpose Covered Court, Brgy. Sta. Ana, San Mateo, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 80 | GF | 1062346.71 |  | 1062346.71 | 1035263.61 |  | 1035263.61 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-066 | 21) Concreting of Road with Drainage Canal at Road Lot 5 Purok 7 Lupang Arenda, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 120 | GF | 4256103.28 |  | 4256103.28 | 4214056.49 |  | 4214056.49 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-067 | 22) Concreting of Road with Drainage Canal at Road Lot 37 Purok 7 Lupang Arenda, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 80 | GF | 2653598.34 |  | 2653598.34 | 2674312.58 |  | 2674312.58 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-024 | 23) Concreting of Road with Drainage Canal at Road Lot 7 Purok 7 Lupang Arenda, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 140 | GF | 5049694.58 |  | 5049694.58 | 4999340.29 |  | 4999340.29 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-035 | 24) Construction of 2-Storey Ynares Multi-Purpose Bldg. (GAD Center) at Brgy. Kay-Buto, Tanay, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 156 | GF | 2952255.92 |  | 2952255.92 | 3910100.61 |  | 3910100.61 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-017 | 25) Improvement/Upgrading/Concreting (portion) of Tanay Catholic Cemetery Road to Gawad Kalinga, Brgy. Katipunan-Bayani, Tanay, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 140 | GF | 4598812.28 |  | 4598812.28 | 4553728.61 |  | 4553728.61 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-018 | 26) Concreting of Sitio Bathala Road (Loob), Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 120 | GF | 4802191.36 |  | 4802191.36 | 4750135.45 |  | 4750135.45 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-024 | 27) Construction of Evacuation Center at CHE I, Brgy. Bagumbayan, Teresa, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 250 | GF | 14986199.17 |  | 14986199.17 | 14889031.71 |  | 14889031.71 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-069 | 28) Construction of Stone Masonry for Slope Protection of Creek at Carissa Homes East I (CHE-I), Brgy. Bagumbayan and Brgy. Prinza, Teresa, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 100 | GF | 2322080.39 |  | 2322080.39 | 2294270.72 |  | 2294270.72 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-070 | 29) Construction of Stone Masonry for Slope Protection (portion) of Teresa, River, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 160 | GF | 6410549.4 |  | 6410549.4 | 6355398.7 |  | 6355398.7 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-071 | 30) Construction of Stone Masonry for Slope Protection (portion) of Teresa River at Bridge No. 1, Brgy. May-Iba, Teresa, Rizal | PEO |  | Public Bidding | 2021-12-22 | 24-30 Dec-21 | 2022-01-02 |  | 2022-01-17 | 2022-01-21 | 2022-02-04 |  | 2022-02-10 | 2022-02-18 | 2022-02-24 | 80 | GF | 2156099.87 |  | 2156099.87 | 2132349.61 |  | 2132349.61 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-025 | 1) Improvement/Concreting of Road with Drainage Canal at Doña Maria St.and Doña Justa Extension, Brgy. San Roque, Angono, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 100 | GF | 3454068.28 |  | 3454068.28 | 3406184.54 |  | 3406184.54 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-009 | 2) Repair/Repainting of Ynares Multi-Purpose Covered Court at Peace Village Phase 2, Brgy. San Luis, Antipolo City | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 80 | GF | 1434931.17 | 1434931.17 |  | 1395921.01 | 1395921.01 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-013 | 3) Installation of Water Lines at Various School Buildings at Janosa Elem. School, Brgy. Janosa, Binangonan, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 54 | GF | 861197.85 | 861197.85 |  | 843192.62 | 843192.62 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-010 | 4) Construction of 3-Seater Comfort Room and Storage Room atPinagdilawan Elem. School, Brgy. Pinagdilawan, Binangonan, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 85 | GF | 1529455.67 |  | 1529455.67 | 1498350.84 |  | 1498350.84 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-011 | 5) Repair/Repainting of Ynares Multi-Purpose Covered Court, Brgy. Kasile, Binangonan, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 80 | GF | 1790502.68 | 1790502.68 |  | 1751670.8 | 1751670.8 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-006 | 6) Repair/Repainting of Ynares Multi-Purpose Covered Court at Centro Ibaba, Brgy. Bilibiran, Binangonan, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 80 | GF | 1257074.59 | 1257074.59 |  | 1228118.5 | 1228118.5 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-032 8000-000-1-1-51-001-002-033 8000-000-1-1-51-001-002-034 | 7) Construction of Roadway Lightings at Brgy. Tatala, Binangonan, Rizal a) Construction of Roadway Lightings at Ilang-Ilang St., Brgy. Tatala b) Construction of Roadway Lightings at Sebastian Ulang St., Brgy. Tatala c) Construction of Roadway Lightings at Julio Ulang St., Brgy. tatala | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 68 | GF | 2,235,642.73 366,315,78 473,580.74 3,075,539.25 |  | 2,235,642.73 366,315,78 473,580.74 3,075,539.25 | 2,221,281.21 362,921.64 467384.48 3,041,590.33 |  | 2,221,281.21 362,921.64 467384.48 3,041,590.33 | Engr. Nelson Pajarillo Simon King
000-000-1-1-51-001-002-039 8000-000-1-1-51-001-002-040 8000-000-1-1-51-001-002-041 8000-000-1-1-51-001-002-042 8000-000-1-1-51-001-002-043 8000-000-1-1-51-001-002-044 8000-000-1-1-51-001-002-045 8000-000-1-1-51-001-002-046 8000-000-1-1-51-001-002-047 | 8) Construction of Roadway Lightings at Brgy. Macamot, Binangonan, Rizal a) Construction of Roadway Lightings at Yson St., Brgy. Macamot b) Construction of Roadway Lightings at Sitio Kaytikling, Brgy. Macamot c) Construction of Roadway Lightings at Ramos St., Brgy. Macamot d) Construction of Roadway Lightings at Michilina St., Brgy. Macamot e) Construction of Roadway Lightings at M.G. Cequeña St., Brgy. Macamot f) Construction of Roadway Lightings at Membrebe St., Brgy. Macamot g) Construction of Roadway Lightings at Jocson St., Brgy. Macamot h) Construction of Roadway Lightings at C. Apostadero St., Brgy. Macamot i) Construction of Roadway Lightings at B. Apostadero St., Brgy. Macamot | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 80 | GF | 439,549.46, 647,958.86 959,186.53 544,854.14 854,749.64 336,791.42 1,379,404.39 336,791.42 439,549.46 5,938,835.32 |  | 439,549.46, 647,958.86 959,186.53 544,854.14 854,749.64 336,791.42 1,379,404.39 336,791.42 439,549.46 5,938,835.32 | 434,995.15 642,277.53 950,448.63 539,947.31 847,873.64 333,341.77 1,368,460.85 333,341.77 434,995.15 5,885,681.80 |  | 434,995.15 642,277.53 950,448.63 539,947.31 847,873.64 333,341.77 1,368,460.85 333,341.77 434,995.15 5,885,681.80 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-005 | 9) Construction of Stone Masonry for Slope Protection (portion) at Baras River, Brgy. San Juan, Baras, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 140 | GF | 5441835.6 |  | 5441835.6 | 5394689.91 |  | 5394689.91 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-004 | 10) Construction of Stone Masonry for Slope Protection at Kasarinlan Baras Eco Park, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 220 | GF | 22999117.58 |  | 22999117.58 | 22914173.65 |  | 22914173.65
8000-000-1-1-51-001-002-008 8000-000-1-1-51-001-002-009 | 11) Construction of Roadway Lightings at Brgy. Malanggam-Calubacan & Brgy. Tuna, Cardona, Rizal a) Construction of Roadway Lightings at Brgy. Malanggam-Calubacan b) Construction of Roadway Lightings, Brgy. Tuna | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 60 | GF | 2,386,701.22 2,173,936.09 4,560,637.31 |  | 2,386,701.22 2,173,936.09 4,560,637.31 | 2,352,765.40 2,156,771.63 4,509,537.03 |  | 2,352,765.40 2,156,771.63 4,509,537.03 | Engr. Nelson Pajarillo Simon King
9000-900-1-0-41-002-005-006 | 12) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Tuna Balibago National High School, Lambac Extension, Lambac, Cardona, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 64 | GF | 1289518.87 |  | 1289518.87 | 1260462.32 |  | 1260462.32 | Engr. Nelson Pajarillo Simon King
9000-900-1-0-41-002-005-009 | 13) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Jalajala National High School, Brgy. 1st District, Jalajala, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 64 | GF | 1056840.35 |  | 1056840.35 | 1034666.95 |  | 1034666.95 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-017 3000-000-1-2-11-399-005-018 3000-000-1-2-11-399-005-016 | 14) Construction of Comfort Room and Handwashing Area /Improvement of Administrative Office at Brgy. San Pedro, Morong, Rizal a) Construction of 3-Seater Comfort Rooms at Timoteo A. Reyes Mem. Elem. School, Brgy. San Pedro b) Construction of 2-Units Handwashing Area at Timoteo A. Reyes Mem. Elem. School, Brgy. San Pedro c) Improvement of Administrative Office at Timoteo A. Reyes Mem. Elem. School, Brgy. San Pedro | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 80 | GF | 885,207.54 281,369.03 195,352.26 1,361,928.83 |  | 885,207.54 281,369.03 195,352.26 1,361,928.83 | 866,822.89 271,961.74 192,022.47 1,330,807.10 |  | 866,822.89 271,961.74 192,022.47 1,330,807.10 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-053 | 15) Construction of Stone Masonry for Slope Protection (portion) at Morong River, Brgy. San Jose, Morong, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 160 | GF | 7698763.22 |  | 7698763.22 | 7642790.03 |  | 7642790.03 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-203 | 16) Concreting (portion) of Road at Siito Wawa, Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 60 | GF | 915612.22 |  | 915612.22 | 895738.6 |  | 895738.6 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-204 8000-000-1-1-51-001-002-205 8000-000-1-1-51-001-002-206 8000-000-1-1-51-001-002-207 8000-000-1-1-51-001-002-208 | 17) Construction of Roadway Lightings at Brgy. San Juan, Morong, Rizal a) Construction of Roadway Lightings at Cruz Compound, Sitio Taghangin, Brgy. San Juan b) Construction of Roadway Lightings at Martinez St., Sitio Happy Happy (near basketball court), Brgy. San Juan c) Construction of Roadway Lightings at F. Angeles St. & M. De Ungria St.,Siio Pook & Sitio Pook, (near basketball court), Brgy. San Juan d) Construction of Roadway Lightings at Martinez St., Raymundo St., & Turentigue St. Sunday Club Comp., Sitio Poblacion, Brgy. San Juan e) Construction of Roadway Lightings at Martinez St., Turentigue St., & Salubungan St., Sitio Hardin, Brgy. San Juan | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 60 | GF | 412,592.76 432,819.85 676,740.72 446,85.42 339,251.02 2,307,657.20 |  | 412,592.76 432,819.85 676,740.72 446,85.42 339,251.02 2,307,657.20 | 408,557.09 427,610.56 670,980.79 441,568.06 334,523.71 2,282,540 |  | 408,557.09 427,610.56 670,980.79 441,568.06 334,523.71 2,282,540 | Engr. Nelson Pajarillo Simon King
9000-900-1-0-40-002-005-010 | 18) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Quisao National High School, Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 70 | GF | 1017501.54 |  | 1017501.54 | 995211.35 |  | 995211.35 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-004-120 | 19) Construction of 1-Storey Ynares Multi-Purpose Bldg. (HOA Office) at Col. S. Cruz Sabah, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 94 | GF | 2403243.82 |  | 2403243.82 | 2377192.05 |  | 2377192.05 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-008 | 20) Improvement of 2-Storey Ynares Multi-Purpose Bldg. (Day Care Center) at Salamat Extension, Brgy. Ampid II, San Mateo, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 64 | GF | 1639680.97 |  | 1639680.97 | 1604511.5 |  | 1604511.5 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-092 | 21) Asphalt Overlaying of Road with Canal Cover at Sta. Maria St., Brgy. Guinayang, San Mateo, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 80 | GF | 2117375.89 | 2117375.89 |  | 2078223.02 |  | 2078223.02 | Engr. Nelson Pajarillo Simon King
9000-900-1-0-40-002-005-013 | 22) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Bankers Village V, Phase-I, Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 64 | GF | 1044087.82 |  | 1044087.82 | 1016109.35 |  | 1016109.35 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-019 | 23) Concreting of Various Roads, Brgy. Sto. Niño, San Mateo, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 60 | GF | 785431.47 |  | 785431.47 | 763761.87 |  | 763761.87 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-021 | 24) Concreting of Sampiro Road (portion), Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 80 | GF | 1905416.94 |  | 1905416.94 | 1870487.55 |  | 1870487.55 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-036 | 25) Construction of 2-Storey Ynares Multi-Purpose Bldg. (Peace & Order Office), Brgy. Kay-Buto, Tanay, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 56 | GF | 3952255.92 |  | 3952255.92 | 3913110.11 |  | 3913110.11 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-028 | 26) Construction of Stone Masonry for Slope Protection at Tanay Senior High School, Sitio Dalawang Kawayan, Brgy. Tandang Kutyo, Tanay, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 120 | GF | 3768317.69 |  | 3768317.69 | 3728762.6 |  | 3728762.6 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-014 | 27) Improvement/Construction of Stone Masonry for Side Protection (portion) along Pinugay Road, Sitio Dalawang Kawayan, Brgy. Tandang Kutyo, Tanay, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 100 | GF | 2800473.16 |  | 2800473.16 | 2769214.47 |  | 2769214.47 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-016 | 28) Construction of Side Protection (portion) of Creek at Brgy. Mag-Ampon, Tanay, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 140 | GF | 6496806.12 |  | 6496806.12 | 6443713.94 |  | 6443713.94 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-022 | 29) Concreting (portion) of Tuoy Road, Brgy. Cuyambay, Tanay, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 140 | GF | 5205362.54 |  | 5205362.54 | 5158280.02 |  | 5158280.02 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-019 | 30) Construction of Roadway Lightings at Narra St., Brgy. Cuyambay, Tanay, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 60 | GF | 3018330.97 |  | 3018330.97 | 2983252.49 |  | 2983252.49 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-001-010 | 31) Improvement of Ground at Rizal Provincial Motorpool, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 160 | GF | 12783417.78 |  | 12783417.78 | 12692433.87 |  | 12692433.87 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-001-011 | 32) Construction of Parking Shed at Rizal Provincial Jail, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 96 | GF | 3446648.79 |  | 3446648.79 | 3406227.15 |  | 3406227.15 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-019 | 33) Improvement of Ynares Multi-Purpose Covered Court at Carissa Homes East II, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 72 | GF | 1637504.52 |  | 1637504.52 | 1598478.69 |  | 1598478.69 | Engr. Nelson Pajarillo Simon King
9000-900-1-0-40-002-005-016 | 34) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene), Brgy. Bagumbayan, Teresa, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 64 | GF | 1042629.93 |  | 1042629.93 | 1014629.73 |  | 1014629.73 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-024 | 35) Construction of Stone Masonry for Slope Protection (portion) of Teresa River, Sitio Abuyod, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding | 2021-12-27 | 4-10 Jan-21 | 2022-01-11 |  | 2022-01-24 | 2022-01-28 | 2022-02-08 |  | 2022-02-14 | 2022-02-18 | 2022-02-24 | 100 | GF | 3609626.51 |  | 3609626.51 | 3571116.5 |  | 3571116.5 | Engr. Nelson Pajarillo Simon King
1000-000-1-1-11-007-003 | 1) Repainting of Angono Municipal Bldg. at Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 150 | GF | 3352158.72 | 3352158.72 |  | 3307103.96 | 3307103.96 |  | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-001 | 2) Repair/Repainting of Ynares Multi-Purpose Bldg. (Day Care Center) at Villa Gloria Subd., Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 50 | GF | 306314.27 | 306314.27 |  | 291300.09 | 291300.09 |  | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-002 | 3) Construction of 1-Storey Ynares Multi-Purpose Bldg. at Vermont Royale Exec. Village, Brgy. Mayamot, Antipolo City | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 86 | GF | 2539929.79 |  | 2539929.79 | 2514900.23 |  | 2514900.23 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-012 3000-300-1-2-11-511-005-003 | 4) Improvement of Ynares Multi-Purpose Bldg., Brgy. Pag-Asa, Binangonan, Rizal a) Improvement of 2-Storey Ynares Multi-Purpose Bldg. (Child Development Center) at Brgy. Pag-Asa b) Improvement of Ynares Multi-Purpose Bldg. (Floor Tiles), Brgy. Pag-Asa | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 50 | GF | 183,215.75 228,949.97 412,165.72 |  | 183,215.75 228,949.97 412,165.72 | 174,288.23 220,991.15 395,299.38 |  | 174,288.23 220,991.15 395,299.38 | Engr. Nelson Pajarillo Simon King
3000-300-1-1-31-392-004-004 3000-000-1-1-31-392-004-005 | 5) Improvement/Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Ginoong Sanay, Binangonan, Rizal a) Improvement of Ynares Multi-Purpose Covered Court, Brgy. Ginoong Sanay b) Repair/Repainting of Ynares multi-Purpose Covered Court, Brgy. Ginoong Sanay | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 80 | GF | 1,099,411.00 596,145.63 1,695,556.63 | 596145.63 | 1099411 | 1,086,769.94 583,734.94 1,670,504.88 | 583734.94 | 1086769.94 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-081 | 6) Concreting of Road Shoulders at Darangan-Binangonan-Antipolo-Angono Road (Eastridge), Binangonan-Antipolo-Angono, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 240 | GF | 32406096.43 |  | 32406096.43 | 32311128.66 |  | 32311128.66 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-003 | 7) Concreting of Road with Drainage Canal at Sampaloc Cmpd., Sitio Victoria, Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 120 | GF | 3191049.18 |  | 3191049.18 | 3152156.83 |  | 3152156.83 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-038 | 8) Concreting of S. Ulang St., Brgy. Tatala, Binangopnan, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 80 | GF | 1528751.96 |  | 1528751.96 | 1491221.73 |  | 1491221.73 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-005 | 9) Improvement/ Concreting of Road with Drainage Canal at Sitio Villamayor (Diaz Compound), Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 80 | GF | 1550707.58 |  | 1550707.58 | 1517855.41 |  | 1517855.41 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-036 | 10) Construction of Drainage Canal at Picones St., Brgy. Macamot, Binangonan, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 120 | GF | 4499759.18 |  | 4499759.18 | 4449704.3 |  | 4449704.3 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-013 | 11) Repair/Repainting of 2-Storey Ynares Multi-Purpose Bldg.(Brgy. Hall) at Brgy. San Juan, Baras, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 50 | GF | 350574.05 | 350574.05 |  | 335521.39 | 335521.39 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-010 | 12) Concreting of Bayani Fererra Road, Sitio Inalsan, Brgy. San Jose, Baras, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 140 | GF | 5946095.73 |  | 5946095.73 | 5895190.15 |  | 5946095.73 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-006 | 13) Construction of Stone Masonry for Side Protection of Creek at NIA Road, Brgy. Evangelista, Baras, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 240 | GF | 31800319.85 |  | 31800319.85 | 31800319.85 |  | 31800319.85 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-005 | 14) Rehabilitation/Construction of Stone Masonry for Side Protection (portion) of Baras River along Brgy. San Juan and Brgy. San Jose, Baras, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 180 | GF | 11480815.47 |  | 11480815.47 | 11394011.4 |  | 11394011.4 | Engr. Nelson Pajarillo Simon King
9000-900-1-0-40-002-005-003 | 15) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Village East Executive Homes, Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 66 | GF | 1003387.41 |  | 1003387.41 | 977257.96 |  | 977257.96 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-007 | 16) Repair/Repainting of Ynares Multi-Purpose Covered Court, Brgy. Sampad, Cardona, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 92 | GF | 3099723.27 | 3099723.27 |  | 3069753.08 | 3069753.08 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-012 | 17) Construction of Roadway Lightings, Brgy, Lubo, Jalajala, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 60 | GF | 1117889.08 |  | 1117889.08 | 1094820.78 |  | 1094820.78 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-004 3000-000-1-2-11-399-005-003 | 18) Construction of Welcome Arc/Repair of Ynares School Building at Brgy. 3rd District and Brgy. Sipsipin, Jalajala, Rizal a) Construction of Two (2)-Units Welcome Arc, Brgy. 3rd District b) Repair of 2-Storey 8-Rooms Ynares School Building at University of Rizal System, Brgy. Sipsipin | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 80 | GF | 849,049.61 228,684.34 1,077,733.95 | 228684.34 | 849049.61 | 832,357.93 217,296.14 1,049,654.34 | 217296.14 | 832357.93 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-051 | 19) Concreting of Road at Campo Street, Purok 6, Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 80 | GF | 1790085.49 |  | 1790085.49 | 1755882.12 |  | 1755882.12 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-031 | 20) Construction of 3-Seater Comfort Room at Ynares Multi-Purpose Covered Court, Brgy. San Jose, Morong, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 50 | GF | 832361.64 |  | 832361.64 | 817207.34 |  | 817207.34 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-005 | 21) Construction of Evacuation Center at Market Road, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 250 | GF | 14991710.41 |  | 14991710.41 | 14925697.25 |  | 14925697.25 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-013 8000-000-1-1-51-001-002-054 8000-000-1-1-51-001-002-055 8000-000-1-1-51-001-002-056 8000-000-1-1-51-001-002-057 | 22) Construction of Roadway Lightings at Brgy. Bagumbayan and Brgy. Halayhayin, Pililla, Rizal a) Construction of Roadway Lightings at Balite Road (Market Road) and Avila Compound, Brgy. Bagumbayan b) Construction of Roadway Lightings at Sitio Rambo, Brgy. Halayhayin c) Construction of Roadway Lightings at Mahabang Sapa, Brgy. Halayhayin d) Construction of Roadway Lightings at Bonifacio Rafanan Road, Brgy. Halayhayin e) Construction of Roadway Lightings at Sitio Pahang, Brgy. Halayhayin | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 160 | GF | 1,906,583.87 5,441,707.64 6,459,845.56 1,586,128.07 2,971,697.64 18,367,962.78 |  | 1,906,583.87 5,441,707.64 6,459,845.56 1,586,128.07 2,971,697.64 18,367,962.78 | 1,906,476.46 5,413,017.59 6,439,772.11 1,578,340.97 2,956,260.81 18,293,867.94 |  | 1,906,476.46 5,413,017.59 6,439,772.11 1,578,340.97 2,956,260.81 18,293,867.94 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-014 | 23) Concreting of Road (portion) at Delos Santos Compound, Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 60 | GF | 571058.78 |  | 571058.78 | 550109.93 |  | 550109.93 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-026 | 24) Concreting of Calasiao Feeder Road (portion), Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 80 | GF | 1986361.96 |  | 1986361.96 | 1953207.61 |  | 1953207.61 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-016 | 25) Repair/Repainting of Ynares Multi-Purpose Building at Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 48 | GF | 537593.66 | 537593.66 |  | 520589.48 | 520589.48 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-018 | 26) Repair/Repainting of Ynares Multi-Purpose Covered Court at Sunnyville 4, Brgy. Ampid I, San Mateo, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 45 | GF | 1191388.97 | 1191388.97 |  | 1167297.34 | 1167297.34 |  | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-027 | 27) Improvement of 2-Storey Ynares Multi-Purpose Bldg. (HOA Office) at Bankers Village 5 Phase 9-1, Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 76 | GF | 1329908.62 |  | 1329908.62 | 1298936.13 |  | 1298936.13 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-063 | 28) Concreting of Road along Horseshoe Drive, Brgy. Sto. Niño, San Mateo, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 100 | GF | 2458189.21 |  | 2458189.21 | 2428346.6 |  | 2428346.6 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-018 | 29) Improvement of 17.0 x 30.0 Ynares Multi-Purpose Covered Court at Sitio Aguho, Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 54 | GF | 1431259.43 |  | 1431259.43 | 1405222.04 |  | 1405222.04 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-019 | 30) Repair/Repainting of 25 x 36m Ynares Multi-Purpose Covered Court at Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 84 | GF | 2594561.97 | 2594561.97 |  | 2562310.13 | 2562310.13 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-013 | 31) Concreting of Various Roads at Southville 10 Area, Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 100 | GF | 2689590.55 | 2689590.55 |  | 2660696.91 | 2660696.91 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-065 | 32) Concreting of Road with Drainage Canal at Road Lot 10, Purok 7, Lupang Arenda, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 160 | GF | 5092103.43 |  | 5092103.43 | 5046107.98 |  | 5046107.98 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-001-006 | 33) Construction of Rescue Center at Brgy. Manggahan, Montalban, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 240 | GF | 97890405.32 |  | 97890405.32 | 97840180.16 |  | 97840180.16 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-001-001 | 34) Construction of Teresa Public Market, Brgy. San Gabriel, Teresa, Rizal | PEO |  | Public Bidding | 2022-01-03 | 7-13-Jan-22 | 2022-01-19 |  | 2022-01-27 | 2022-02-02 | 2022-02-14 |  | 2022-02-18 | 2022-02-24 | 2022-03-04 | 380 | GF | 146911641.19 |  | 146911641.19 | 146852631.35 |  | 146852631.35 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-008 | 1) Improvement of Ynares Multi-Purpose Covered Court at Doña Justa Village Phase I, Brgy. San Roque, Angono, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 90 | GF | 3399054.07 |  | 3399054.07 | 3362089.46 |  | 3362089.46 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-030 | 2) Repair/Repainting of Ynares School Buildings at Vicente Madrigal National High School, Brgy. Palangoy, Binangonan, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 112 | SEF | 8987202.95 | 8987202.95 |  | 8922164.63 | 8922164.63 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-031 3000-000-1-2-11-399-005-032 | 3) Improvement/Repair of Ynares Multi-Purpose Covered Court/Stage at Brgy. Lunsad, Binangonan, Rizal a) Improvement of Ynares Multi-Purpose Covered Court at Lunsad Elem. School, Brgy. Lunsad b) Repair of Stage at Lunsad Elem. School, Brgy. Lunsad | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 60 | SEF | 715,075.23 227,939.25 943,014.48 | 227939.25 | 715075.23 | 100,788.04 217,220.04 918,008.90 | 217220.04 | 100788.04 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-033 | 4) Repair/Repainting of Ynares School Buildings at Ithan Elem. School, Brgy. Ithan, Binangonan, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 90 | SEF | 2559583.36 | 2559583.36 |  | 2530578.97 | 2530578.97 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-038 | 5) Construction of Covered Pathwalk at Baras-Pinugay Elem. School (One Ynares Annex), Brgy. San Salvador, Baras, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 60 | SEF | 1096560.17 |  | 1096560.17 | 1073201.18 |  | 1073201.18 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-039 | 6) Improvement of School Bldg. at Painaan Elem. School-Heroes Ville Annex, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 45 | SEF | 672786.7 |  | 672786.7 | 653679.65 |  | 653679.65 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-042 | 7) Improvement of Ynares Multi-Purpose Covered Court at Baras Senior High School, Brgy. San Juan, Baras, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 60 | SEF | 1104898.6 |  | 1104898.6 | 1082757.08 |  | 1082757.08 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-045 | 8) Repair/Repainting of Ynares School Bldgs. at Exodus Elem. School, Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 64 | SEF | 1203916.13 | 1203916.13 |  | 1180839.78 | 1180839.78 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-046 | 9) Repair/Repainting of Ynares Multi-Purpose Covered Court at Exodus Elem. School, Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 68 | SEF | 1348624.94 | 1348624.94 |  | 1323521.95 | 1323521.95 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-049 | 10) Construction of Ynares Stage at Catalino D. Salazar National High School, Brgy. Subay, Cardona, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 70 | SEF | 1618776.37 |  | 1618776.37 | 1587697.11 |  | 1587697.11 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-050 | 11) Repair/Repainting of 2-Storey 6-Rooms Ynares School Building at Patunhay-Calahan Elem. School, Cardona, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 50 | SEF | 1518782.98 | 1518782.98 |  | 1490700.84 | 1490700.84 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-052 | 12) Repair/Repainting of Ynares School Buildings at Jalajala Elem. School, Brgy. 1st District, Jalajala, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 90 | SEF | 2685048.84 | 2685048.84 |  | 2656033.83 | 2656033.83 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-053 | 13) Repair/Repainting of Ynares Multi-Purpose Covered Court and Ynares Stage at Jalajala Elem. School, Brgy. 1st District, Jalajala, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 90 | SEF | 1684110.58 | 1684110.58 |  | 1648112.9 | 1648112.9 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-055 | 14) Repair/Repainting of Stage at Tomas Claudio Elem. School, Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 48 | SEF | 457797.7 | 457797.7 |  | 438718.86 | 438718.86 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-059 | 15) Constructon of Covered Pathwalk at Bugarin National High School, Brgy. Halayhayin, Pililla, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 96 | SEF | 1952273.17 |  | 1952273.17 | 1919395.94 |  | 1919395.94 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-060 | 16) Construction of Covered Pathwalk at Pililla Elem. School, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 60 | SEF | 1774639.21 |  | 1774639.21 | 1743469.79 |  | 1743469.79 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-061 | 17) Repair/Repainting of Ynares School Buildings at Malaya Elem. School, Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 215 | SEF | 6573680.84 | 6573680.84 |  | 6520597.31 | 6520597.31 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-064 | 18) Repair/Repainting of Ynares Multi-Purpose Covered Court at Gen. Licerio Geronimo Mem. National High School, Brgy. Geronimo, Rodriguez, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 90 | SEF | 3681270.73 | 3681270.73 |  | 3647108.37 | 3647108.37 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-065 | 19) Improvement of Ynares Multi-Purpose Covered Court at Gen Licerio Geronimo Mem. National High School, Brgy. Geronimo, Rodriguez, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 60 | SEF | 2594481.6 |  | 2594481.6 | 2567389.32 |  | 2567389.32 | Engr. Nelson Pajarillo Simon King
9000-900-1-0-40-001-001-002 | 20) Construction of Stone Masonry Riprap at Sapang Labo Creek, Abuab, Brgy. Dulong Bayan 2, San Mateo, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 280 | GF | 58738.43 |  | 58738.43 | 58628235.62 |  | 58628235.62 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-012 | 21) Construction of Stone Masonry for Side Protection (Portion) along Nangka River Purok 3, Brgy. Silangan, San Mateo, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 320 | GF | 68645713.03 |  | 68645713.03 | 68507615.28 |  | 68507615.28 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-0013-015 | 22) Rehabilitation/Construction of Stone Masonry for Side Protection (Portion) of Creek at Brgy. Wawa, Tanay, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 160 | GF | 7766224.81 |  | 7766224.81 | 7695405.48 |  | 7695405.48 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-082 | 23) Improvement of Ynares Multi-Purpose Covered Court at Don Domingo Capistrano Elem. School, Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 45 | SEF | 535427.86 |  | 535427.86 | 517406.7 |  | 517406.7 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-083 | 24) Repair/Repainting of 2-Storey 6-Rooms Ynares School Building at San Andres Elem. School, Brgy. San Andres, Tanay, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 60 | SEF | 2069309.05 | 2069309.05 |  | 2043276.43 | 2043276.43 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-074 | 25) Improvement of Perimeter Fence, Replacement/Improvement of Gates at Sitio Simona Elem. School, Brgy. San Isidro, Taytay, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 80 | SEF | 1138792.25 |  | 1138792.25 | 1116669.12 |  | 1116669.12 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-003-021 | 26) Construction of Slope Protection/Retaining Wall (Various Creek), Taytay, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 90 | GF | 2603515.45 |  | 2603515.45 | 256454545.74 |  | 256454545.74 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-020 | 27) Improvement of Drainage System at Switzerland St., Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 60 | GF | 846882.65 |  | 846882.65 | 826515.23 |  | 826515.23 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-003-024 | 28) Improvement of Drainage System at Blk. 35 Pilipinas St., West Bank, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 60 | GF | 895457.78 |  | 895457.78 | 878409.08 |  | 878409.08 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-007 3000-000-1-2-11-511-005-009 | 29) Construction of Guardhouse and Concreting of Pathway at Brgy. Dalig and Brgy. Poblacion, Teresa, Rizal a) Construction of Guardhouse at Pantay National High School, Brgy. Dalig b) Concreting of Pathway going to Ynares Multi-Purpose Covered Court/MRF, Brgy. Poblacion | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 60 | GF | 622,210.23 167,535.81 789,746.04 |  | 622,210.23 167,535.81 789,746.04 | 615,621.98 160,097.46 775,719.44 |  | 615,621.98 160,097.46 775,719.44 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-017 | 30) Concreting of Sitio Road at Sitio Ibabaw 2, Brgy. Dulumbayan, Teresa, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 100 | GF | 2305088.58 |  | 2305088.58 | 2281255.79 |  | 2281255.79 | Engr. Nelson Pajarillo Simon King
3000-400-1-1-11-006-003 | 31) Construction of 2-Units Artesian Well at Maximiniano Comp.,Sitio Buhangin, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 54 | GF | 807940.64 |  | 807940.64 | 791672.46 |  | 791672.46 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-094 | 32) Repair/Repainting of 2-Storey 6-Rooms Ynares School Building at Teresa National High School, Brgy. Bagumbayan, Teresa, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 45 | SEF | 1243758.86 | 1243758.86 |  | 1213621.79 | 1213621.79 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-095 | 33) Improvement of 2-Storey 4-Rooms Ynares School Buildings at Teresa National High School, Brgy. Dulumbayan, Teresa, Rizal | PEO |  | Public Bidding | 2022-01-14 | 17-23-Jan-22 | 2022-01-24 |  | 2022-02-07 | 2022-02-10 | 2022-02-18 |  | 2022-02-24 | 2022-03-04 | 2022-03-18 | 65 | SEF | 1958429.96 |  | 1958429.96 | 1293307.38 |  | 1293307.38 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-034 | 1) Repair/Repainting of Ynares School Buildings at Margarito A. Duavit Integrated School, Brgy. Pila-Pila, Binangonan, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 180 | SEF | 6849126.23 | 6849126.23 |  | 6781100.67 | 6781100.67 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-035 | 2) Improvement of Ynares Multi-Purpose Covered Court at Pinagdilawan Elem. School, Brgy. Pinagdilawan, Binangonan, Rizal |  |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 100 | SEF | 3728346.53 |  | 3728346.53 | 3694218.33 |  | 3694218.33 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-036 | 3) Repair/Repainting of Ynares School Buildings at Calumpang Elem. School, Brgy. Calumpang, Binangonan, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 103 | SEF | 3996049.73 | 3996049.73 |  | 3958089.27 | 3958089.27 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-037 | 4) Repair/Repainting of Ynares School Buildings at Tayuman Elem. School, Brgy. Tayuman, Binangonan, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 180 | SEF | 7262740.73 | 7262740.73 |  | 7193650.22 | 7193650.22 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-040 3000-000-1-2-11-399-005-041 | 5) Improvement of Ynares School Building at Brgy. Pinugay, Baras, Rizal a) Improvement of 1-Storey 6-Rooms Ynares School Building at Baras-Pinugay Integrated High School, Brgy. Pinugay b) Improvement of 2-Units, 1-Storey, 3-Rooms Ynares School Building at Pinugay Elem. School, Brgy. Pinugay | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 60 | SEF | 532,353,53 496,582.28 1.028,935.81 |  | 532,353,53 496,582.28 1.028,935.81 | 517,067.26 490,496.08 1,007,563.34 |  | 517,067.26 490,496.08 1,007,563.34 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-047 3000-000-1-2-11-399-005-048 | 6) Repair/Repainting of Ynares School Buildings/Ynares Multi-Purpose Covered Court at Brgy. Sto. Domingo, Cainta, Rizal a) Repair/Repainting of Ynares School Buildings at St. Joseph Elem. School, Brgy. Sto. Domingo b) Repair/Repainting of Ynares Multi-Purpose Covered Court at St. Joseph Elem. School, Brgy. Sto..Domingo | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 60 | SEF | 170,7614.31 495,,073.80 2,202,688.11 | 170,7614.31 495,,073.80 2,202,688.12 |  | 1,692,305.38 487,324.81 2,179,630.19 | 1,692,305.38 487,324.81 2,179,630.20 |  | Engr. Nelson Pajarillo Simon King
3000-400-1-2-11-511-004-020 | 7) Construction of 1-StoreyYnares Multi-Purpose Hall at Block 108 Kalinisan St., Karangalan Village, Brgy. San Isidro, Cainta, Rizal |  |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 75 | SEF | 2699808.71 |  | 2699808.71 | 2688799.64 |  | 2688799.64 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-051 | 8) Repair/Repainting of Covered Pathwalk at Bagumbong Elem. School, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 40 | SEF | 667448.06 | 667448.06 |  | 650399.29 | 650399.29 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-054 | 9) Construction of Covered Pathwalk at Talaga Elem. School, Sitio Talaga, Brgy. Maybancal, Morong, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 60 | SEF | 1398602.66 |  | 1398602.66 | 1372597.04 |  | 1372597.04 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-056 | 10) Construction of 6x18m Ynares Multi-Purpose Covered Court at Pulong Kumanoy Elem. School, Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 90 | SEF | 2092116.5 |  | 2092116.5 | 2061048.39 |  |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-062 | 11) Improvement of Ynares School Buildings at Hulo National High School, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 45 | SEF | 892779.85 |  | 892779.85 | 876698.84 |  | 876698.84 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-063 | 12) Construction of Fence at Matagbak Elem. School, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 42 | SEF | 640159.42 |  | 640159.42 | 622121.81 |  | 622121.81 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-066 3000-000-1-2-11-399-005-067 | 13) Repair/Repainting/Improvement of Ynares School Buildings at Brgy. San Jose, Rodriguez, Rizal a) Repair/Repainting of Ynares School Buildings at Tagumpay National High School, Brgy. San Jose b) Improvement of 1-Storey Ynares School Building at Tagumpay National High School, Brgy. San Jose | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 160 | SEF | 6,602,730.16 489,109.20 7,091,839.36 | 6602730.16 | 489109.2 | 6,534,620.81 482,149.27 7,016,770.08 | 6534620.81 | 482149.27 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-068 | 14) Construction of Covered Pathwalk at Puray National High School, Brgy. Puray, Rodriguez, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 60 | SEF | 1368572.07 |  | 1368572.07 | 1341324.47 |  | 1341324.47 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-069 | 15) Construction of Stage at San Mateo Senior High School, Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 70 | SEF | 1199557.07 |  | 1199557.07 | 1175509.34 |  | 1175509.34 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-034 | 16) Installation of Steel Window Grills at DPWH School Bldg., at San Mateo Senior High School, Brgy. Guitnang Bayan II, San Mateo, Rizal |  |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 60 | SEF | 1536244.03 |  | 1536244.03 | 1507082.22 |  | 1507082.22 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-0770 | 17) Repair/Repainting of Ynares School Buildings at San Mateo National High School, Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 265 | SEF | 11497298.61 | 11497298.61 |  | 11318255.44 | 11318255.44 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-075 3000-000-1-2-11-399-005-076 | 18) Provision of Stair on Fill and Improvement of Ynares Stage at Brgy. Dolores, Taytay, Rizal a) Provision of Stair on Fill at Casimiro A. Ynares Mem. National High School, Brgy. Dolores b) Improvement of Ynares Stage at Casimiro A. Ynares Sr. Mem. National High School, Brgy. Dolores | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 60 | SEF | 763,719.02 167,229.66 930,948.68 | 763719.02 | 167229.66 | 747,999.33 162,897.96 910,897.29 | 747999.33 | 162897.96 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-077 | 19) Repair/Repainting of Ynares School Buildings at Dolores Elem. School, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 60 | SEF | 1117688.64 | 1117688.64 |  | 1094323.86 | 1094323.86 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-078 | 20) Repair/Repainting of Ynares School Buildings at San Francisco Elem. School, Brgy. Muzon, Taytay, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 90 | SEF | 3736833.37 | 3736833.37 |  | 3701798.35 | 3701798.35 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-079 | 21) Repair/Repainting of Ynares Multi-Purpose Covered Court at Hapay Na Mangga Elem. School, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 96 | SEF | 1468613.37 | 1468613.37 |  | 1439589.47 | 1439589.47 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-080 | 22) Concreting of School Ground (Portion) at Casimiro A. Ynares Sr. Mem. National High School, Brgy. Dolores, Taytay, Rizal |  |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 45 | SEF | 531276.93 |  | 531276.93 | 512159.47 |  | 512159.47 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-081 | 23) Construction of 4-Seater Comfort Room at Casimiro A. Ynares Sr. Mem. National High School, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 64 | SEF | 1458737.58 |  | 1458737.58 | 1427697.34 |  | 1427697.34 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-084 | 24) Repair/Repainting of Ynares School Building at Wawa Elem. School, Brgy. Wawa, Tanay, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 200 | SEF | 8791521.48 | 8791521.48 |  | 8722497.35 | 8722497.35 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-085 | 25) Repair/Repainting of Ynares Multi-Purpose Covered Court and Stage at Wawa Elem. School, Brgy. Wawa, Tanay, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 70 | SEF | 1944741.53 | 1944741.53 |  | 1909647.37 | 1909647.37 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-088 | 26) Improvement of Fence and School Gate at Teresa National High School,Brgy. Bagumbayan, Teresa, Rizal |  |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 45 | SEF | 472927.77 |  | 472927.77 | 457836.08 |  | 457836.08 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-089 | 27) Improvement of Ynares Multi-Purpose Covered Court and Stage at Pantay Integrated High School, Sitio Pantay, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 90 | SEF | 3104741.05 |  | 3104741.05 | 3071682.13 |  | 3071682.13 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-090 | 28) Improvement of 1-Storey 5-Rooms Ynares School Building at Pantay Integrated High School, Sitio Pantay, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 45 | SEF | 701067.74 |  | 701067.74 | 682130.02 |  | 682130.02 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-091 | 29) Repair/Repainting of Ynares School Building at Pantay Integrated High School, Sitio Pantay, Brgy. Dalig, Teresa, Rizal |  |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 50 | SEF | 1020383.34 | 1020383.34 |  | 1020429.65 | 1020429.65 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-092 | 30) Construction of Covered Pathwalk at Pantay Integrated High School, Sitio Pantay, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 72 | SEF | 1105783.03 |  | 1105783.03 | 1083735.52 |  | 1083735.52 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-093 | 31) Improvement of Ynares Multi-Purpose Covered Court at Teresa National High School, Brgy. Dulumbayan, Teresa, Rizal | PEO |  | Public Bidding | 2022-01-17 | 19-25-Jan-22 | 2022-01-26 |  | 2022-02-09 | 2022-02-14 | 2022-02-24 |  | 2022-03-03 | 2022-03-11 | 2022-03-17 | 50 | SEF | 1189647.7 |  | 1189647.7 | 1163647.65 |  | 1163647.65 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-043 | 1) Construction of 4-Storey 12-Rooms Ynares School Building at Francisco P. Felix Mem. National High School, Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding | 2022-01-18 | 21-27-Jan-22 | 2022-01-28 |  | 2022-02-11 | 2022-02-17 | 2022-02-28 |  | 2022-03-04 | 2022-03-11 | 2022-03-17 |  | SEF | 51134000.56 |  | 51134000.56 | 51005348.12 |  | 51005348.12 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-044 | 2) Construction of 4-Storey 12-Rooms Ynares School Building at Karangalan Elem. School, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding | 2022-01-18 | 21-27-Jan-22 | 2022-01-28 |  | 2022-02-11 | 2022-02-17 | 2022-02-28 |  | 2022-03-04 | 2022-03-11 | 2022-03-17 |  | SEF | 43909894.81 |  | 43909894.81 | 43852717.96 |  | 43852717.96 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-057 | 3) Construction of 3-Storey 15-Rooms Ynares School Building at Pililla Elem. School (Central), Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2022-01-18 | 21-27-Jan-22 | 2022-01-28 |  | 2022-02-11 | 2022-02-17 | 2022-02-28 |  | 2022-03-04 | 2022-03-11 | 2022-03-17 |  | SEF | 44816227.03 |  | 44816227.03 | 44761287.39 |  | 44761287.39 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-058 | 4) Construction of 3-Storey 6-Rooms Ynares School Building at Halayhayin Elem. School, Brgy.Halayhayin, Pililla, Rizal | PEO |  | Public Bidding | 2022-01-18 | 21-27-Jan-22 | 2022-01-28 |  | 2022-02-11 | 2022-02-17 | 2022-02-28 |  | 2022-03-04 | 2022-03-11 | 2022-03-17 |  | SEF | 20360873.48 |  | 20360873.48 | 20311753.87 |  | 20311753.87 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-072 | 5) Construction of 4-Storey 12-Rooms Ynares School Building at Ampid National High School, Brgy. Ampid, San Mateo, Rizal | PEO |  | Public Bidding | 2022-01-18 | 21-27-Jan-22 | 2022-01-28 |  | 2022-02-11 | 2022-02-17 | 2022-02-28 |  | 2022-03-04 | 2022-03-11 | 2022-03-17 |  | SEF | 37996660.59 |  | 37996660.59 | 37921517.35 |  | 37921517.35 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-073 | 6) Construction of 4-Storey 12-Rooms Ynares School Building at Maly Elem. School, Brgy. Maly, San Mateo, Rizal | PEO |  | Public Bidding | 2022-01-18 | 21-27-Jan-22 | 2022-01-28 |  | 2022-02-11 | 2022-02-17 | 2022-02-28 |  | 2022-03-04 | 2022-03-11 | 2022-03-17 |  | SEF | 46699967.22 |  | 46699967.22 | 46629263.68 |  | 46629263.68 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-086 | 7) Construction of 4-Storey 12-Rooms Ynares School Building at Simeon R. Bendana, Sr. Mem. Elem. School, Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding | 2022-01-18 | 21-27-Jan-22 | 2022-01-28 |  | 2022-02-11 | 2022-02-17 | 2022-02-28 |  | 2022-03-04 | 2022-03-11 | 2022-03-17 |  | SEF | 46760044.96 |  | 46760044.96 | 46691006.29 |  | 46691006.29 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-087 | 8) Construction of 4-Storey 8-Rooms Ynares School Building at Tanay National High School, Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding | 2022-01-18 | 21-27-Jan-22 | 2022-01-28 |  | 2022-02-11 | 2022-02-17 | 2022-02-28 |  | 2022-03-04 | 2022-03-11 | 2022-03-17 |  | SEF | 25485398.27 |  | 25485398.27 | 25434264.22 |  | 25434264.22 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-003-018 | 9) Upgrading of Road with Drainage Improvement at Gomez St., Kapalaran Subd., Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding | 2022-01-18 | 21-27-Jan-22 | 2022-01-28 |  | 2022-02-11 | 2022-02-17 | 2022-02-28 |  | 2022-03-04 | 2022-03-11 | 2022-03-17 |  | GF | 7199980.78 | 7199980.78 |  | 7130198.24 | 7130198.24 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-094 | 1) Concreting/Construction of Drainage Canal at 10th Street, San Martin Subd., Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 60 | GF | 1182333.83 |  | 1182333.83 | 1161306.1 |  | 1161306.1 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-044 3000-300-1-2-11-511-005-045 | 2) Repair/Repainting/Improvement of Ynares Multi-Purpose Building at Brgy. Poblacion Itaas and Brgy. San Isidro, Angono, Rizal a) Repair/Repainting of 3-Storey with Roof Deck Ynares Multi-Purpose Bldg. (Brgy. Hall), brgy. Poblacion Itaas b) Improvement of 2-Storey Ynares Multi-Purpose Building at Venus Compound, Brgy. San Isidro | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 80 | GF | 601,765.22 672,331.51 1,274,096.83 | 601765.22 | 672331.51 | 590,810.42 659,296.11 1,250,106.53 | 590810.42 | 659296.11 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-046 | 3) Construction of 2-Storey Ynares Multi-Purpose Building at Phase 1, Sta. Maria Subd., Brgy. Dalig, Antipolo, City | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 150 | GF | 3978681.63 |  | 3978681.63 | 3940519.01 |  | 3940519.01 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-023 | 4) Construction of 14x24m Ynares Multi-Purpose Covered Court at Tres Hermanas Village, Brgy. Mayamot, Antipolo, City |  |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 100 | GF | 4464503.8 |  | 4464503.8 | 4417486.04 |  | 4417486.04 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-021 | 5) Repair/Repainting of Ynares Multi-Purpose Covered Court at Phase 5 Lower Lucban, Brgy. Dela Paz, Antipolo, City | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 60 | GF | 1045065 | 1045065 |  | 1025434.13 | 1025434.13 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-022 | 6) Repair/Repainting of Ynares Multi-Purpose Covered Court at Vermont Royale Village, Brgy. Mayamot, Antipolo, City | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 60 | GF | 993865.64 | 993865.64 |  | 976897.82 | 976897.82 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-095 | 7) Construction of Drainage Canal at Manga St., Blooming Breeze Subd., (formerly Vocalan Compound), Brgy. Pag-Asa, Binangonan, Rizal |  |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 100 | GF | 1819914.05 |  | 1819914.05 | 1794648.95 |  | 1794648.95 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-096 | 8) Construction of Drainage Canal at Mabolo St., Blooming Breeze Subd., (formerly Vocalan Compound), Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 140 | GF | 3459516.81 |  | 3459516.81 | 3425110.96 |  | 3425110.96 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-098 | 9) Construction of Drainage Canal at Purok 1 to Purok 4, Brgy. Kinagatan, Binangonan, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 120 | GF | 2988117.5 |  | 2988117.5 | 2959410.79 |  | 2959410.79 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-064 | 10) Construction of 2-Storey Ynares Multi-Purpose Building at Brgy. Tagpos, Binangonan, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 140 | GF | 4367694.13 |  | 4367694.13 | 4322522.56 |  | 4322522.56 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-099 | 11) Construction of Drainage Canal (portion) at Magsaysay Blvd., Sitio Mangga Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 100 | GF | 2236257.88 |  | 2236257.88 | 2211119.45 |  | 2211119.45 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-050 | 12) Construction of 2-Storey Ynares Multi-Purpose Building at Esla Urban Homes Marick Subd., Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 156 | GF | 4155860.14 |  | 4155860.14 | 4111579.63 |  | 4111579.63 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-051 | 13) Construction of 2-Storey Ynares Multi-Purpose Building at Vista Verde Exec. Village Phase 9, Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 156 | GF | 4146278.89 |  | 4146278.89 | 4104200.5 |  | 4104200.5 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-100 | 14) Concreting of Road (portion) at Purok 6, Sitio Sampalok, Brgy. Looc, Cardona, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 100 | GF | 2904785.25 |  | 2904785.25 | 2877127.47 |  | 2877127.47 | Engr. Nelson Pajarillo Simon King
3000-400-1-1-11-006-004 | 15) Construction of Water System Level II at Bgry. Tuna, Cardona, Rizal |  |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 148 | GF | 4317619.24 |  | 4317619.24 | 4275597.81 |  | 4275597.81 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-102 | 16) Improvement/Construction of Drainage Canal at Kalaw St. and J.P Burgos St., Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 100 | GF | 3499834.51 |  | 3499834.51 | 3453730.95 |  | 3453730.95 | Engr. Nelson Pajarillo Simon King
3000-400-1-1-11-006-005 | 17) Construction of 3-Units Artesian Well at Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 72 | GF | 981684.57 |  | 981684.57 | 963520.77 |  | 963520.77 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-103 | 18) Construction of Stone Masonry for Slope Protection (portion) of Quisao River,Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 140 | GF | 4651577.15 |  | 4651577.15 | 4610512.17 |  | 4610512.17 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-052 | 19) Construction of 2-Storey Ynares Multi-Purpose Bldg. (HOA Office) at Aranzazu Subd. Brgy. Burgos, Rodriguez, Rizal |  |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 138 | GF | 3526824.52 |  | 3526824.52 | 3495719.34 |  | 3495719.34 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-053 | 20) Construction of 2-Storey Ynares Multi-Purpose Bldg., (BADAC, VAWC) Brgy. Burgos, Rodriguez, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 132 | GF | 3407433.24 |  | 3407433.24 | 3376317.35 |  | 3376317.35 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-027 | 21) Construction of 15x30m Ynares Multi-Purpose Covered Court (Rafter Type) at Eastwood Villa (Phase 1), at Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 120 | GF | 5201763.8 |  | 5201763.8 | 5148605.84 |  | 5148605.84 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-106 | 22) Repair/Repainting of School Bldg., at Kasiglahan Vill. Senior High School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 120 | GF | 4892923.63 | 4892923.63 |  | 4843870.13 | 4843870.13 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-033 | 23) Repair/Repainting of Ynares Multi-Purpose Covered Court at Portbello Homes, Brgy. Guitnang Bayan 1, San Mateo, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 45 | GF | 964525.33 | 964525.33 |  | 945417.39 | 945417.39 |  | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-054 | 24) Construction of Ynares Stage at Sitio Mabolo at Brgy. Puray, Rodriguez, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 68 | GF | 1419962.98 |  | 1419962.98 | 1396801.29 |  |  | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-056 3000-300-1-1-31-392-004-025 | 25) Improvement of Ynares Multi-Purpose Bldg. & Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. San Isidro, Rodriguez, Rizal a) Improvement of 2-Storey Ynares Multi-Purpose Bldg. & Perimeter Fence at La Solidaridad Estate Homes Phase I-B, Brgy. San Isidro b) Installation of Electrical Lighting System of 14x24m Ynares Multi-Purpose Covered Court at Eastwood Residences Phase 6A, Brgy. San Isidro | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 60 | GF | 704,,422.44 335,010.91 1,039,433.35 |  | 704,,422.44 335,010.91 1,039,433.35 | 696,098.99 323,219.48 1,019,318.47 |  | 696,098.99 323,219.48 1,019,318.47 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-057 3000-300-1-2-11-511-005-058 3000-000-1-1-31-392-004-026 | 26) Construction/Extension of Ynares Multi-Purpose Building & Welcome Arc and Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. San Isidro, Rodriguez, Rizal a.) Construction/Extension of Ynares Multi-Purpose Building at Southville 8C, Phase 1N, Brgy. San Isidro b) Construction of Welcome Arc at Eastwood Residences Phase 3A, Brgy. San Isidro c) Installation of electrical Lighting System of 17x30m Ynares Multi-Purpose Covered Court at Eastwood Residences Phase 8/8A, Brgy. San Isidro | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 60 | GF | 414,416.22 321,331.67 447,299.67 1,183,047.56 |  | 414,416.22 321,331.67 447,299.67 1,183,047.56 | 407,893.77 310,621.30 443,594.61 1,162,109.58 |  | 407,893.77 310,621.30 443,594.61 1,162,109.58 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-029 3000-000-1-1-31-392-004-030 | 27) Installation/Improvement of Electrical Lighting System of Ynares Multi-Purpose Covered Court , Brgy. San Jose, Rodriguez, Rizal a) Installation of Electrical Lighting System of 15x30m Ynares Multi-Purpose Covered Court at Villa Ana Maria Subd., Brgy. San Jose b) Improvement of Electrical Lighting System of 17x30m Ynares Multi-Purpose Covered Court at North Triangle Alliance (Montalban Hts.), Brgy. San Jose | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 40 | GF | 380.339.87 355,595.31 735,935.18 |  | 380.339.87 355,595.31 735,935.18 | 371,470.69 347,257.64 718,728.38 |  | 371,470.69 347,257.64 718,728.38 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-399-005-108 | 28) Repair/Repainting of Ynares School Buildings at Justice Vicente Santiago Elem. School, Brgy. Ampid 2, San Mateo, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 92 | GF | 1676707.36 | 1676708.36 |  | 1651507.35 | 1651508.35 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-106 8000-000-1-1-51-001-002-107 | 29) Asphalt Overlaying at Brgy. Guinayang, San Mateo, Rizal a) Asphalt Overlaying of Road at Santiago St., Brgy. Guinayang b) Asphalt Overlaying of Magsikap St., Brgy. Guinayang | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 60 | GF | 962,910.28 569,833.33 1,532,743.61 | 962,910.28 569,833.33 1,532,743.62 |  | 946,293.39 563,390.82 1,509,684.21 | 946,293.39 563,390.82 1,509,684.22 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-108 | 30) Construction of Drainage Canal at M. Borja St., Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 140 | GF | 4067745.94 |  | 4067745.94 | 4031684.47 |  | 4031684.47 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-035 | 31) Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 80 | GF | 1999762.39 | 1999762.39 |  | 1972644.17 | 1972644.17 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-109 | 32) Concreting (portion) of Ka Maning Road, Brgy. Tandang Kutyo, Tanay, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 120 | GF | 4514555.08 |  | 4514555.08 | 4470596.34 |  | 4470596.34 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-036 | 33) Repair/Repainting of Ynares Multi-Purpose Covered Court at Camp Mateo Capinpin, Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 108 | GF | 3895458.62 | 3895458.62 |  | 3858316.46 | 3858316.46 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-116 | 34) Construction of Stone Masonry for Slope Protection (portion) at Laiban National High School, Brgy. Laiban, Tanay, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 60 | GF | 1106605.5 |  | 1106605.5 | 1087554.66 |  | 1087554.66 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-069 | 35) Improvement of 2-Storey Ynares Multi-Purpose Building (Brgy. Hall) at Brgy. Calumpang- Sto. Cristo, Teresa, Rizal | PEO |  | Public Bidding | 2022-01-25 | 27-Jan-2-Feb-22 | 2022-02-02 |  | 2022-02-16 | 2022-02-22 | 2022-03-04 |  | 2022-03-09 | 2022-03-14 | 2022-03-17 | 54 | GF | 1689328.23 |  | 1689328.23 | 1660127.31 |  | 1660127.31 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-51-392-004-020 | 1) Repair/Repainting of Ynares Multi-Purpose Covered Court at Venus Compound, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 95 | GF | 1611991.05 | 1611991.05 |  | 1587867.94 | 1587867.94 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-112 | 2) Improvement of Drainage System at San Vicente Elem. School, Brgy. San Vicente, Angono, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 84 | GF | 1323150.36 |  | 1323150.36 | 1302095.63 |  | 1302095.63 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-113 | 3) Repair/Repainting of Ynares School Building at San Vicente Elem. School, Brgy. San Vicente, Angono, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 60 | GF | 1557999.02 | 1557999.02 |  | 1531897.28 | 1531897.28 |  | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-064 | 4) Construction of Stage at Sitio Lupanggue, Brgy. Sta. Cruz, Antipolo City | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 70 | GF | 1239201.32 |  | 1239201.32 | 1216183.95 |  | 1216183.95 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-047 | 5) Improvement of 2-Storey Ynares Multi-Purpose Building (Brgy. Hall/ Health Center) at Brgy. Kasile, Binangonan, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 68 | GF | 902914.72 |  | 902914.72 | 884883.75 |  | 884883.75 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-097 | 6) Concreting of Road at Venaville Compound, Sitio Gupiing, Brgy. Lunsad, Binangonan, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 80 | GF | 1751031.91 |  | 1751031.91 | 1722020.51 |  | 1722020.51 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-048 3000-300-1-2-11-511-005-049 | 7) Repair/Repainting/Improvement of Ynares Multi-Purpose Building at Brgy. Tayuman, Binangonan, Rizal a) Repair/Repainting of Ynares Multi-Purpose Building (ALS Bldg.), Brgy. Tayuman b) Improvement of Ynares Multi-Purpose Building (Senior Citizen’s Bldg.) Brgy. Tayuman | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 60 | GF | 530,797.11 525,872.82 1,056,669.93 | 530797.11 | 525872.82 | 515,411.43 513,195.81 1,028,607.24 | 515411.43 | 513195.81 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-110 | 8) Concrete Reblocking and Rehabilitation of Headwalls at E. Jacinto St., Sitio Gupiing, Brgy. Lunsad, Binangonan, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 60 | GF | 843076.69 |  | 843076.69 | 824034.41 |  | 824034.41 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-037 | 9) Repair/Repainting of Ynares Multi-Purpose Covered Court & Comfort Room at Tuazon Compound, Brgy. Tagpos, Binangonan, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 60 | GF | 1271378.17 | 1271378.17 |  | 1297317.08 | 1297317.08 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-196 | 10) Repair/Repainting of Ynares School Bldg.at Francisco P. Felix Mem. National High School, Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 46 | GF | 2281276.51 | 2281276.51 |  | 2251846.99 | 2251846.99 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-097 | 11) Repair/Repainting of Ynares School Bldg. at Francisco P. Felix Mem. National High School, JICA -Annex ROTC Ave., Brgy. San Juan,Cainta, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 46 | GF | 1761871.29 | 1761871.29 |  | 1730862.72 | 1730862.72 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-098 | 12) Repair/Repainting of Ynares Multi-Purpose Covered Court at Saint Anthony | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 90 | GF | 769826.02 | 769826.02 |  | 781871.22 | 781871.22 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-111 | 13) Improvement of Drainage Canal at Matahimik St., Brgy. San Roque, Cainta, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 80 | GF | 1290230.6 |  | 1290230.6 | 1265950.64 |  | 1265950.64 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-112 | 14) Concreting of Road at J.P. Rizal St., Purok 3, Brgy. Subay, Cardona, Rizal |  |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 80 | GF | 1298279.38 |  | 1298279.38 | 1276100.87 |  | 1276100.87 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-101 | 15) Concreting of Road at Sitio Manggahan, Brgy. 2nd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 60 | GF | 597881.23 |  | 597881.23 | 581795.35 |  | 581795.35 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-099 | 16) Repair/Repainting of Ynares Multi-Purpose Covered Court and Stage at Pagkalinawan Elem. School, Brgy. Pagkalinawan, Jalajala, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 60 | GF | 754588.56 | 754588.56 |  | 736560.21 | 736560.21 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-100 | I7) Improvement of Ynares Multi-Purpose Covered Court and Stage at Pagkalinawan Elem. School, Brgy. Pagkalinawan, Jalajala, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 76 | GF | 795835.64 |  | 795835.64 | 775747.48 |  | 775747.48 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-038 3000-300-1-2-11-511-005-066 | 18) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court and Ynares Multi-Purpose Building at Brgy. Punta and Brgy. Special District, Jalajala, Rizal a.) Repair/Repainting of Ynares Multi-Purpose Covered Court at Punta Elem. School, Brgy. Punta, b.) Improvement of 1-Storey Ynares Multi-Purpose Bldg. at Brgy. Special District, | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 100 | GF | 686,688.94 696,467.26 1,383,156.20 | 686688.94 | 696467.26 | 679,813.21 677,236.11 1,257,049.32 | 679813.21 | 677236.11 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-067 | 19) Repair/Repainting of Various Ynares Waiting Shed & Welcome Arc at Brgy. Palaypalay, Jalajala, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 60 | GF | 419438.79 | 419438.79 |  | 403395.28 | 403395.28 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-101 | 20) Repair/Repainting of Stage at Roman Tantiongco Mem. Elem. School, Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 45 | GF | 245140.98 | 245140.98 |  | 232099.95 | 232099.95 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-113 | 21) Asphalt Overlay/Concrete Reblocking of Vicencio St., Brgy. Niogan, Pililla, Rizal |  |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 60 | GF | 875419.08 | 875419.08 |  | 857389.31 | 857389.31 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-114 | 22) Construction of Stone Masonry Headwall (portion) of Wawa Wharf & Boulevard Extension, Brgy. Wawa, Pililla, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 60 | GF | 1049997.59 |  | 1049997.59 | 1022610.11 |  | 1022610.11 | Engr. Nelson Pajarillo Simon King
3000-400-1-1-11-006-006 | 23) Repair/Repainting of Brgy. Health Center at Brgy. Niogan, Pililla, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 50 | GF | 585366.25 | 585366.25 |  | 568307.52 | 568307.52 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-103 | 24) Repair / Repainting of Ynares School Bldg., of Gen Licerio Geronimo National High School, Brgy. Geronimo, Rodriguez, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 60 | GF | 706917.27 | 706917.27 |  | 687899.55 | 687899.55 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-102 3000-300-1-2-11-511-005-055 3000-000-1-1-31-392-004-024 | 25) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court and Ynares Multi-Purpose Building at Brgy. Balite , Brgy. San Isidro and Brgy. Burgos, Rodriguez, Rizal a.)Repair/Repainting of Ynares Multi-Purpose Covered Court/Pathwalk/Stage at Eulogio Rodriguez Jr. Elem. School, Brgy. Balite, b.) Improvement of 2 Storey Ynares Multi-Purpose Building (HOA Office) at Southville 8A, Block 28, at Brgy. San Isidro, c.) Improvement of Ynares Multi-Purpose Covered Court at Montavilla Subd., Phase II, Brgy. Burgos |  |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 90 | GF | 649,573.26 303,751.36 267,689.72 1,221,014.34 | 649573.26 | 303,751.36 267,689.72 | 632,162,57 301,022.72 263,824.20 1,197,009.49 | 632,162,57 | 301,022.72 263,824.20 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-028 | 26) Repair/Repainting of Ynares Multi-Purpose Covered Court at Sitio Tanag, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 76 | GF | 1209838.26 | 1209838.26 |  | 1185704.39 | 1185704.39 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-511-005-060 3000-000-1-2-11-511-005-061 | 27) Repair/Repainting/Improvement of Ynares Multi-Purpose Building at Brgy. San Jose, Rodriguez, Rizal a.)Repair/Repainting of 2 Storey Ynares Multi-Purpose Building ( HOA Office ) At North Triangle Alliance Vill., Brgy. San Jose, b.)Improvement Of Multi-Purpose Building (HOA Office) At Isla Montalban Hts. Brgy. San Jose, | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 80 | GF | 428,647.78 399.282.11 827,929.89 | 428647.78 | 399.282.11 | 427,453.97 381,297.53 808,751.50 | 427453.97 | 381297.53 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-105 3000-300-1-2-11-511-005-063 3000-300-1-2-11-511-005-070 3000-000-1-1-31-392-004-039 | 28) Improvement/Repair/Repainting of Perimeter Fence, Ynares Multi-Purpose Building, Comfort Room and Ynares Multi-Purpose Covered Court at Brgy. San Jose, Rodriguez, Rizal a.)Improvement of Perimeter Fence at Kasiglahan Village Senior High School, Brgy. San Jose, b.)Improvement of Ynares Multi-Purpose Bldg., at Montalban Heights Phase 2, Brgy., San Jose, c.)Repair/Repainting of 2-Seater Comfort Room at Montalban Heights Phase 2, Brgy. San Jose d.)Impr./Extension of Fence at Ynares Multi-Purpose Covered Court at Montalban Heights Phase 2, Brgy., San Jose, | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 90 | GF | 914,102.72 381,397.27 55,530.59 312,722.34 1,663,752.94 | 55530.59 | 914,102.72 381,397.27 312,722.3 | 898,148.79 375,578.52 53,136.59 309,372.85 1,636,236.75 | 53136.59 | 898,148.79 375,578.52 309,372.85 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-031 | 29) Improvement of Ynares Multi-Purpose Covered Court at Phase 1K-1, Kasiglahan Village, Southville 8C, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 60 | GF | 1793083.99 |  | 1793083.99 | 1765009.54 |  | 1765009.54 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-104 | 30) Construction of Stone Masonry For Side Protection (Portion) Mango River (Hinayon Cmpd. ), at Brgy. Manggahan, Rodriguez, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 60 | GF | 997171.48 |  | 997171.48 | 979087.02 |  | 979087.02 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-123 | 31) Construction of Ynares Multi-Purpose Covered Court at East Bellevue Extension Residence Subd., Brgy. San Isidro,Rodriguez, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 96 | GF | 2838312.96 |  | 2838312.96 | 2809213.09 |  | 2809213.09 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-034 3000-000-1-2-11-399-005-109 3000-000-1-2-11-399-005-110 | 32) Improvement of Ynares Multi-Purpose Covered Court and Construction of Flag Pole/Drainage Canal at Brgy. Guitnang Bayan 1 and Brgy. Sta. Ana, San Mateo, Rizal a.)Improvement of Ynares Multi-Purpose Covered Court at Divine Mercy Village, Brgy. Guitnang Bayan 1, b.)Construction of Flag Pole at San Mateo Elem. School, Brgy. Sta. Ana, c.) Construction of Drainage Canal at San Mateo Elem. School, Brgy. Sta. Ana, | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 80 | GF | 552,302.90 349,099.41 268,425.87 1,169,828.18 |  | 552,302.90 349,099.41 268,425.87 1,169,828.18 | 531,287.44 342,749.03 263,676.87 1,137,713.34 |  | 531,287.44 342,749.03 263,676.87 1,137,713.34 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-111 | 33) Repainting of School Buildings at Cresdaville Elem. School, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 56 | GF | 758063.06 |  |  | 741179.35 |  |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-115 | 34) Concreting of School Ground with Drainage Canal at Teresa National High School, Brgy. Bagumbayan, Teresa, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 60 | GF | 910892.43 |  |  | 891781.88 |  |  | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-068 | 35) Repair/Repainting of 2-Storey Ynares Multi-Purpose Building (Brgy. Hall) at Brgy. Bagumbayan, Teresa, Rizal | PEO |  | Public Bidding |  | 31-Jan-6-Feb-22 | 2022-02-07 |  | 2022-02-18 | 2022-02-22 | 2022-03-03 |  | 2022-03-09 | 2022-03-15 | 2022-03-21 | 50 | GF | 444006.39 |  |  | 429001.8 |  |  | Engr. Nelson Pajarillo Simon King
3000-400-1-2-21-006-002 | 1) Construction of RPHS Building & Training Center in Brgy. San Juan, Morong, Rizal | PEO | [15 empty] | 499694947.98 | CANCELLED
3000-300-1-2-11-511-005-065 | 1A) Repair/Repainting of 2-Storey Ynares Multi-Purpose Building (Brgy. Hall) at Brgy. Pila-Pila, Binangonan, Rizal | PEO |  | Public Bidding | 2022-02-07 | 3-9 Feb. 22 | 2022-02-04 |  | 2022-02-22 | 2022-02-24 | 2022-03-07 |  | 2022-03-11 | 2022-03-18 | 2022-03-23 | 60 | GF | 1117067.21 | 1117067.21 |  | 1099015.58 | 1099015.58 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-21-009-008 | 2) Installation of Steel Ladder at Margarito A. Duavit Memorial Hospital, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding | 2022-02-07 | 3-9 Feb. 22 | 2022-02-04 |  | 2022-02-22 | 2022-02-24 | 2022-03-07 |  | 2022-03-11 | 2022-03-18 | 2022-03-23 | 30 | GF | 214960.99 |  | 214960.99 | 203103.28 |  | 203103.28 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-399-005-114 | 3) Repair/Repainting of Ynares School Building at Sampad Elem. School, Brgy. Sampad, Cardona, Rizal | PEO |  | Public Bidding | 2022-02-07 | 3-9 Feb. 22 | 2022-02-04 |  | 2022-02-22 | 2022-02-24 | 2022-03-07 |  | 2022-03-11 | 2022-03-18 | 2022-03-23 | 88 | GF | 2070865.91 | 2070865.91 |  | 2040790.27 | 2040790.27 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-010 | 4) Construction of Multi-Purpose Covered Court at Brgy. 1st District, Jalajala, Rizal | PEO |  | Public Bidding | 2022-02-07 | 3-9 Feb. 22 | 2022-02-04 |  | 2022-02-22 | 2022-02-24 | 2022-03-07 |  | 2022-03-11 | 2022-03-18 | 2022-03-23 | 116 | GF | 5499964 |  | 5499964 | 5451449.09 |  | 5451449.09 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-115 | 5) Improvement of Wharf at G. Del Pilar, Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding | 2022-02-07 | 3-9 Feb. 22 | 2022-02-04 |  | 2022-02-22 | 2022-02-24 | 2022-03-07 |  | 2022-03-11 | 2022-03-18 | 2022-03-23 | 90 | GF | 1647998.64 |  | 1647998.64 | 1622891.5 |  | 1622891.5 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-104 | 6) Construction/Provision Of Wash Facilities (Water,Sanitation & Hygiene) at Macabud National High School, Brgy. Macabud, Rodriguez, Rizal | PEO |  | Public Bidding | 2022-02-07 | 3-9 Feb. 22 | 2022-02-04 |  | 2022-02-22 | 2022-02-24 | 2022-03-07 |  | 2022-03-11 | 2022-03-18 | 2022-03-23 | 60 | GF | 1171415.44 |  | 1171415.44 | 1151387.24 |  | 1151387.24 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-105 | 7) Concreting of Road With Drainage Canal along T. Manuel St. Brgy. San Jose, Rodriguez, Rizal |  |  | Public Bidding | 2022-02-07 | 3-9 Feb. 22 | 2022-02-04 |  | 2022-02-22 | 2022-02-24 | 2022-03-07 |  | 2022-03-11 | 2022-03-18 | 2022-03-23 | 80 | GF | 1298348.47 |  | 1298348.47 | 1274215.36 |  | 1274215.36 | Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-031 | 8) Construction of Ynares Stage & Concrete Bleacher at Phase 1K-1, Kasiglahan Village, Southville 8C, Brgy. San Jose, Rodriguez, Rizal |  |  | Public Bidding | 2022-02-07 | 3-9 Feb. 22 | 2022-02-04 |  | 2022-02-22 | 2022-02-24 | 2022-03-07 |  | 2022-03-11 | 2022-03-18 | 2022-03-23 | 70 | GF | 1299986.27 |  | 1299986.27 | 1277900.35 |  | 1277900.35 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-107 | 9) Impr./Conc. of Ground at San Isidro Labrador Elem. School, at Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding | 2022-02-07 | 3-9 Feb. 22 | 2022-02-04 |  | 2022-02-22 | 2022-02-24 | 2022-03-07 |  | 2022-03-11 | 2022-03-18 | 2022-03-23 | 80 | GF | 1570670.12 |  | 1570670.12 | 1543577.24 |  | 1543577.24 | Engr. Nelson Pajarillo Simon King
80
8000-000-1-1-51-001-001-001 | 1) Ynares Center II, Rodriguez, Rizal (Sports Complex) |  |  | Public Bidding | 2022-02-11 | 14-20 Feb. 22 | 2022-02-21 |  | 2022-03-04 | 2022-03-08 | 2022-03-14 |  | 2022-03-17 | 2022-03-18 | 2022-03-23 |  |  | 499982602.28
3000-300-1-2-11-51-005-071 | 1) Construction of Retaining Wall (Slope Protection) at the Provincial Satellite Auditing Office (PSAO)- Rizal at Sitio Cabading, Brgy. Inarawan, Antipolo, City |  |  | Public Bidding | 2022-06-03 | 7-13 Jun. 22 | 2022-06-14 |  | 2022-06-28 | 2022-07-04 | 2022-07-15 |  | 2022-07-22 | 2022-07-29 | 2022-08-06 | 120 | GF | 9999685.64 |  | 9999685.64 | 9929506.58 |  | 9929506.58 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-122 | 2) Asphalt Overlaying/Concrete Reblocking at M. Oja Road at Brgy. Mahabang Parang, Municipality of Binangonan, Rizal |  |  | Public Bidding | 2022-06-03 | 7-13 Jun. 22 | 2022-06-14 |  | 2022-06-28 | 2022-07-04 | 2022-07-15 |  | 2022-07-22 | 2022-07-29 | 2022-08-06 | 140 | TF | 11774431.03 | 11774431.03 |  | 11645097.36 | 11645097.36 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-123 | 3) Improvement/Asphalt Overlaying (portion) of Road at P. Burgos Street at Brgy. Lunsad, Municipality of Binangonan, Rizal |  |  | Public Bidding | 2022-06-03 | 7-13 Jun. 22 | 2022-06-14 |  | 2022-06-28 | 2022-07-04 | 2022-07-15 |  | 2022-07-22 | 2022-07-29 | 2022-08-06 | 80 | TF | 8225568.97 |  | 8225568.97 | 8164099.92 |  | 8164099.92 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-120 | 4) Asphalt Overlaying/Concrete Reblocking of Pitallo St., Brgy. Mahabang Parang, Binangonan, Rizal |  |  | Public Bidding | 2022-06-03 | 7-13 Jun. 22 | 2022-06-14 |  | 2022-06-28 | 2022-07-04 | 2022-07-15 |  | 2022-07-22 | 2022-07-29 | 2022-08-06 | 100 | TF | 4327941.6 | 4327941.6 |  | 4287179.36 | 4287179.36 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-116 | 5) Repair/Repainting of Ynares School Building at Bilibiran Elementary School, Brgy.Bilibiran, Binangonan, Rizal |  |  | Public Bidding | 2022-06-03 | 7-13 Jun. 22 | 2022-06-14 |  | 2022-06-28 | 2022-07-04 | 2022-07-15 |  | 2022-07-22 | 2022-07-29 | 2022-08-06 | 100 | TF | 4594506.17 | 4594506.17 |  | 4555054.07 | 4555054.07 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-117 | 6) Construction of Hand Washing Facilities at Various Schools within the Province of Rizal a) Construction of Hand Washing Facility at Mahabang Parang Elementary School, Brgy. Mahabang Parang, Binangonan, Rizal b) Construction of Hand Washing Facility at Mahabang Parang National High School, Brgy. Mahabang Parang, Binangonan, Rizal c) Construction of Hand Washing Facility at Lunsad Elementary School, Brgy. Lunsad, Binangonan, Rizal d) Construction of Hand Washing Facility at Cainta Elementary School, Brgy. San Roque, Cainta, Rizal e) Construction of Hand Washing Facility at Kapalaran Elementary School, Brgy. San Juan, Taytay, Rizal f) Construction of Hand Washing Facility at Felix M. San Victores Elementary School, Brgy. San Isidro, Taytay, Rizal g) Construction of Hand Washing Facility at Sitio Simona Elementary School, Brgy. San Isidro, Taytay, Rizal |  |  | Public Bidding | 2022-06-03 | 7-13 Jun. 22 | 2022-06-14 |  | 2022-06-28 | 2022-07-04 | 2022-07-15 |  | 2022-07-22 | 2022-07-29 | 2022-08-06 | 170 | TF | 307,636.90 307,636.94 307,636.94 307,636.94 295,350.92 295,350.92 295,350.92 2,116,600.48 |  | 307,636.90 307,636.94 307,636.94 307,636.94 295,350.92 295,350.92 295,350.92 2,116,600.48 | 298.824.64 300,005.97 303,937.89 300,209.80 293,642.09 294,626.46 293.642.09 2,084,888.94 |  | 298.824.64 300,005.97 303,937.89 300,209.80 293,642.09 294,626.46 293.642.09 2,084,888.94 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-118 | 7) Construction of 2-Storey, 4-Rooms Ynares School Building at Mahabang Parang Elementary School, Brgy. Mahabang Parang, Binangonan, Rizal |  |  | Public Bidding | 2022-06-03 | 7-13 Jun. 22 | 2022-06-14 |  | 2022-06-28 | 2022-07-04 | 2022-07-15 |  | 2022-07-22 | 2022-07-29 | 2022-08-06 | 190 | TF | 12579753.74 |  | 12579753.74 | 12496577.52 |  | 12496577.52 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-118 | 8) Improvement/Concreting (portion) of Road at Pililla Public Market, Brgy. Bagumbayan, Pililla, Rizal |  |  | Public Bidding | 2022-06-03 | 7-13 Jun. 22 | 2022-06-14 |  | 2022-06-28 | 2022-07-04 | 2022-07-15 |  | 2022-07-22 | 2022-07-29 | 2022-08-06 | 140 | TF | 4290904.6 |  | 4290904.6 | 4250544.95 |  | 4250544.95 | Engr. Nelson Pajarillo Simon King
3000-400-1-2-21-009-001 | 9) Improvement of Rizal Provincial Hospital System (RPHS) Casimiro A. Ynares Sr. Memorial Hospital Building, Brgy. Burgos, Rodriguez, Rizal |  |  | Public Bidding | 2022-06-03 | 7-13 Jun. 22 | 2022-06-14 |  | 2022-06-28 | 2022-07-04 | 2022-07-15 |  | 2022-07-22 | 2022-07-29 | 2022-08-06 | 220 | GF | 6578359.72 |  | 6578359.72 | 6531095.24 |  | 6531095.24 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-119 | 10) Concreting (portion) of Road at Sitio Maysawa, Brgy. Cuyambay, Tanay, Rizal |  |  | Public Bidding | 2022-06-03 | 7-13 Jun. 22 | 2022-06-14 |  | 2022-06-28 | 2022-07-04 | 2022-07-15 |  | 2022-07-22 | 2022-07-29 | 2022-08-06 | 140 | TF | 5672058.4 |  | 5672058.4 | 5627461.55 |  | 5627461.55 | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-005-040 | 11) Repair of Bahay Pag-Asa |  |  | Public Bidding | 2022-06-03 | 7-13 Jun. 22 | 2022-06-14 |  | 2022-06-28 | 2022-07-04 | 2022-07-15 |  | 2022-07-22 | 2022-07-29 | 2022-08-06 | 60 | TF | 1881466.3 | 1881466.3 |  | 1854116.06 | 1854116.06 |  | Engr. Nelson Pajarillo Simon King
1000-000-1-1-11-007-004 | 12) Repair of Provincial Jail |  |  | Public Bidding | 2022-06-03 | 7-13 Jun. 22 | 2022-06-14 |  | 2022-06-28 | 2022-07-04 | 2022-07-15 |  | 2022-07-22 | 2022-07-29 | 2022-08-06 | 60 | GF | 1733816.7 | 1733816.7 |  | 1707642.55 | 1707642.55 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-005-119 | 13) Construction of 4-Storey, 8-Rooms Ynares School Building at Teresa Elementary School, Brgy. Dalig, Teresa, Rizal |  |  | Public Bidding | 2022-06-03 | 7-13 Jun. 22 | 2022-06-14 |  | 2022-06-28 | 2022-07-04 | 2022-07-15 |  | 2022-07-22 | 2022-07-29 | 2022-08-06 |  | TF | 30244222.46 |  | 30244222.46 | 30145117.85 |  | 30145117.85 | Engr. Nelson Pajarillo Simon King
Total Alloted Budget of On-going Procurement Activities
| Prepared by: | [8 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
|  | MA. TERESA E. LASQUETY | [12 empty] | Engr. LUISITO G. MUNSOD | [8 empty] | HON. NINA RICCI A. YNARES
|  | (Sgd)Head - BAC Secretariat | [12 empty] | (Sgd) BAC Chairperson | [8 empty] | (Sgd) Governor