## PMR 2022- AS OF DEC 2022
PROVINCE OF RIZAL PROCUREMENT MONITORING REPORT as of DECEMBER 2022
Code | Procurement | PMO/ | Is this | Mode of | Actual Procurement Activity | [11 empty] | Source | ABC (Php) |  |  | Contract Cost (Php) |  |  | List of | Date of Receipt of Invitation | [5 empty] | Remarks
(UACS/PAP) | Program/Project | End-User | Early Procurement? | Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | BAC Res Date Recom Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | of Funds | Total | MOOE | CO | Total | MOOE | CO | Invited Observers | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (if applicable) | (Explaining changes from the APP)
2022-08-01
8000-000-1-1-51-001-001-003 | 1) Extension of Generator Roofing Near PGSO Office at Rizal Provincial Government, Brgy. San Roque, Antipolo City | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 60 | GF | 793589.08 |  | 793589.08 | 781544.66 |  | 781544.66 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
8000-000-1-1-51-001-001-004 | 2) Repair of Ynares Event Center (Ynares Compound), Brgy. San Roque, Antipolo City | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 68 | GF | 2598261.13 | 2598261.13 |  | 2580115.87 | 2580115.87 |  | Engr. David Disimulacion Jr. Simon King | 2022-07-12
3000-300-1-2-11-57-005-075 | 3) Construction of 2-Storey Ynares Multi-Purpose Building at Grand Valley Subd., Phase 2, Brgy. Mahabang Parang, Angono, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-01-28 | 2022-01-28 | 2022-08-19 | 2022-09-09 | 156 | GF | 4475760.85 |  | 4475760.85 | 4440741.83 |  | 4440741.83 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
8000-000-1-1-51-001-002-131 | 4) Asphalt Overlaying with Drainage Canal of Various Road at Brgy. San Jose, Baras, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 100 | GF | 4032506.38 | 4032506.38 |  | 3995452.58 | 3995452.58 |  | Engr. David Disimulacion Jr. Simon King | 2022-07-12
3000-000-1-2-11-399-005-120 | 5) Construction of Area Lightings at School Compound at Painaan Elem. School, Brgy. Pinugay, Baras, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 52 | GF | 2023097.43 |  | 2023097.43 | 1993898.19 |  | 1993898.19 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
8000-000-1-1-51-001-002-141 | 6) Concreting with Drainage Canal at E. Rodriguez St., Brgy. Buhangin, Binangonan, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 100 | GF | 2036166.26 |  | 2036166.26 | 2005766 |  | 2005766 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
3000-300-1-2-11-511-005-082 | 7) Construction of Perimeter Fence at RHU3, Brgy. Lunsad, Binangonan, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  |  | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 80 | GF | 1332375.93 |  | 1332375.93 | 1311947.69 |  | 1311947.69 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
8000-000-1-1-51-001-002-132 8000-000-1-1-51-001-002-137 8000-000-1-1-51-001-002-138 | 8) Asphalt Overlaying at Brgy. Layunan, Binangonan, Rizal a) Asphalt Overlaying of M.H. Del Pilar St. (portion), Brgy. Layunan b) Asphalt Overlaying of J. Luna St., Brgy. Layunan c) Asphalt Overlaying of Osmeña St., Brgy. Layunan | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 80 | GF | 1,441,316.74 871,648.18 739,305.48 30,052,270.40 | 1,441,316.74 871,648.18 739,305.48 30,052,270.40 |  | 1,415,381.44 868,622.79 736,213.16 | 1,415,381.44 868,622.79 736,213.16 |  | Engr. David Disimulacion Jr. Simon King | 2022-07-12
3000-300-1-2-11-511-005-087 3000-300-1-2-11-511-005-089 | 9) Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. San Isidro, Cainta, Rizal a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Vista Verde Executive Vill., Phase 2, Brgy. San Isidro b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Vista Verde Phase 5, Brgy. San Isidro | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 90 | GF | 995,731.90 1,1511,333.82 2,150,065.72 | 995,731.90 1,1511,333.82 2,150,065.72 |  | 985,614.66 1,735,404.45 | 985,614.66 1,735,404.45 |  | Engr. David Disimulacion Jr. Simon King | 2022-07-12
3000-300-1-2-11-511-005-088 3000-300-1-2-11-511-005-091 | 10) Repair/Improvement of Ynares Multi-Purpose Covered Court and Ynares Multi-Purpose Building at Brgy. San Isidro, Cainta, Rizal a) Repair of Ynares Multi-Purpose Covered Court at Vista Verde Executive Vill. Phase 3, Brgy. San Isidro b) Improvement of 2-Storey Ynares Multi-Purpose Building at Vista Verde Executive Village Phase 4, Brgy. San Isidro | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 52 | GF | 892,819.49 209,389.95 1,102,209.44 | 892819.49 | 209389.95 | 873,051.28 207,155.39 | 873051.28 | 207155.39 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
3000-300-1-2-11-511-005-092 | 11) Improvement of Ynares Multi-Purpose Covered Court at Brgy. Nagsulo, Cardona, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 0 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 80 | GF | 247272958 |  | 247272958 | 2447699.2 |  | 2447699.2 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
8000-000-1-1-51-001-002-149 | 12) Construction of Stone Masonry for Slope Protection of Creek (Boundary of Brgy. Bayugo & Brgy. 3rd District), Brgy. 3rd District, Jalajala, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 60 | GF | 803185.33 |  | 803185.33 | 785911.73 |  | 785911.73 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
8000-000-1-1-51-001-002-148 | 13) Asphalt Overlaying of Road at Sitio Masikap, Brgy. 3rd District, Jalajala, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 60 | GF | 2549204.75 | 2549204.75 |  | 2516223.74 | 2516223.74 |  | Engr. David Disimulacion Jr. Simon King | 2022-07-12
3000-300-1-2-11-511-005-096 | 14) Improvement of 2-Storey Ynares Multi-Purpose Building, Brgy. Maybancal, Morong, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 75 | GF | 1221923.32 |  | 1221923.32 | 1197912.07 |  | 1197912.07 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
8000-000-1-1-51-001-002-155 | 15) Construction of Drainage Canal with Steel Grating at Sitio Bulacan II, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 0 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 140 | GF | 5018623.94 |  | 5018623.94 | 4977091.65 |  | 4977091.65 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
8000-000-1-1-51-001-002-157 | 16) Construction of Sone Masonry for Slope Protection (portion) at Quisao River, Brgy. Quisao, Pililla, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 180 | GF | 10505330.28 |  | 10505330.28 | 10346397.24 |  | 10346397.24 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
8000-000-1-1-51-001-002-156 | 17) Construction of Stone Masonry for Slope Protection (portion) at Barak Creek, Brgy. Quisao, Pililla, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 200 | GF | 14878713.29 |  | 14878713.29 | 14680138.62 |  | 14680138.62 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
3000-300-1-2-11-511-005-107 | 18) Improvement of Ynares Multi-Purpose Covered Court at LA MAR Village, Brgy. Gutinang Bayan 2, San Mateo, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 69 | GF | 1488532.77 |  | 1488532.77 | 1460419.34 |  | 1460419.34 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
3000-300-1-2-11-511-005-106 | 19) Improvement of Ynares Multi-Purpose Covered Court at Portobello Homes, Brgy. Guitnang Bayan 1, San Mateo, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 0 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 60 | GF | 1337945.95 |  | 1337945.95 | 1307879.34 |  | 1307879.34 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
3000-000-1-2-11-399-005-148 | 20) Construction of Link Bridge at Manuel L. Santos Mem. NationalHigh School, Brgy. San Juan, Taytay, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 90 | GF | 2498672.65 |  | 2498672.65 | 2466534.59 |  | 2466534.59 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
3000-300-1-2-11-511-005-110 | 21) Concreting of Road and Installation of Electrical Lighting System atBrgy. Prinza, Teresa, Rizal a) Concreting of Road from F. Gonzales St., to Carissa Home East 1 (CHE-1) Extn., Brgy. Prinza b) Installation of Electrical Lighting System of 10 x 30m Ynares Multi-Purpose Covered Court at Carissa Homes East 1, Brgy. Prinza | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 60 | GF | 749,616.75 451,004.56 1,200,621.31 |  | 749,616.75 451,004.56 1,200,621.31 | 734,997.60 439,588.86 |  | 734,997.60 439,588.86 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
3000-400-1-1-11-006-007 3000-300-1-2-11-511-005-072 | 22) Repainting of Inuman Health Station Bldg., at Brgy. Inarawan and Repair of Ynares Multi-Purpose Covered Court at Brgy. San Luis, Antipolo City a) Repainting of 2-Storey Inuman Health Station Bldg., at Sitio Inuman, Brgy. Inarawan b) Repair of Electrical Lighting System of 17 x 30m Ynares Multi-Purpose Covered Court at Bermuda Heights Subd., Sitio Bermuda, Brgy. San Luis | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 60 | GF | 291,308.04 388,856.99 680,165.03 | 291,308.04 388,856.99 680,165.03 |  | 286,187.40 286,187.40 | 286,187.40 286,187.40 |  | Engr. David Disimulacion Jr. Simon King | 2022-07-12
8000-000-1-1-51-001-002-126 | 23) Asphalt Overlaying of Various Road at Brgy. Poblacion Ibaba, Angono, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 0 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 60 | GF | 3100089.22 | 3100089.22 |  | 3065016.89 | 3065016.89 |  | Engr. David Disimulacion Jr. Simon King | 2022-07-12
8000-000-1-1-51-001-001-005 3000-300-1-2-11-511-005-076 | 24) Construction of Storage for Disaster Equipment and Improvement of Ynares Multi-Purpose Building (Brgy. Hall) at Brgy. San Jose, Baras, Rizal a) Construction of Storage for Disaster Equipment at Brgy. San Jose b) Improvement of 2-Storey Ynares Multi-Purpose Building (Brgy. Hall) at Brgy. San Jose | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 60 | GF | 264,325.90 566,659.82 830,985.72 |  | 264,325.90 566,659.82 830,985.72 | 253,122.20 562,755.02 |  | 253,122.20 562,755.02 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
3000-300-1-2-11-511-005-077 | 25) Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Kalinawan, Binangonan, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 70 | GF | 1799685.85 | 1799685.85 |  | 1776091.05 | 1776091.05 |  | Engr. David Disimulacion Jr. Simon King | 2022-07-12
3000-300-1-2-11-511-005-086 | 26) Imrprovement of Ynares Multi-Purpose Covered Court at Cainta Greenpark Village, Zone 6, Brgy. San Isidro, Cainta, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 45 | GF | 1299005.6 |  | 1299005.6 | 1275019.58 |  | 1275019.58 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
3000-300-1-2-11-511-005-094 | 27) Construction of Perimeter Fence at Central Fire Station, Brgy. San Juan, Morong, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 0 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 86 | GF | 2009122.45 |  | 2009122.45 | 1979103.31 |  | 1979103.31 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
8000-000-1-1-51-001-002-157 | 28) Concreting of Farm to Market Road at T. Daria St. Extn., Sitio Tanza, Brgy. Niogan, Pililla, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 72 | GF | 1034334.66 |  | 1034334.66 | 1014072.32 |  | 1014072.32 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
8000-000-1-1-51-001-002-158 | 29) Concreting of Road at Yokinco Cmpd., Brgy. Bagumbayan, Pililla, Rizal | PEO |  | PUBLIC BIDDING | 2022-07-08 | 12-18-Jul-22 | 2022-07-19 |  | 2022-08-01 | 2022-08-05 | 2022-08-15 | 2022-08-23 | 2022-08-23 | 2022-08-19 | 2022-09-09 | 90 | GF | 1970641.86 |  | 1970641.86 | 1941590.58 |  | 1941590.58 | Engr. David Disimulacion Jr. Simon King | 2022-07-12
2022-08-09
8000-000-1-1-51-001-002-128 8000-000-1-1-51-001-002-129 8000-000-1-1-51-001-002-130 | 1) Asphalt Overlaying/Concrete Reblocking at Brgy. San Pedro, Angono, Rizal a.) Asphalt Overlaying / Concrete Reblocking (portion) of Christian Dior St., Bloomingdale Subd., Brgy. San Pedro b.) Asphalt Overlaying/ Concrete Reblocking (portion) of Tiffany St., Bloomingdale Subd., Brgy. San Pedro c.) Asphalt Overlaying/ Concrete Reblocking (portion) of Saks St., Bloomingdale Subd., Brgy. San Pedro | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 100 | GF | 3,291,276.02 2,001,982.90 2.613,108.90 7,906,367.82 | 3,291,276.02 2,001,982.90 2.613,108.90 7,906,367.82 |  | 3,252,844.21 1,947,640.02 2.600,622.99 | 3,252,844.21 1,947,640.02 2.600,622.99 |  | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-300-1-2-11-511-015-073 3000-300-1-2-11-511-005-085 | 2) Improvement of Ynares Multi-Purpose Building at Brgy. San Isidro, Angono, Rizal and Brgy. Bangad, Binangonan, Rizal a.) Improvement of 2-Storey Ynares Multi-Purpose Building Constellation Homes Subd., Brgy. San Isidro, Angono, Rizal b.) Improvement of 2-Storey Ynares Multi-Purpose Building,Brgy. Bangad, Binangonan, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 68 | GF | 205,003.04 791,601.73 996,604.77 |  | 205,003.04 791,601.73 996,604.77 | 201,008.80 774,596.49 |  | 201,008.80 774,596.49 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-300-1-2-11-511-005-074 | 3) Improvement of 2-Storey Ynares Multi-Purpose Building (Brgy. Hall) Brgy. San Vicente, Angono, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 70 | GF | 1064618.01 |  | 1064618.01 | 1040694.28 |  | 1040694.28 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-300-1-2-11-399-005-121 | 4) Installation of Electrical Lightings System of 10x24m Ynares Multi-Purpose Covered Court at Baras Senior High School, Sitio Rumaguit, Brgy. San Juan, Baras, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 16 | GF | 372758.46 | 372758.46 |  | 357695.14 |  | 357695.14 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-300-1-2-11-399-005-125 | 5) Improvement of School Drainage System at Lunsad Elem. School, Brgy. Lunsad, Binangonan, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 78 | GF | 1258945.7 |  | 1258945.7 | 1235934.37 |  | 1235934.37 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-300-1-2-11-511-005-078 | 6) Repair /Repainting of Ynares Multi-Purpose Covered Court at Brgy. Bangad, Binangonan, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 80 | GF | 1914461.08 | 1914461.08 |  | 1887420.8 |  |  | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-300-1-2-11-511-005-079 | 7) Improvement of Ynares Multi-Purpose Covered Court at Brgy. Kaytome, Binangonan, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 60 | GF | 1040846.41 |  | 1040846.41 | 1015785.5 |  | 1015785.5 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-300-1-2-11-511-081 | 8) Improvement of 2-Storey Ynares Multi-Purpose Building (Brgy. Hall) at Brgy. Kaytome, Binangonan, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 60 | GF | 1428950.21 |  | 1428950.21 | 1406990.01 |  | 1406990.01 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-000-1-2-11-399-005-127 3000-300-1-2-11-511-005-080 | 9) Construction of School Signage and Improvement of Multi-Purpose Building at Brgy. Sapang and Brgy. Mambog, Binangonan, Rizal a.) Construction of School Signage at Sapang Elem. School, Brgy. Sapang b.) Improvement of Multi-Purpose Building (Brgy. Hall Annex) at Sampaguita St., Brgy. Mambog | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 60 | GF | 353,773.80 473,543.23 827,317.03 |  | 353,773.80 473,543.23 827,317.03 | 346,731.08 463,583.13 |  | 346,731.08 463,583.13 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-300-1-2-11-511-005-083 | 10) Improvement of 1-Storey Multi-Purpose Building (Daycare Center) at Ynares Village, Brgy. Pantok, Binangonan, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 60 | GF | 1002856.18 |  | 1002856.18 | 978817.12 |  | 978817.12 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-300-1-2-11-511-005-084 | 11) Construction of Perimeter Fence at Children's Park at San Clemente Village 1 & 2, Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 60 | GF | 1262055.69 |  | 1262055.69 | 1235009.34 |  | 1235009.34 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
8000-000-1-1-51-001-002-142 | 12) Concreting with Drainage Canal of Road at Purok 2,Brgy. Kinaboogan, Binangonan, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 100 | GF | 1773952.76 |  | 1773952.76 | 1734913.26 |  | 1734913.26 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-000-1-2-11-399-005-131 | 13) Construction of Drainage Canal at Francisco P. Felix Mem. National High School Karangalan Annex, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 60 | GF | 507584.21 |  | 507584.21 | 492679.75 |  | 492679.75 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
8000-000-1-1-51-001-002-144 | 14) Construction of Drainage Canal (portion) of R. Valle St., Brgy. San Roque, Cainta, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 90 | GF | 1486264.47 |  | 1486264.47 | 1457269.29 |  | 1457269.29 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-300-1-2-11-511-005-090 | 15) Construction of 2-Storey Ynares Multi-Purpose Building (Senior Citizens Office) at Adelina Homes, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 126 | GF | 3564912.02 |  | 3564912.02 | 3524926.67 |  | 3524926.67 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-300-1-2-11-511-005-095 | 16) Repair / Repainting of 1-Storey Ynares Multi-Purpose Building (IMAP Bldg.) at Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 44 | GF | 711273.37 | 711273.37 |  | 693209.3 | 693209.3 |  | Engr. David Disimulacion Jr. Simon King | 2022-07-21
8000-000-1-1-51-001-002-150 8000-000-1-1-51-001-002-151 8000-000-1-1-51-001-002-152 8000-000-1-1-51-001-002-153 8000-000-1-1-51-001-002-154 | 17) Construction of Roadway Lightings at Brgy. San Guillermo, Morong, Rizal a.) Construction of Roadway Lightings at Francisco St., Sitio Estacion at Brgy. San Guillermo b.) Construction of Roadway Lightings at San Luis St., Sitio Dulo at Brgy. San Guillermo c.) Construction of Roadway Lightings at Bernardino St., Sitio Tabing-Ilog at Brgy. San Guillermo d.) Construction of Roadway Lightings at Lambingan St., Sitio Gitna atBrgy. San Guillermo e.) Construction of Roadway Lightings at Tambongco St., Sitio Tambongco at Brgy. San Guillermo | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 60 | GF | 2,059,040.08 1,867,942.03 2,795,743.50 3,116,163.01 1,086,084.83 10,924,973.45 |  | 2,059,040.08 1,867,942.03 2,795,743.50 3,116,163.01 1,086,084.83 10,924,973.45 | 2,031,744.44 1,841,803.70 2,755,981.74 3,057,826.93 1,072,345.58 |  | 2,031,744.44 1,841,803.70 2,755,981.74 3,057,826.93 1,072,345.58 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-000-1-2-11-399-005-137 | 18) Improvement of Ynares Multi-Purpose Covered Court at URS-Pililla, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 100 | GF | 2449932.74 |  | 2449932.74 | 2425093.21 |  | 2425093.21 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-300-1-2-11-511-005-098 | 19) Repair/Repainting of Ynares Multi-Purpose Building (Day Care Center) Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 65 | GF | 541852.24 | 541852.24 |  | 525818.65 | 525818.65 |  | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-300-1-2-11-511-005-099 | 20) Repair / Repainting of 2-Storey Ynares Multi-Purpose Building at A. Luna St., Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 50 | GF | 786387.86 | 786387.86 |  | 767354.27 | 767354.27 |  | Engr. David Disimulacion Jr. Simon King | 2022-07-21
3000-300-1-2-11-511-005-108 | 21) Repair / Repainting of Ynares Multi-Purpose Covered Court at New San Mateo Subd., Phase 3 & 4, Brgy. Guitnang Bayan 1, San Mateo, Rizal | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 60 | GF | 1070783.86 | 1070783.86 |  | 1046770.5 | 1046770.5 |  | Engr. David Disimulacion Jr. Simon King | 2022-07-21
8000-000-1-1-51-001-002-181 8000-000-1-1-51-001-002-182 | 22) Construction of Roadway Lightings at Brgy. Dalig andBrgy. Dulumbayan, Teresa, Rizal a.) Construction of Roadway Lightings at MRF-Sitio Korokan Rd. Brgy. Dalig b.) Construction of Roadway Lightings at Farm to Market Road, | PEO |  | Public Bidding | 2022-07-15 | 21-27 Jul-22 | 2022-07-28 |  | 2022-08-09 | 2022-08-15 | 2022-08-25 | 2022-08-31 | 2022-08-31 | 2022-09-09 | 2022-09-13 | 68 | GF | 3,162,375.08 1,716,834.94 4,870,210.02 |  | 3,162,375.08 1,716,834.94 4,870,210.02 | 3,135,690.12 1,698,427.61 |  | 3,135,690.12 1,698,427.61 | Engr. David Disimulacion Jr. Simon King | 2022-07-21
2022-08-22
3000-000-1-2-11-399-005-122 3000-000-1-2-11-399-005-123 | 1) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court at Brgy. Pantok, Binangonan, Rizal a.) Repair / Repainting of Ynares Multi-Purpose Covered Court at Doña Susana Madrigal Elem. School, Brgy. Pantok b.) Improvement of Ynares Multi-Purpose Covered Court at Doña Susana Madrigal Elem. School, Brgy. Pantok | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 80 | GF | 649,968.12 1,199,980.62 1,849,948.74 | 649968.12 | 1199980.62 | 625,250.10 1,183,651.43 | 625250.1 | 1183651.43 | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-128 3000-000-1-2-11-399-005-129 | 2) Repair/Repainting of Ynares School Bldg. and Ynares Stage at Brgy. San Juan, Cainta, Rizal a.) Repair / Repainting of Ynares School Bldg. at Jansenville Elem. School, Brgy. San Juan b.) Repair / Repainting of Ynares Stage at Jansenville Elem. School, Brgy. San Juan | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 90 | SEF | 2.045,776.87 176,928.89 2,222,705.75 | 2.045,776.87 176,928.89 2,222,705.75 |  | 2.016,474.66 174,224.28 | 2.016,474.66 174,224.28 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-130 | 3) Repair / Repainting of Ynares School Bldg. at Arinda Elem. School, Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 90 | SEF | 3013251.93 | 3013251.93 |  | 2979200.17 | 2979200.17 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-125 | 4) Repair / Repainting of Ynares Multi-Purpose Covered Court at Bombong Elem. School, Brgy. Bombong, Binangonan, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 60 | SEF | 874316.66 | 874316.66 |  | 861309.02 | 861309.02 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-126 8000-000-1-1-51-001-002-143 | 5) Installation of Safety Grills and Asphalt Overlaying at Brgy. Lunsad, Binangonan, Rizal a.) Installation of Safety Grills (Enclosure on 4-Storey, 8 Rooms, (DPWH Bldg.) at Lunsad Elem. School, Brgy. Lunsad b.) Asphalt Overlaying of Milagros St., Brgy. Lunsad | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 80 | SEF GF | 699,906.37 597,399.91 1,297,306.28 | 699,906.37 597,399.91 1,297,306.28 |  | 686,966.47 583,331.22 | 686,966.47 583,331.22 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-01
8000-000-1-1-51-001-002-135 | 6) Construction of Stone Masonry for Slope Protection (portion) at Gupiing Creek, Brgy. Lunsad, Binangonan, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 80 | SEF | 6298714.44 |  | 6298714.44 | 6233341.11 |  | 6233341.11 | Engr. David Disimulacion Jr. Simon King | 2022-08-01
8000-000-1-1-51-001-002-136 | 7) Construction of Drainage Canal at Lower J. Sumulong Road, Brgy. Lunsad, Binangonan, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 60 | SEF | 1149359.27 |  | 1149359.27 | 1128287.28 |  | 1128287.28 | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-132 | 8) Improvement of Ynares Multi-Purpose Covered Court at Tadlak Elem. School, Brgy. Looc, Cardona, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 60 | SEF | 1036511.08 |  | 1036511.08 | 1014495.6 |  | 1014495.6 | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-133 | 9) Construction of Covered Pathwalk at Patunhay-Calahan Elem. School, Brgy. Calahan, Cardona, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 75 | SEF | 1873603.97 |  | 1873603.97 | 1841600.16 |  | 1841600.16 | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-300-1-2-511-005-093 3000-000-1-2-11-399-005-136 | 10) Repair/Repainting of Ynares Multi-Purpose Building and Ynares School Bldg. at Brgy. Palaypalay, Jalajala, Rizal and Brgy. Quisao, Pililla, Rizal a.) Repair / Repainting of 2-Storey Ynares Multi-Purpose Building (Brgy. Hall) at Brgy. Palaypalay b.) Repair of Ynares School Bldg. at Quisao Elem. School, Brgy. Quisao | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 60 | GF SEF | 619,816.99 359,296.61 979,113.60 | 619,816.99 359,296.61 979,113.60 |  | 611,735.19 349,353.46 | 611,735.19 349,353.46 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-134 | 11) Repair / Repainting of Ynares School Bldg. at Calero-Lanang Elem. School, Brgy. CCL, Morong, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 92 | SEF | 2354511.28 | 2354511.28 |  | 2323449.54 | 2323449.54 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-135 | 12) Construction of Perimeter Fence & Gate at Lagundi CCL National High School (New Campus), Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 120 | SEF | 4399554.04 |  | 4399554.04 | 4359537.34 |  | 4359537.34 | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-138 | 13) Construction of Perimeter Fence at Hulo National High School, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 116 | SEF | 5236134.99 |  | 5236134.99 | 5187087.33 |  | 5187087.33 | Engr. David Disimulacion Jr. Simon King | 2022-08-01
8000-000-1-1-51-001-002-160 | 14) Asphalt Overlaying / Concrete Reblocking (portion) of Balite Feeder Road, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 100 | GF | 2245670.58 | 2245670.58 |  | 2226956.56 | 2226956.56 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-01
8000-000-1-1-51-001-002-161 | 15) Asphalt Overlaying of Road at Sitio Bulacan 1, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 60 | GF | 1299532.76 | 1299532.76 |  | 1274530.66 | 1274530.66 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-01
8000-000-1-1-51-001-002-163 8000-000-1-1-51-001-002-164 8000-000-1-1-51-001-002-165 | 16) Asphalt Overlaying at Brgy. Niogan, Pililla, Rizal a.) Asphalt Overlaying (portion) at T. Daria St., Brgy. Niogan b.) Asphalt Overlaying at Amican St., Brgy. Niogan c.) Asphalt Overlaying at Villarojas St., Brgy. Niogan | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 60 | GF | 2,999,571.55 1,074,070,65 992,331.29 5,065,973.49 | 2,999,571.55 1,074,070,65 992,331.29 5,065,973.49 |  | 2,967,420.82 1,059,515,94 979,937.96 | 2,967,420.82 1,059,515,94 979,937.96 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-01
8000-000-1-1-51-001-002-167 8000-000-1-1-51-001-002-168 | 17) Asphalt Overlaying at Brgy. Niogan, Pililla, Rizal a.) Asphalt Overlaying of Villaran St., Brgy. Niogan b.) Asphalt Overlaying of Judea St., Brgy. Niogan | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 60 | GF | 972,450,64 4,617,220.83 5,589,671.47 | 972,450,64 4,617,220.83 5,589,671.47 |  | 961,168,42 4,566,431.33 | 961,168,42 4,566,431.33 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-01
8000-000-1-1-51-001-002-166 | 18) Asphalt Overlaying/ Concreting Reblocking (portion) of Feliciano St., Brgy. Niogan, Pililla, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 80 | GF | 1426377.69 | 1426377.69 |  | 1397311.59 | 1397311.59 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-01
8000-000-1-1-51-001-002-169 | 19) Asphalt Overlaying of G. Cruz St., Brgy. Niogan, Pililla, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 60 | GF | 681076.83 | 681076.83 |  | 667021.78 | 667021.78 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-139 3000-000-1-2-11-399-005-140 | 20) Improvement of Ynares Multi-Purpose Covered Court and Construction of Drainage Canal at Brgy. Maly and Brgy. Silangan, San Mateo, Rizal a.) Improvement of Ynares Multi-Purpose Covered Court at Maly Elem. School, Brgy. Maly b.) Construction of Drainage Canal at Silangan National High School, Brgy. Silangan | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 75 | GF | 198,147.50 468,488.39 666,635.89 |  | 198,147.50 468,488.39 666,635.89 | 185,647.08 464,961.93 |  | 185,647.08 464,961.93 | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-141 | 21) Repair / Repainting of Ynares School Building at Simeon Bendaña Elem. School Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 120 | SEF | 4999120.7 | 4999120.7 |  | 4951098.72 |  | 4951098.72 | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-142 | 22) Construction of Covered Pathwalk at Marciana P. Catolos National High School, Brgy. Kaybuto, Tanay, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 48 | SEF | 397152 |  | 397152 | 385065.64 |  | 385065.64 | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-143 | 23) Construction of 8 x 24m Ynares Multi-Purpose Covered Court at Tanay Senior High School, Brgy. Tandang Kutyo, Tanay, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 124 | SEF | 3888281.46 |  | 3888281.46 | 3853182.61 |  | 3853182.61 | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-300-1-2-11-511-005-109 3000-000-1-2-11-399-005-144 | 24) Provision of Movable Bleachers at Ynares Multi-Purpose Covered Court and Improvement of Fence at Brgy. Daraitan, Tanay, Rizal a.) Provision of Movable Bleachers at Ynares Multi-Purpose Covered Court at Brgy. Daraitan b.) Improvement of Fence at Daraetan National High School, Brgy. Daraitan | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 90 | GF SEF | 794,442.87 896,461.21 1,690,904.08 |  | 794,442.87 896,461.21 1,690,904.08 | 787,354.42 536,656.73 |  | 787,354.42 536,656.73 | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-145 3000-000-1-2-11-399-005-146 | 25) Improvement/Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Plaza Aldea, Tanay, Rizal a.) Improvement of Ynares Multi-Purpose Covered Court at Tanay East Integrated National High School Brgy. Plaza Aldea b.) Repair / Repainting of Ynares Multi-Purpose Covered Court at Tanay East Integrated National High School, Brgy. Plaza Aldea | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 72 | SEF SEF | 299,960.33 545,072.34 845,032.67 | 545072.34 | 299960.33 | 293,355.12 536,656.73 | 536656.73 | 293355.12 | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-149 3000-000-1-2-11-399-005-150 | 26) Repair/Repainting of Perimeter Fence and Stage at Brgy. Dalig, Teresa, Rizal a.) Repair / Repainting of Perimeter Fence at Pantay Integrated High School, Brgy. Dalig b.) Repair / Repainting of Stage at Pantay Integrated High School, Brgy. Dalig | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 92 | SEF SEF | 499,814.26 309,038.12 808,852.38 | 499,814.26 309,038.12 808,852.38 |  | 491,725.06 299,034.77 | 491,725.06 299,034.77 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-01
3000-000-1-2-11-399-005-151 | 27) Improvement of Ynares Multi-Purpose Covered Court at Abuyod National High School, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 1-7 Aug-22 | 2022-08-08 |  | 2022-08-22 | 2022-08-26 | 2022-09-06 | 2022-09-12 | 2022-09-12 | 2022-09-19 | 2022-09-27 | 80 | SEF | 2299961.24 |  | 2299961.24 | 2270856.97 |  | 2270856.97 | Engr. David Disimulacion Jr. Simon King | 2022-08-01
2022-09-05
8000-000-1-1-51-001-001-006 | 1) Repair/Repainting of Ynares View Deck and Conference Room at Brgy. Bagong Nayon I, Antipolo, City | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 129 | GF | 1823197.35 | 1823197.35 |  | 1802050.14 | 1802050.14 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-400-1-1-11-006-008 | 2) Improvement of Day Care Center at Sitio Lipana Pandayan Upper, Brgy. Inarawan, Antipolo, City | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 57 | GF | 514909.99 | 514909.99 |  | 502893.71 | 502893.71 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-114 3000-600-1-2-11-511-004-113 | 3) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court and Ynares Multi-Purpose Bldg. at Brgy. Mahabang Parang, Angono, Rizal a.) Repair / Repainting of Ynares Multi-Purpose Covered Court at Grandvalley Subd., Phase 2, Brgy. Mahabang Parang b.) Improvement of 2 Storey Ynares Multi-Purpose Bldg. at Grandvalley Subd., Phase 3, Brgy. Mahabang Parang | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 80 | GF | 553,439.49 352,316.14 905,755.63 |  | 553,439.49 352,316.14 905,755.63 | 538,933.76 349,820.33 |  | 538,933.76 349,820.33 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-115 | 4) Improvement of Ynares Multi-Purpose Covered Court at Grandvalley Subd., Phase 2, Brgy. Mahabang Parang, Angono, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 90 | GF | 3599870.55 |  | 3599870.55 | 3568817.32 |  | 3568817.32 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
8000-000-1-1-51-001-002-184 | 5) Asphalt Overlaying of Gimbels Street, Bloomingdale Subd., Brgy. San Pedro, Angono, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 60 | GF | 447376.25 | 447376.25 |  | 436370.1 | 436370.1 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-15
8000-000-1-1-51-001-001-007 | 6) Improvement of Office & Comfort Room of Rizal Provincial Mobile Force Company, Third Maneuver Platoon at Brgy. San Juan, Baras, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 58 | GF | 1035483.4 |  | 1035483.4 | 1012408.85 |  | 1012408.85 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-119 | 7) Repair/Repainting of Ynares Multi-Purpose Covered Court and Stage at Brgy. Palangoy, Binangonan, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 61 | GF | 1425062.37 | 1425062.37 |  | 1400051.82 | 1400051.82 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-000-1-2-11-399-005-153 3000-000-1-2-1-399-005-155 | 8) Construction of Materials Recovery Facility/School Signage at Brgy. Palangoy and Brgy. Lunsad, Binangonan, Rizal a.) Construction of Materials Recovery facility at Vicente Madrigal Integrated School Brgy. Palangoy b.) Construction of School Signage at Lunsad Elem. School, Brgy. Lunsad | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 80 | GF | 563,889.52 276,221.74 840,111.26 |  | 563,889.52 276,221.74 840,111.26 | 553,584.84 269,515.25 |  | 553,584.84 269,515.25 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
8000-000-1-1-51-001-002-198 | 9) Improvement of Road at Durian St., Blooming Breeze Subd., (formerly Vocalan Cmpd.) Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 100 | GF | 3525317.22 |  | 3525317.22 | 3494357.32 |  | 3494357.32 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-122 | 10) Construction of 1-Storey Ynares Multi-Purpose Building(Day Care Center) at San Clemente Village 1 & 2, Brgy. Pag-Asa,Binangonan, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 86 | GF | 2822737.39 |  | 2822737.39 | 2792698.28 |  | 2792698.28 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-123 | 11) Repair/Repainting of Ynares Multi-Purpose Covered Court at Graceville Subd., Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 60 | GF | 1357824.95 | 1357824.95 |  | 1329807.98 | 1329807.98 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-124 | 12) Improvement of Ynares Multi-Purpose Covered Court at Graceville Subd., Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 75 | GF | 2174251.14 |  | 2174251.14 | 2148029.34 |  | 2148029.34 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-124 | 13) Construction of Ynares Stage at Graceville Subd., Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 72 | GF | 1549584.77 |  | 1549584.77 | 1520516.52 |  | 1520516.52 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-129 | 14) Improvement of Ynares Multi-Purpose Covered Court at Vista Verde Phase 1, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 60 | GF | 1610916.06 |  | 1610916.06 | 1584901.28 |  | 1584901.28 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-128 | 15) Repair/Repainting of Ynares Multi-Purpose Covered Court at Vista Verde Phase 1, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 60 | GF | 673290.05 | 673290.05 |  | 657179.35 | 657179.35 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-130 | 16) Improvement of Ynares Multi-Purpose Covered Court at Mercedes Executive Village Phase 2, Brgy. San Andres, Cainta, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 95 | GF | 1947146.31 |  | 1947146.31 | 1917049.21 |  | 1917049.21 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-131 | 17) Improvement of Ynares Multi-Purpose Covered Court at Greenwoods Executive Village, Area 8 Phase 6, Brgy. San Andres, Cainta, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 81 | GF | 2099998.77 |  | 2099998.77 | 2066957.62 |  | 2066957.62 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-133 | 18) Repair/Repainting of Ynares Multi-Purpose Covered Court at Gruar Phase 1, Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 60 | GF | 1995570.24 | 1995570.24 |  | 1969487.29 | 1969487.29 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-15
8000-000-1-1-51-001-002-205 | 19) Improvement of Wharf at Brgy. Sampad, Cardona, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 80 | GF | 1345618.44 |  | 1345618.44 | 1320590.64 |  | 1320590.64 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
8000-000-1-1-51-001-002-206 | 20) Concreting of Road at Purok 3, Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 60 | GF | 611698.48 |  | 611698.48 | 597409.67 |  | 597409.67 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-139 | 21) Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Special District, Jalajala, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 96 | GF | 1705431.41 | 1705431.41 |  | 1677479.36 | 1677479.36 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-140 | 22) Improvement of Ynares Multi-Purpose Covered Court at Sitio Tabing-Ilog, Brgy. San Guillermo, Morong, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 90 | GF | 2406800.54 |  | 2406800.54 | 2377786.38 |  | 2377786.38 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-141 3000-600-1-2-11-511-004-142 | 23) Repair/Repainting of Ynares Multi-Purpose Covered Court and Installation of Electronic Scoreboard at Brgy. San Guillermo, Morong, Rizal a.) Repair / Repainting of Ynares Multi-Purpose Covered Court and Stage at Sitio Tabing Ilog Brgy. San Guillermo b.) Installation of Electronic Scoreboard at Ynares Multi-Purpose Covered Court at Sitio Agas-As, Brgy. San Guillermo | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 60 | GF | 1,118,497.08 187,350.18 1,305,847.26 | 1,118,497.08 187,350.18 1,305,847.26 |  | 1,094,706.29 186,103.30 | 1,094,706.29 186,103.30 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-15
8000-000-1-1-51-001-002-210 | 24) Asphalt Overlaying of Pendon St., Brgy. Niogan, Pililla, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 60 | GF | 425657.07 | 425657.07 |  | 413609.68 | 413609.68 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-15
8000-000-1-1-51-001-002-211 | 25) Concreting (portion) of Calasiao Feeder Road at Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 80 | GF | 2039877.5 |  | 2039877.5 | 2013867.18 |  | 2013867.18 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-143 | 26) Construction of 2-Seater Comfort Room at Eastwood Residences, Phase 6A, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 49 | GF | 483931.94 |  | 483931.94 | 473927.39 |  | 473927.39 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-144 | 27) Construction of Perimeter Fence at Eastwood Residences Phase 6A, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 62 | GF | 1171754.34 |  | 1171754.34 | 1146708.28 |  | 1146708.28 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-145 | 28) Construction of 2-Storey Ynares Multi-Purpose Building (Makabagong Kababaihan ng Rodriguez Rizal - MKRR Office) at Eastwood Residences, Phase 9 Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 157 | GF | 4567010.65 |  | 4567010.65 | 4526007.35 |  | 4526007.35 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-600-1-2-11-511-004-146 | 29) Construction of 2-Storey Ynares Multi-Purpose Building(Day Care Center) at Eastwood Residences, Phase 6, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 180 | GF | 4215922.91 |  | 4215922.91 | 4176908.97 |  | 4176908.97 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-300-1-2-11-511-005-105 3000-300-1-2-11-511-005-100 | 30) Construction of Welcome Arc and Improvement of Ynares Multi-Purpose Covered Court at Brgy. Burgos and Brgy. Geronimo, Rodriguez, Rizal a.) Construction of Welcome Arc at King David Subd., Brgy. Burgos b.) Improvement Ynares of Multi-Purpose Covered Court at Greenrose 1, Brgy. Geronimo | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 60 | GF | 337,973.25 291,491.97 629,465.22 |  | 337,973.25 291,491.97 629,465.22 | 327,820.76 386,629.31 |  | 327,820.76 386,629.31 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-300-1-2-11-511-005-101 3000-300-1-2-11-511-005-104 | 31) Improvement of Ynares Multi-Purpose Covered Court and Construction of Demountable Stage at Brgy. San Isidro, Rodriguez, Rizal a.) Improvement of Ynares Multi-Purpose Covered Court at Southville 8B Phase 4, Brgy. San Isidro b.) Construction of Demountable Stage at Eastwood Residences Phase 8 & 8A Brgy. San Isidro | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 60 | GF | 907,328.30 227,148.81 1,134,477.11 |  | 907,328.30 227,148.81 1,134,477.11 | 886,841.86 224,647.19 |  | 886,841.86 224,647.19 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-300-1-2-11-511-005-102 | 32) Repair/Repainting of Ynares Multi-Purpose Covered Court at Montalban Heights, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 72 | GF | 1119118.22 | 1119118.22 |  | 1097108.39 | 1097108.39 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-15
3000-300-1-2-11-511-005-103 | 33) Construction of 2-Storey Ynares Multi-Purpose Building (HOA Office) at Eastwood Residences, Phase 9, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 156 | GF | 3471826.71 |  | 3471826.71 | 3437836.37 |  | 3437836.37 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
8000-000-1-1-51-001-002-219 | 34) Asphalt Overlaying (portion) of E. Rodriguez Avenue, Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 60 | GF | 5482321.56 | 5482321.56 |  | 5434317.14 | 5434317.14 |  | Engr. David Disimulacion Jr. Simon King | 2022-08-15
8000-000-1-1-51-001-002-223 | 35) Concreting (portion) of Catanduanes Avenue Carissa Homes East I, Brgy. Prinza, Teresa. Rizal | PEO |  | Public Bidding |  | 15-21 Aug 22 | 2022-08-22 |  | 2022-09-05 | 2022-09-09 | 2022-09-20 | 2022-09-26 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 100 | GF | 2547432.53 |  | 2547432.53 | 2517357.47 |  | 2517357.47 | Engr. David Disimulacion Jr. Simon King | 2022-08-15
2022-09-21
3000-600-1-2-11-511-004-112 | 1) Construction of 17x30m Ynares Multi-Purpose Covered Court at Vermont Royale Executive Village, Brgy. Mayamot, Antipolo City | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 162 | GF | 6824955.36 |  | 6824955.36 | 6773900.19 |  | 6773900.19 | Engr. David Disimulacion Jr. Simon King | 2022-09-02
8000-000-000-1-1-51-001-002-184 | 2) Asphalt Overlaying/Concrete Reblocking (portion) of Charles St., Bloomingdale Subd., Brgy. San Pedro, Angono, Rizal | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 80 | GF | 1680780.24 | 1680780.24 |  | 1655799.43 | 1655799.43 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-02
8000-000-000-1-1-51-001-002-186 8000-000-000-1-1-51-001-002-187 8000-000-000-1-1-51-001-002-188 8000-000-000-1-1-51-001-002-189 | 3) Asphalt Overlaying/Concrete Reblocking at Brgy. San Isidro, Angono, Rizal a) Asphalt Overlaying/Concrete Reblocking (portion) of Turquoise St., Medalva Hills Village Phase 2, Brgy. San Isidro b) Asphalt Overlaying/Concrete Reblocking (portion) of Abalone St., Medalva Hills Village Phase 2, Brgy. San Isidro c) Asphalt Overlaying/Concrete Reblocking (portion) of Topaz St., Medalva Hills Village Phase 2, Brgy. San Isidro d) Asphalt Overlaying/Concrete Reblocking (portion) of Sapphire St., Medalva Hills Village Phase 2, Brgy. San Isidro | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 120 | GF | 3,715,722.85 2,883,198.24 4,638,564.80 1,754,358.10 12,991,843.99 | 3,715,722.85 2,883,198.24 4,638,564.80 1,754,358.10 12,991,843.99 |  | 3,688,639.95 2,868,772.01 4,598,476.61 1,750,861.60 | 3,688,639.95 2,868,772.01 4,598,476.61 1,750,861.60 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-02
8000-000-000-1-1-51-001-002-190 8000-000-000-1-1-51-001-002-191 8000-000-000-1-1-51-001-002-192 8000-000-000-1-1-51-001-002-193 | 4) Asphalt Overlaying/Concrete Reblocking at Brgy. Mahabang Parang, Angono, Rizal a) Asphalt Overlaying/Concrete Reblocking (portion) of Marigold Street, Grandvalley Subd., Phase III, Brgy. Mahabang Parang b) Asphalt Overlaying/Concrete Reblocking (portion) of Rose Street, Grandvalley Subd., Phase III, Brgy. Mahabang Parang c) Asphalt Overlaying/Concrete Reblocking (portion) of Daisy Street, Grandvalley Subd., Phase III, Brgy. Mahabang Parang d) Asphalt Overlaying/Concrete Reblocking (portion) of Lily Street, Grandvalley Subd., Phase III, Brgy. Mahabang Parang | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 100 | GF | 1,085,157.84 3,607,868.89 1,427,041.45 1,417,984.10 7,538,052.18 | 1,085,157.84 3,607,868.89 1,427,041.45 1,417,984.10 7,538,052.18 |  | 1,082,531.98 3,564,201.76 1,417,891.01 1,415,285.64 | 1,082,531.98 3,564,201.76 1,417,891.01 1,415,285.64 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-02
8000-000-000-1-1-51-001-002-195 8000-000-000-1-1-51-001-002-196 | 5) Construction of Roadway Lightings at Brgy. Concepcion, Baras, Rizal a) Construction of Roadway Lightings at F. Manalo St.,Brgy. Concepcion b) Construction of Roadway Lightings at Raymundo Robles St., Brgy. Concepcion | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 60 | GF | 1,552,220.21 3,162,375.08 4,714,595.29 |  | 1,552,220.21 3,162,375.08 4,714,595.29 | 1,543,670.13 3,126,839.45 |  | 1,543,670.13 3,126,839.45 | Engr. David Disimulacion Jr. Simon King | 2022-09-02
3000-600-1-2-11-511-004-117 | 6) Construction of Ynares Multi-Purpose Bldg. (Day Care and Senior Citizen’s Office) at Brgy. Libid, Binangonan, Rizal | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 168 | GF | 6059138.4 |  | 6059138.4 | 6008099.91 |  | 6008099.91 | Engr. David Disimulacion Jr. Simon King | 2022-09-02
8000-000-1-1-51-001-002-201 8000-000-1-1-51-001-002-202 8000-000-1-1-51-001-002-203 8000-000-1-1-51-001-002-204 | 7) Construction of Roadway Lightings at Brgy. Mambog, Binangonan, Rizal a) Const ruction of Roadway Lightings at Champaca St., Brgy. Mambog b) Construction of Roadway Lightings at T. Ceñidoza St., Brgy. Mambog c) Construction of Roadway Lightings at Sitio Tabtab St., Brgy. Mambog d) Construction of Roadway Lightings at Lobarbio St., Brgy. Mambog | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 68 | GF | 1,460,555.47 1,937,060.92 1,364,385.87 1,170,055.08 5,932,057.34 |  | 1,460,555.47 1,937,060.92 1,364,385.87 1,170,055.08 5,932,057.34 | 1,449,622.59 1,992,700.24 1,354,165.28 1,156,578.87 |  | 1,449,622.59 1,992,700.24 1,354,165.28 1,156,578.87 | Engr. David Disimulacion Jr. Simon King | 2022-09-02
3000-600-1-2-11-511-004-120 | 8) Repair/Repainting of Ynares Multi-Purpose Covered Court, Comfort Room and Fence at Brgy. Libis, BInangonan, Rizal | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 85 | GF | 3506435.84 | 3506435.84 |  | 3471400.92 | 3471400.92 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-02
3000-600-1-2-11-511-004-121 | 9) Improvement of 2-Storey Ynares Multi-Purpose Building (Brgy. Hall) at Brgy. Ithan, Binangonan, Rizal | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 70 | GF | 808639 | 808639 |  | 793076.24 | 793076.24 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-02
3000-600-1-2-11-511-004-121 | 10) Repair/Repainting of Ynares Multi-Purpose Covered Court at Marick Subd., Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 65 | GF | 649649.4 | 649649.4 |  | 636781.29 | 636781.29 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-02
3000-600-1-2-11-511-004-127 | 11) Repair/Repainting of Ynares Multi-Purpose Covered Court at St. Joseph, Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 60 | GF | 1154333.32 | 1154333.32 |  | 1129632.65 | 1129632.65 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-02
3000-600-1-2-11-511-004-132 | 12) Repair/Repainting of Ynares Multi-Purpose Covered Court at Cainta Greenpark Village Zone 3, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 60 | GF | 639365.87 | 639365.87 |  | 625347.18 | 625347.18 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-02
3000-600-1-2-11-511-004-134 | 13) Repair/Repainting of Ynares Multi-Purpose Covered Court at Mercedes Executive Village, Brgy. San Andres, Cainta, Rizal | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 75 | GF | 1473600.52 | 1473600.52 |  | 1449596.04 | 1449596.04 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-02
3000-600-1-2-11-511-004-137 | 14) Repair/Repainting of Ynares Multi-Purpose Covered Court at Greenpark Village, Zone 4, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 60 | GF | 2146682.3 | 2146682.3 |  | 2118329.86 | 2118329.86 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-02
3000-600-1-2-11-511-004-138 | 15) Repair/Repainting of 2-Storey Ynares Multi-Purpose Building(Brgy. Hall) at Brgy. Looc, Cardona, Rizal | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 52 | GF | 673713.62 | 673713.62 |  | 660701.23 | 660701.23 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-02
3000-600-1-2-11-511-004 | 16) Improvement of Perimeter Fence (portion) at Brgy. Takungan, Pililla, Rizal | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 50 | GF | 1005448.88 | 1005448.88 |  | 984430.81 | 984430.81 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-02
8000-000-1-1-51-001-002-207 8000-000-1-1-51-001-002-208 8000-000-1-1-51-001-002-209 | 17) Asphalt Overlaying/Concrete Reblocking at Brgy. Niogan, Pililla, Rizal a) Asphalt Overlaying/Concrete Reblocking (portion) of Lomabas St., Brgy. Niogan b) Asphalt Overlaying/Concrete Reblocking (portion) of Road with Drainage Canal at Manuyag St., Brgy. Niogan c) Asphalt Overlaying/Concrete Reblocking (portion) of New Road, Brgy. Niogan | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 100 | GF | 1,457,120.40 2,630,412.02 4,447,303.34 8,534,835.76 | 1,457,120.40 2,630,412.02 4,447,303.34 8,534,835.76 |  | 1,448,340.44 2,585,145.74 4,438,339.26 | 1,448,340.44 2,585,145.74 4,438,339.26 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-02
8000-000-1-1-51-001-002-212 8000-000-1-1-51-001-002-213 8000-000-1-1-51-001-002-214 8000-000-1-1-51-001-002-215 | 18) Construction of Roadway Lightings at Brgy. Niogan, Pililla, Rizal a) Construction of Roadway Lightings at New Road St., Brgy. Niogan b) Construction of Roadway Lightings at Feliciano St., Villarojas St., and Villaran St., Brgy. Niogan c) Construction of Roadway Lightings at T. Daria, T. Daria Kaliwa, T. Daria Kanan and Kamay-Ari St., Brgy. Niogan d) Construction of Roadway Lightings at Judea Tower St., Judea E. Cruz Extension St., Brgy. Niogan | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 60 | GF | 1,419,960.59 1,019,646.78 1,904,941.31 579,926.73 4,924,475.41 |  | 1,419,960.59 1,019,646.78 1,904,941.31 579,926.73 4,924,475.41 | 1,409,352.95 1,010,172.68 1,989,567.44 575,269.42 |  | 1,409,352.95 1,010,172.68 1,989,567.44 575,269.42 | Engr. David Disimulacion Jr. Simon King | 2022-09-02
8000-000-1-1-51-001-002-220 | 19) Improvement of Drainage Canal at J.M. Catolos St., Brgy. Katipunan-Bayani, Tanay, Rizal | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 120 | GF | 4444614.37 |  | 4444614.37 | 4402272.08 |  | 4402272.08 | Engr. David Disimulacion Jr. Simon King | 2022-09-02
3000-600-1-2-11-511-004-147 | 20) Improvement of 2-Storey Ynares Multi-Purpose Bldg. (Daycare Center & Livelihood) at Blk. 17 Egypt St., Bagong Pag-Asa, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 57 | GF | 833682.43 |  | 833682.43 | 814680.48 |  | 814680.48 | Engr. David Disimulacion Jr. Simon King | 2022-09-02
3000-000-1-2-11-399-005-171 | 21) Construction of Link Bridge at Muzon Elem. School, Brgy. Muzon, Taytay, Rizal eligibility | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 70 | GF | 909071.17 |  | 909071.17 | 888099.32 |  | 888099.32 | Engr. David Disimulacion Jr. Simon King | 2022-09-02
3000-600-1-2-11-511-004-135 | 22) Construction of 2-Storey Ynares Multi-Purpose Building at Carissa Homes East II, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding | 2022-08-30 | 2-8 Sept 22 | 2022-09-09 |  | 2022-09-21 | 2022-09-27 | 2022-10-07 | 2022-10-13 | 2022-10-13 | 2022-10-21 | 2022-10-28 | 164 | GF | 4315795.51 |  | 4315795.51 | 4275621.13 |  | 4275621.13 | Engr. David Disimulacion Jr. Simon King | 2022-09-02
2022-10-04
8000-000-1-1-51-001-002-127 | 1) Improvement / Upgrading / Concreting of Road w/ Drainage Canal at San Lorenzo Ruiz Road, at Brgy. Kalayaan and Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 220 | GF | 26498046.98 |  | 26498046.98 | 26403008.62 |  | 26403008.62 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
3000-600-1-2-11-511-004-116 | 2) Construction of 13x30m Ynares Multi-Purpose Covered Court (Tennis Court) at Rainbow Village 1, Brgy. Kalayaan, Angono, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 120 | GF | 6941940.22 |  | 6941940.22 | 6890913.64 |  | 6890913.64 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
8000-000-1-1-51-001-002-133 | 3) Improvement / Concreting of Road with Drainage Canal & Const. of Box Culvert at Santos Compound, Brgy. Tatala, Binangonan, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 140 | GF | 5599596.38 |  | 5599596.38 | 5553411.38 |  | 5553411.38 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
8000-000-1-1-51-001-002-134 | 4) Concreting of Road with Drainage Canal at Antazo Compound, Sitio Villamayor, Brgy. Pag-asa, Binangonan, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 100 | GF | 3543677.47 |  | 3543677.47 | 3505802.14 |  | 3505802.14 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
8000-000-1-1-51-001-002-139 | 5) Asphalt Overlaying / Concrete Reblocking (portion) of Paralejas St., Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 80 | GF | 2123361.85 | 2123361.85 |  | 2092317.13 | 2092317.13 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-15
8000-000-1-1-51-001-002-140 | 6) Asphalt Overlaying of B. Mesa St., Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 80 | GF | 4231510.75 | 4231510.75 |  | 4191499.7 | 4191499.7 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-15
8000-000-1-1-51-001-002-197 | 7) Improvement of A. Bonifacio St., (portion) Binangonan, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 140 | GF | 7421721.77 |  | 7421721.77 | 7361610.33 |  | 7361610.33 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
3000-600-1-2-11-511-004-118 | 8) Construction of 12 x 20m Ynares Multi-Purpose Covered Court at Grand View Homes 2, Sitio Calvon, Brgy. Mambog, Binangonan, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 103 | GF | 5400019.42 |  | 5400019.42 | 5351007.42 |  | 5351007.42 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
8000-000-1-1-51-001-002-199 | 9) Concreting of Roads with Drainage Canal at Picones I Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 148 | GF | 7263071.7 |  | 7263071.7 | 7204019.27 |  | 7204019.27 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
8000-000-1-1-51-001-002-200 | 10) Construction of Drainage Canal and Concrete Overlaying of Tabtab St., Brgy. Mambog, Binangonan, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 120 | GF | 5564587.4 |  | 5564587.4 | 5515514.35 |  | 5515514.35 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
9000-900-1-0-40-001-001-003 | 11) Construction of Slope Protection (portion) and Concreting of Creek Bed of Creek at Purok 3, Brgy. Bombong, Binangonan, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 90 | GF | 1449900.26 |  | 1449900.26 | 1425548.95 |  | 1425548.95 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
3000-000-1-2-11-399-005-152 | 12) Construction of School Compound Lightings at Painaan Elementary School, Baras Heroes Ville Annex, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 44 | GF | 1318956.83 |  | 1318956.83 | 1290861.12 |  | 1290861.12 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
8000-000-1-1-51-001-002-147 | 13) Concrete Reblocking of various Roads at Mercedes Executive Village, Brgy. San Andres, Cainta, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 180 | GF | 11999999.33 |  | 11999999.33 | 11918917.65 |  | 11918917.65 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
8000-000-1-1-51-001-002-162 | 14) Construction of Drainage Canal at G. Del Pilar St., Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 190 | GF | 11096711.18 |  | 11096711.18 | 11005759.42 |  | 11005759.42 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
8000-000-1-1-51-001-002-218 | 15) Asphalt Overlaying / Concrete Reblocking (portion) of Sumulong St., Brgy. Guinayang, San Mateo, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 80 | GF | 1825460.74 | 1825460.74 |  | 1796412.67 | 1796412.67 |  | Engr. David Disimulacion Jr. Simon King | 2022-09-15
3000-000-1-2-11-399-005-147 | 16) Construction of Concrete Bleachers with Canopy of School Ground at Patricio Jarin Elem. School Brgy. San Isidro, Tanay, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 120 | SEF | 4499057.41 |  | 4499057.41 | 4454047.96 |  | 4454047.96 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
9000-900-1-0-40-001-001-005 | 17) Construction of Slope Protection at Rizal Provincial Motorpool,Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 80 | GF | 2256752.76 |  | 2256752.76 | 2227712.72 |  | 2227712.72 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
9000-900-1-0-40-002-005-018 | 18) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Palmera Homes III, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 64 | GF | 1518240.59 |  | 1518240.59 | 1491109.24 |  | 1491109.24 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
8000-000-1-1-51-001-002-125 | 19) Concreting of Local Road at ACME to Coral 3, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 200 | GF | 18951843.36 |  | 18951843.36 | 18857060.54 |  | 18857060.54 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
8000-000-1-1-51-001-002-227 | 20) Construction of Bridge I along Roman Roxas Road, Teresa, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 312 | GF | 90567369.19 |  | 90567369.19 | 90397334.04 |  | 90397334.04 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
9000-900-1-0-40-001-001-006 | 21) Construction of Slope Protection (portion) of Teresa River (near Guido Pangilinan's Residence) Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding | 2022-09-12 | 15-21-Sep-22 | 2022-09-22 |  | 2022-10-04 | 2022-10-10 | 2022-10-19 | 2022-10-25 | 2022-10-25 | 2022-10-31 | 2022-11-09 | 160 | GF | 4444089.53 |  | 4444089.53 | 4401054.15 |  | 4401054.15 | Engr. David Disimulacion Jr. Simon King | 2022-09-15
2022-10-24
8000-000-1-1-51-001-002-185 | 1) Concreting of Road with Drainage Canal at Sitio Hangganan, Brgy. Pag-Asa, Binangonan and Brgy. San Pedro, Angono, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 120 | GF | 5056352.86 |  | 5056352.86 | 5008315.66 |  | 5008315.66 | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-000-1-2-11-399-005-156 | 2) Repair/Repainting of Ynares School Buildings at Bombong Elem. School, Brgy. Bombong, Binangonan, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 120 | SEF | 2669823.53 | 2669823.53 |  | 2637289.37 | 2637289.37 |  | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-000-1-2-11-399-005-157 | 3) Repair/Repainting of Ynares School Buildings at Doña Susana Madrigal Elem. School, Brgy. Pantok, Binangonan, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 272 | SEF | 12095117.85 | 12095117.85 |  | 12010099.78 | 12010099.78 |  | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-000-1-2-11-399-005-158 | 4) Repair/Repainting of Ynares School Building at Mahabang Parang Elem. School, Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 45 | SEF | 1001585.25 | 1001585.25 |  | 979511.17 | 979511.17 |  | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-000-1-2-11-399-005-159 3000-000-1-2-11-399-005-168 | 5) Construction of Hand Washing Facility at Brgy. Darangan & Brgy. Calumpang, Binangonan, Rizal a) Construction of Hand Washing facility at Darangan Elem. School, Brgy. Darangan b) Construction of Hand Washing Facility at Calumpang Elem. School, Brgy. Calumpang | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 90 | SEF | 334,133.69 334,133.69 668,267.38 |  | 334,133.69 334,133.69 668,267.38 | 326,554.22 326,554.22 |  | 326,554.22 326,554.22 | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
8000-000-1-1-51-001-002-145 | 6) Improvement of Road at P. Burgos St., Brgy. Sta. Rosa, Cainta, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 140 | GF | 5490420.07 |  | 5490420.07 | 5438923.04 |  | 5438923.04 | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
8000-000-1-1-51-001-002-146 | 7) Improvement of Road at M.H. Del Pilar St., Brgy. Sta. Rosa, Cainta, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 120 | GF | 4459794.02 |  | 4459794.02 | 4411718.91 |  | 4411718.91 | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-000-1-2-11-399-005-161 3000-000-1-2-11-399-005-162 | 8) Construction of Hand Washing Facility at Brgy. San Isidro & Brgy. San Andres, Cainta, Rizal a) Construction of Hand Washing Facility at F.P. Felix Mem. National High School (Karangalan Annex) Brgy. San Isidro b) Construction of Hand Washing Facility at Kabisig Elem. School, Brgy. San Andres | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 80 | SEF | 320,221.19 318,777.44 638,998.63 |  | 320,221.19 318,777.44 638,998.63 | 311,668.17 310,236.12 |  | 311,668.17 310,236.12 | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-600-1-2-11-511-004-136 3000-000-1-2-11-399-005-163 | 9) Repair/Repainting of Ynares Multi-Purpose Covered Court and Construction of Hand Washing Facility at Brgy. San Juan, Cainta, Rizal a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Apricot St., Phase 5C, Cainta Greenland Exec. Village, Brgy. San Juan b) Construction of Hand Washing | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 109 | GF SEF | 1,471,774.11 323,554.95 1,795,329.06 | 1471774.11 | 323554.95 | 1,433,906.95 320,868.15 | 1433906.95 | 320868.15 | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
9000-900-1-0-40-002-005-147 | 10) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Ynares Multi-Purpose Covered Court at Vista Verde Executive Village Phase 3, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 70 | GF | 1226068.2 |  | 1226068.2 | 1202183.65 |  | 1202183.65 | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-000-1-2-11-399-005-164 | 11) Construction of Ynares Stage at Morong National High School-SHS Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 76 | SEF | 1791600.78 |  | 1791600.78 | 1765587.37 |  | 1765587.37 | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-000-1-2-11-399-005-165 | 12) Construction of Stage at Pulong Kumanoy Elem. School, Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 72 | SEF | 1478844.49 |  | 1478844.49 | 1448795.29 |  | 1448795.29 | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-000-1-2-11-399-005-166 | 13) Repair/Repainting of Ynares School Buildings at Silangan National High School, Brgy. Silangan, San Mateo, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 90 | SEF | 4060504.16 | 4060504.16 |  | 4015487.71 | 4015487.71 |  | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-000-1-2-11-399-005-167 | 14) Repair/Repainting of Ynares Multi-Purpose Covered Court at San Mateo Elem. School, Brgy. Sta. Ana, San Mateo, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 30 | SEF | 456381.36 | 456381.36 |  | 444412.68 | 444412.68 |  | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-000-1-2-11-399-005-168 | 15) Improvement of Ynares Multi-Purpose Covered Court at Tanay-Sampaloc Integrated National High School, Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 130 | SEF | 5036138.67 |  | 5036138.67 | 4985097.59 |  | 4985097.59 | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-000-1-2-11-399-005-173 | 16) Improvement of Perimeter Fence & Gate at Muzon Elem. School, Brgy. Muzon, Taytay, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 45 | SEF | 671413.98 |  | 671413.98 | 654379.08 |  | 654379.08 | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-000-1-2-11-399-005-169 | 17) Repair/Repainting of Ynares School Building at Sta. Ana Elem. School, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 60 | SEF | 2054864.94 | 2054864.94 |  | 2019857.39 | 2019857.39 |  | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
8000-000-1-1-51-001-002-221 | 18) Concreting of Road with Drainage Canal of Road Lot 14 Purok 7, Lupang Arenda, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 140 | GF | 5971936.1 |  | 5971936.1 | 5921896.29 |  | 5921896.29 | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
8000-000-1-1-51-001-002-222 | 19) Concreting of Road with Drainage Canal of Road Lot 23 Purok 7, Lupang Arenda, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 160 | GF | 7697485.4 |  | 7697485.4 | 7635013.49 |  | 7635013.49 | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-000-1-2-11-399-005 | 20) Construction of 4-Storey, 8-Rooms Ynares School Building at Kapalaran Elem. School, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 250 | SEF | 30952088.37 |  | 30952088.37 | 30797017.43 |  | 30797017.43 | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-000-1-2-11-399-005-172 | 21) Installation of Safety Grills (Enclosure) for 4-Storey Ynares School Buildings at Rosario Ocampo Elem. School, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 60 | SEF | 1323419.6 |  | 1323419.6 | 1301400.97 |  | 1301400.97 | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
3000-000-1-2-11-399-005-154 | 22) Repair/Repainting of Ynares School Buildings at San Isidro Elem. School, Brgy. San Isidro, Taytay, Rizal | PEO |  | Public Bidding | 2022-09-30 | 4-10-Oct-22 | 2022-10-11 |  | 2022-10-24 | 2022-10-28 | 2022-11-08 | 2022-11-11 | 2022-11-11 | 2022-11-20 | 2022-12-01 | 100 | SEF | 5547894.52 | 5547894.52 |  | 5500811.93 | 5500811.93 |  | Engr. David Disimulacion Jr. Simon King |  |  | 4-Oct-22
2022-11-21
3000-600-1-2-11-511-004-150 | 1) Construction of 2-Storey Ynares Multi-Purpose Bldg. (HOA Office) at Doña Justa Guido Phase 2, Brgy. San Roque, Angono, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 156 | GF | 4699662.68 | 4699662.68 |  | 4662602.08 | 4662602.08 |  | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
8000-800-1-1-51-001-002 | 2) Asphalt Overlaying/Concrete Reblocking (portion) of Magtanggol St., Brgy. Rizal, Baras, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 60 | GF | 948499.56 |  | 948499.56 | 933411.67 |  | 933411.67 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
8000-000-1-1-51-001-002-244 | 3) Concreting of Various Roads at Sitio Lapaan, Brgy. Concepcion, Baras, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 90 | GF | 2251860.9 |  | 2251860.9 | 2224785.47 |  | 2224785.47 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-000-1-2-11-399-005-182 | 4) Construction of 3-Storey 6-Rooms Ynares School Building at Darangan Elem. School, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 250 | GF | 24452985 |  | 24452985 | 24344893.13 |  | 24344893.13 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
8000-000-1-1-51-001-002-245 | 5) Improvement of Grana St., Brgy. Macamot, Binangonan, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 90 | GF | 3298616.63 |  | 3298616.63 | 3271587.28 |  | 3271587.28 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-000-1-2-11-399-005-178 | 6) Upgrading of Electrical Service Entrance and Feeder Wires of Vicente Madrigal National High School, Brgy. Palangoy, Binangonan, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 80 | GF | 4988727.94 |  | 4988727.94 | 4949685.96 |  | 4949685.96 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-600-1-2-11-511-004-148 | 7) Improvement of Perimeter Fence of Open Space at Greenpark Village Zone 4, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 90 | GF | 4238565.48 |  | 4238565.48 | 4204071.69 |  | 4204071.69 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-000-1-2-11-399-005-175 | 8) Improvement of Perimeter Fence and Gate at Balanti Elem. School, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 90 | GF | 1643145.38 |  | 1643145.38 | 1621097 |  | 1621097 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
8000-000-1-1-51-001-002-247 | 9) Concreting (portion) of San Francisco St., Brookside Hills Subd., Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 140 | GF | 4332238.55 |  | 4332238.55 | 4298200.37 |  | 4298200.37 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-600-1-2-11-511-004-152 | 10) Improvement of Ynares Multi-Purpose Covered Court at Brgy. San Roque, Cardona, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 48 | GF | 1073879.62 |  | 1073879.62 | 1052887.56 |  | 1052887.56 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-000-1-2-11-399-005-186 | 11) Improvement of Ynares Multi-Purpose Covered Court at Looc Elementary School, Brgy. Looc, Cardona, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 48 | GF | 1231435.73 |  |  | 1208411.56 |  | 1208411.56 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
9000-900-1-0-40-001-001-006 | 12) Construction of Slope Protection (portion) of Creek, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 100 | GF | 3549909.06 |  |  | 3522900.54 |  | 3522900.54 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-600-1-2-11-511-004-153 | 13) Improvement of Ynares Multi-Purpose Covered Court at Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 52 | GF | 607824.28 |  |  | 592804.34 |  | 592804.34 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-600-1-2-11-511-004-154 | 14) Improvement of Ynares Multi-Purpose Covered Court at Sitio Pulong Ligaya, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 45 | GF | 828192.48 |  |  | 828517.21 |  | 828517.21 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-600-1-2-11-511-004-155 | 15) Improvement of Ynares Multi-Purpose Covered Court at Sitio Naglabas, Brgy. Pagkalinawan, Jalajala, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 45 | GF | 828192.48 |  |  | 808097.32 |  | 808097.32 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
8000-000-1-1-51-001-002-248 | 16) Improvement of Morong-San Guillermo Road, Morong, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 140 | GF | 12998218.73 |  |  | 12923601.34 |  | 12923601.34 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-600-1-2-11-511-004-149 | 17) Improvement of Morong Town Plaza, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 128 | GF | 4696593.24 |  |  | 4658579.64 |  | 4658579.64 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-000-1-2-11-399-005-177 | 18) Construction of Elevated Water Tank and Installation of Distribution Lines at Pulong Kumanoy Elementary School, Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 60 | GF | 1327765.88 |  |  | 1303547.46 |  | 1303547.46 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-000-1-2-11-399-005-184 | 19) Construction of 3-Storey 9-Rooms Ynares School Building at Malaya Integrated National High School, Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 260 | GF | 27623035.95 |  |  | 27504125.88 |  | 27504125.88 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
8000-000-1-1-511-001-002-249 | 20) Concreting of Road with Slope Protection at Sitio Mulawin, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 120 | GF | 3172606.7 |  |  | 3145587.52 |  | 3145587.52 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-600-1-2-11-511-004-159 | 21) Construction of 17 x 30m Ynares Multi-Purpose Covered Court at Estrella Heights Subd., Brgy. Burgos, Montalban, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 148 | GF | 6396868.16 |  |  | 6357534.33 |  | 6357534.33 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-600-1-2-11-511-004-161 | 22) Improvement of Ynares Multi-Purpose Covered Court at Christine Ville Subd., Brgy. San Jose, Montalban, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 110 | GF | 2515771.92 |  | 2515771.92 | 2486698.85 |  | 2486698.85 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-600-1-2-11-511-004-157 3000-600-1-2-11-511-004-162 | 23) Construction of Ynares Stage and Improvement of Ynares Multi-Purpose Covered Court at Brgy. San Isidro, Montalban, Rizal a) Construction of Ynares Stage at Eastwood Residences Phase 6A, Brgy. San Isidro b) Improvement of Ynares Multi-Purpose Covered Court at Eastwood Residences Phase 4, Brgy. San Isidro | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 80 | GF | 1,232,256.78 226,851.88 1,459,108.66 |  | 1,232,256.78 226,851.88 1,459,108.66 | 1,212,211.73 226,788.82 |  | 1,212,211.73 226,788.82 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-600-1-2-11-511-004-160 | 24) Improvement of Ynares Multi-Purpose Covered Court at Doña Maria Subd., Brgy. Burgos, Montalban, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 48 | GF | 1323262.94 |  | 1323262.94 | 1298218.29 |  | 1298218.29 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-000-1-2-11-399-005-176 | 25) Concreting of School Ground at Burgos National High School-Sorrento Extension, Sorrento Village, Brgy. Burgos, Montalban, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 60 | GF | 1005740.39 |  | 1005740.39 | 986718.29 |  | 986718.29 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-600-1-2-11-511-004-151 | 26) Improvement/Extension of 2-Storey Ynares Multi-Purpose Bldg. (Brgy. Hall) at Brgy. Sto. Niño, San Mateo, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 191 | GF | 5286819.06 |  | 5286819.06 | 5243800.96 |  | 5243800.96 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-600-1-2-11-511-004-164 | 27) Improvement of Ynares Multi-Purpose Covered Court at Villa San Mateo 2, Brgy. Guitnang Bayan II, San Mateo, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 60 | GF | 2041740.1 |  | 2041740.1 | 2013443.03 |  | 2013443.03 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
8000-000-1-1-51-001-002-254 | 28) Improvement of Drainage Canal (portion) at Damaso Reyes St., Brgy. San Isidro, Tanay, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 120 | GF | 4898497.28 |  | 4898497.28 | 4861479.32 |  | 4861479.32 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
8000-000-1-1-51-001-002-250 | 29) Concreting of Road with Drainage Canal of Road Lot 1 Purok 2, Lupang Arenda, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 120 | GF | 4443954.07 |  | 4443954.07 | 4408971.45 |  | 4408971.45 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
8000-000-1-1-51-001-002-257 | 30) Concreting of Road with Drainage Canal of Road Lot 2 Purok 2, Lupang Arenda, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 112 | GF | 3893095.44 |  | 3893095.44 | 3865001.75 |  | 3865001.75 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
8000-000-1-1-51-001-001-001-05 | 31) Installation of Water Distribution Line at Philippine National Police, Rizal Police Provincial Office, Cabrera Rd., Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 90 | GF | 1419282.78 | 1419282.78 |  | 1401197.97 | 1401197.97 |  | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-000-1-2-11-399-005-185 | 32) Construction of 3-Storey 9-Rooms Ynares School Building at Abuyod Elem. School, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 280 | GF | 27827753.01 |  | 27827753.01 | 27706687.57 |  | 27706687.57 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
3000-600-1-2-11-511-004-166 | 33) Improvement of Ynares Multi-Purpose Covered Court at Carissa Homes East II, Brgy. San Gabriel, Teresa, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 80 | GF | 2600858.12 |  | 2600858.12 | 2570758.29 |  | 2570758.29 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
9000-900-1-0-40-001-001-007 | 34) Construction of Slope Protection along Teresa River,Brgy. San Roque, Teresa, Rizal | PEO |  | Public Bidding | 2022-10-28 | 2-8-Nov-22 | 2022-11-09 |  | 2022-11-21 | 2022-11-25 | 2022-12-06 | 2022-12-09 | 2022-12-09 | 2022-12-21 | 2022-12-26 | 80 | GF | 1556789.63 |  | 1556789.63 | 1535699.37 |  | 1535699.37 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-10-28
| 2022-12-05 | [15 empty] | GF
9000-900-1-0-40-002-005-019 | 1) Construction of Handwashing Facilities at Various Schools Within Municipality of Angono, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 136 | GF | 1627039.49 |  | 1627039.49 | 1604709.86 |  | 1604709.86 |  |  |  | 2022-11-16
9000-900-1-0-40-002-005-020 | 2) Construction of Handwashing Facility at Angono Elem. School, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 45 | GF | 317728.27 |  | 317728.27 | 305713.01 |  | 305713.01 |  |  |  | 2022-11-16
8000-000-1-1-51-001-002-228 | 3) Concreting (portion) of Farm to Market Road at Sitio Kaytangab-Kaytambo, Brgy. San Jose, Baras, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 60 | GF | 830539.91 |  | 830539.91 | 811501.35 |  | 811501.35 |  |  |  | 2022-11-16
8000-000-1-1-51-001-002-243 | 4) Concreting (portion) of Norberto Robles Road (formerly known as Maharlika Road), Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 60 | GF | 999778.23 |  | 999778.23 | 978685.9 |  | 978685.9 |  |  |  | 2022-11-16
9000-900-1-0-40-002-005-022 | 5) Construction of Handwashing Facilities at Various Schools Within Municipality of Binangonan, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 132 | GF | 1561711.34 |  | 1561711.34 | 1539700.57 |  | 1539700.57 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
3000-000-1-2-11-399-005-180 | 6) Improvement of Principal’s Office and Computer Room at Talim Elem. School, Brgy. Habagatan, Binangonan, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 48 | GF | 411408 |  | 411408 | 398245.09 |  | 398245.09 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
9000-900-1-0-40-002-005-023 9000-900-1-0-40-002-005-26 | 7) Construction of Hand Washing Facility at Pila-Pila Elem. School, Brgy. Pila-Pila, Binangonan, Rizal a) Construction of Hand Washing Facility at Pila-Pila Elem. School, Brgy. Pila-Pila b) Construction of Hand Washing Facility at Margarito A. Duavit Memorial National High School, Brgy. Pila-Pila | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 80 | GF | 343,619.65 276,160.71 619,757.25 |  | 343,619.65 276,160.71 619,757.25 | 336,725.02 226,992.66 |  | 336,725.02 226,992.66 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
9000-900-1-0-40-002-005-027 9000-900-1-0-40-002-005-028 | 8) Construction of Hand Washing Facility at Brgy. Macamot and Brgy. Ithan, Binangonan, Rizal a) Construction of Hand Washing Facility at Macamot Elem. School, Brgy. Macamot b) Construciton of Hand Washing Facility at Ithan Elem. School, Brgy. Ithan | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 80 | GF | 320,305.19 319,452.06 639,757.25 |  | 320,305.19 319,452.06 639,757.25 | 313,325.73 312,472.60 |  | 313,325.73 312,472.60 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
3000-000-1-2-11-399-005-183 | 9) Installation of Safety Grills (enclosure) on 4-Storey 12-Rooms Ynares School Building at Darangan Elem. School, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 60 | GF | 721545.25 | 721545.25 |  | 706483.53 | 706483.53 |  | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
8000-000-1-1-51-001-002-252 8000-000-1-1-51-001-002-253 | 10) Construction of Drainage Canal of Road at Brgy. Kaytome, Binangonan, Rizal a) Construction of Drainage Canal of Road at Purok 3, Brgy. Kaytome b) Construction of Drainage Canal of Road at Purok 4, Brgy. Kaytome | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 120 | GF | 2,699.207.43 595,099.04 3.294,306.47 |  | 2,699.207.43 595,099.04 3.294,306.47 | 2,675.327.04 594,316.26 |  | 2,675.327.04 594,316.26 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
8000-000-1-1-51-001-002-246 | 11) Improvement of Road at Purok 3, Brgy. Limbon-Limbon, Binangonan, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 60 | GF | 995629.72 |  | 995629.72 | 979602.73 |  | 979602.73 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
9000-900-1-0-40-002-005-024 | 12) Construction of Hand Washing Facilities at Various Schools Within Municipality of Cainta, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 136 | GF | 1480787.02 |  | 1480787.02 | 1461789.64 |  | 1461789.64 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
3000-000-1-2-11-399-005-174 | 13) Concreting of Grounds with Drainage Canal at St. Joseph Elem. School, Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 60 | GF | 802573.41 |  | 802573.41 | 782517.44 |  | 782517.44 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
9000-900-1-0-40-002-005-029 3000-000-1-2-11-399-005-181 | 14) Construction of Hand Washing Facility and Improvement of Library at Brgy. San Juan and Brgy. Dolores, Cainta and Taytay, Rizal a) Co nstruction of Hand Washing Facility at Planters Elem. School, Brgy. San Juan, Cainta, Rizal b) Imp rovement of Library at Existing DPWH Building, Dolores Elem. School, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 60 | GF | 325.392.13 361,982.61 687,374.74 |  | 325.392.13 361,982.61 687,374.74 | 318.3400.85 354,917.78 |  | 318.3400.85 354,917.78 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
9000-900-1-0-40-002-005-025 | 15) Construction of Hand Washing Facilities at Various Schools Within Municipality of Cardona, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 136 | GF | 1630858.21 |  | 1630858.21 | 1616816.55 |  | 1616816.55 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
9000-900-1-0-40-002-005-030 | 16) Construction of Hand Washing Facilities at Various Schools Within Municipality of Jalajala, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 136 | GF | 1706689.95 |  | 1706689.95 | 1681568.57 |  | 1681568.57 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
8000-000-1-1-51-001-002-229 8000-000-1-1-51-001-002-230 | 17) Concreting (portion) of Patag St. and Flores St., at Brgy. Bayugo, Jalajala, Rizal a) Concreting (portion) of Patag St., Brgy. Bayugo b) Concreting (portion) at Flores St., Brgy. Bayugo | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 60 | GF | 1377204.9 |  | 1377204.9 | 1357197.23 |  | 1357197.23 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
3000-000-1-2-11-399-005-179 | 18) Construction of Drainage Canal at Punta Elem. School, Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 60 | GF | 474334.35 |  | 474334.35 | 460914.09 |  | 460914.09 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
9000-900-1-0-40-002-005-031 | 19) Construction of Hand Washing Facilities at Various Schools Within Municipality of Morong, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 136 | GF | 1597260.3 |  | 1597260.3 | 1574203.75 |  | 1574203.75 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
9000-900-1-0-40-002-005-033 | 20) Construction of Hand Washing Facilities at Various Schools Within Municipality of Montalban, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 136 | GF | 1593650.95 |  | 1593650.95 | 1568600.2 |  | 1568600.2 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
3000-600-1-2-11-511-004-156 | 21) Improvement of Ynares Multi-Purpose Covered Court and Stage at Southville 8C, Phase 1K2, Brgy. San Jose, Montalban, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 60 | GF | 782067.1 |  | 782067.1 | 764023.35 |  | 764023.35 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
3000-600-1-2-11-511-004-158 | 22) Construction of Welcome Arc (2-Units) at Sub-Urban Village Phase 1, L2 Area 6, Brgy. San Jose, Montalban, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 85 | GF | 728171.98 |  | 728171.98 | 712107.65 |  | 712107.65 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
9000-900-1-0-40-002-005-034 | 23) Construction of Hand Washing Facilities at Various Schools Within Municipality of San Mateo, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 136 | GF | 1579776.15 |  | 1579776.15 | 1558646.14 |  | 1558646.14 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
3000-600-1-2-11-511-004-163 | 24) Improvement of Diaz Multi-Purpose Covered Court at Bancom Life Homes, Brgy. Gulod Malaya, San Mateo, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 60 | GF | 1161956.59 |  | 1161956.59 | 1142875.94 |  | 1142875.94 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
3000-600-1-2-11-511-004-165 | 25) Improvement of Ynares Multi-Purpose Covered Court at Liamson Subd., Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 45 | GF | 389335.77 |  | 389335.77 | 376347.29 |  | 376347.29 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
9000-900-1-0-40-002-005-035 | 26) Construction of Hand Washing Facilities at Various Schools Within Municipality of Tanay, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 136 | GF | 1825732.87 |  | 1825732.87 | 1797789.34 |  | 1797789.34 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
9000-900-1-0-40-002-005-036 | 27) Construction of Hand Washing Facilities at Various Schools Within Municipality of Taytay, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 136 | GF | 1600294.94 |  | 1600294.94 | 1578214.14 |  | 1578214.14 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
9000-900-1-0-40-002-005-037 | 28) Construction of Hand Washing Facilities at Various Schools Within Municipality of Teresa, Rizal | PEO |  | Public Bidding |  | 16-22-Nov-22 | 2022-11-23 |  | 2022-12-05 | 2022-12-12 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 2022-01-04 | 2022-01-11 | 136 | GF | 1598188.88 |  | 1598188.88 | 1573179.49 |  | 1573179.49 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-11-16
2022-12-27
8000-000-1-1-51-001-002-125 | 1) Improvement/Rehabilitation of Floodway East Embankment Road,Cainta-Taytay, Rizal | PEO |  | Public Bidding | 2022-12-02 | 8-12-Dec-22 | 2022-12-13 |  | 2022-12-27 | 2022-01-02 | 2022-01-13 | 2022-01-20 | 2022-01-20 | 2022-01-27 | 2022-01-04 | 72 | GF | 20887720.08 |  | 20887720.08 | 20772616.75 |  | 20772616.75 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-12-08
8000-000-1-1-51-001-002-124 | 2) Improvement of Velasquez St. Extension, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding | 2022-12-02 | 8-12-Dec-22 | 2022-12-13 |  | 2022-12-27 | 2022-01-02 | 2022-01-13 | 2022-01-20 | 2022-01-20 | 2022-01-27 | 2022-01-04 | 56 | GF | 9112270.92 |  | 9112270.92 | 9034202.66 |  | 9034202.66 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-12-08
8000-000-1-1-51-001-002-255 | 1A ) Construction of Road with Slope Protection Taytay-Angono-Binangonan Diversion Road (Binangonan Section), Binangonan Rizal | PEO |  | Public Bidding | 2022-12-02 | 8-14-Dec-22 | 2022-12-15 |  | 2022-12-27 | 2022-01-02 | 2022-01-13 | 2022-01-20 | 2022-01-20 | 2022-01-27 | 2022-01-04 | 440 | GF | 255498515.66 |  | 255498515.66 | 255334683.55 |  | 255334683.55 | Engr. David Disimulacion Jr. Simon King |  |  | 2022-12-08
Total Alloted Budget of On-going Procurement Activities
| Prepared by: | [8 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
|  | MA. TERESA E. LASQUETY | [12 empty] | Engr. LUISITO G. MUNSOD | [8 empty] | HON. NINA RICCI A. YNARES
|  | Head - BAC Secretariat | [12 empty] | BAC Chairperson | [8 empty] | Governor